## Result 1 (2)
PROJ_ID | WBS_ID | BCWP | BCWS | EAC_WORK_QTY | ETC | ETC_WORK_QTY | PERFM_WORK_QTY | SCHED_WORK_QTY | COMPLETE_CNT | ACTIVE_CNT | NOTSTARTED_CNT | BASE_COMPLETE_CNT | BASE_ACTIVE_CNT | BASE_NOTSTARTED_CNT | ACT_DRTN_HR_CNT | TOTAL_DRTN_HR_CNT | BASE_DRTN_HR_CNT | REMAIN_DRTN_HR_CNT | TOTAL_FLOAT_HR_CNT | ACT_END_DATE | ACT_START_DATE | BASE_END_DATE | BASE_START_DATE | REEND_DATE | RESTART_DATE | ACT_THIS_PER_WORK_COST | ACT_THIS_PER_WORK_QTY | ACT_THIS_PER_EQUIP_COST | ACT_THIS_PER_EQUIP_QTY | ACT_THIS_PER_MAT_COST | ACT_EQUIP_COST | ACT_EXPENSE_COST | ACT_MAT_COST | ACT_WORK_COST | ACT_EQUIP_QTY | ACT_WORK_QTY | BASE_EQUIP_COST | BASE_EXPENSE_COST | BASE_MAT_COST | BASE_WORK_COST | BASE_EQUIP_QTY | BASE_WORK_QTY | REMAIN_WORK_QTY | REMAIN_EQUIP_COST | REMAIN_EXPENSE_COST | REMAIN_MAT_COST | REMAIN_WORK_COST | REMAIN_EQUIP_QTY | CREATE_DATE | CREATE_USER | UPDATE_DATE | UPDATE_USER | DELETE_SESSION_ID | DELETE_DATE
368 | 3684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 353 | 0 | 0 | 353 | 0 | 5630 | 5630 | 5630 | 0 |  |  | 2024-12-31 17:00:00 | 2023-03-16 07:00:00 | 2024-12-31 17:00:00 | 2023-03-16 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
368 | 3683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 353 | 0 | 0 | 353 | 0 | 5630 | 5630 | 5630 | 0 |  |  | 2024-12-31 17:00:00 | 2023-03-16 07:00:00 | 2024-12-31 17:00:00 | 2023-03-16 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
368 | 3682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 353 | 0 | 0 | 353 | 0 | 5630 | 5630 | 5630 | 0 |  |  | 2024-12-31 17:00:00 | 2023-03-16 07:00:00 | 2024-12-31 17:00:00 | 2023-03-16 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
368 | 3681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 353 | 0 | 0 | 353 | 0 | 5630 | 5630 | 5630 | 0 |  |  | 2024-12-31 17:00:00 | 2023-03-16 07:00:00 | 2024-12-31 17:00:00 | 2023-03-16 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
368 | 3680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1412 | 0 | 0 | 1412 | 0 | 5630 | 5630 | 5630 | 0 |  |  | 2024-12-31 17:00:00 | 2023-03-16 07:00:00 | 2024-12-31 17:00:00 | 2023-03-16 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
418 | 4033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 352 | 0 | 0 | 352 | 0 | 5080 | 5080 | 5080 | 0 |  |  | 2024-06-30 11:00:00 | 2022-11-15 11:00:00 | 2024-06-30 11:00:00 | 2022-11-15 11:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
418 | 4032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 352 | 0 | 0 | 352 | 0 | 5770 | 5770 | 5770 | 2610 |  |  | 2023-08-30 11:00:00 | 2021-10-17 11:00:00 | 2023-08-30 11:00:00 | 2021-10-17 11:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
418 | 4031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 206 | 0 | 0 | 206 | 0 | 5880 | 5880 | 5880 | 3650 |  |  | 2023-05-01 11:00:00 | 2021-06-01 07:00:00 | 2023-05-01 11:00:00 | 2021-06-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
418 | 4030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 910 | 0 | 0 | 910 | 0 | 9530 | 9530 | 9530 | 0 |  |  | 2024-06-30 11:00:00 | 2021-06-01 07:00:00 | 2024-06-30 11:00:00 | 2021-06-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
518 | 4585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
518 | 4584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 511 | 0 | 0 | 511 | 0 | 3980 | 3980 | 3980 | 0 |  |  | 2022-04-16 17:00:00 | 2021-01-07 07:00:00 | 2022-04-16 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
518 | 4583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
518 | 4582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
518 | 4581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
518 | 4580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 511 | 0 | 0 | 511 | 0 | 3980 | 3980 | 3980 | 0 |  |  | 2022-04-16 17:00:00 | 2021-01-07 07:00:00 | 2022-04-16 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
520 | 4984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
520 | 4855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 511 | 0 | 0 | 511 | 0 | 3980 | 3980 | 3980 | 0 |  |  | 2022-04-16 17:00:00 | 2021-01-07 07:00:00 | 2022-04-16 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
520 | 4854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
520 | 4853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
520 | 4852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
520 | 4851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 511 | 0 | 0 | 511 | 0 | 3980 | 3980 | 3980 | 0 |  |  | 2022-04-16 17:00:00 | 2021-01-07 07:00:00 | 2022-04-16 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
521 | 5118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 0 | 0 | 34 | 0 | 320 | 340 | 320 | 60 |  |  | 2022-12-07 17:00:00 | 2022-10-30 07:00:00 | 2022-12-05 17:00:00 | 2022-10-30 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
521 | 4989 | 0 | 0 | 0 | 12464852 | 0 | 0 | 0 | 0 | 0 | 511 | 0 | 0 | 511 | 0 | 6040 | 6040 | 6040 | 0 |  |  | 2022-12-12 17:00:00 | 2021-01-07 07:00:00 | 2022-12-12 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12464852 | 0 | 0 | 0 | 0 | 0 | 0 | 12464852 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
521 | 4988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
521 | 4987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
521 | 4986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 6040 | 6040 | 6040 | 0 |  |  | 2022-12-12 17:00:00 | 2021-01-07 07:00:00 | 2022-12-12 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
521 | 4985 | 0 | 0 | 0 | 12464852 | 0 | 0 | 0 | 0 | 0 | 547 | 1 | 0 | 546 | 0 | 6040 | 6040 | 6040 | 0 |  |  | 2022-12-12 17:00:00 | 2021-01-07 07:00:00 | 2022-12-12 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12464852 | 0 | 0 | 0 | 0 | 0 | 0 | 12464852 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
522 | 5271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 0 | 0 | 34 | 0 | 320 | 340 | 320 | 60 |  |  | 2022-12-07 17:00:00 | 2022-10-30 07:00:00 | 2022-12-05 17:00:00 | 2022-10-30 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
522 | 5142 | 0 | 0 | 0 | 12464852 | 0 | 0 | 0 | 0 | 0 | 511 | 0 | 0 | 511 | 0 | 6040 | 6040 | 6040 | 0 |  |  | 2022-12-12 17:00:00 | 2021-01-07 07:00:00 | 2022-12-12 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12464852 | 0 | 0 | 0 | 0 | 0 | 0 | 12464852 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
522 | 5141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
522 | 5140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
522 | 5139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 6040 | 6040 | 6040 | 0 |  |  | 2022-12-12 17:00:00 | 2021-01-07 07:00:00 | 2022-12-12 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
522 | 5138 | 0 | 0 | 0 | 12464852 | 0 | 0 | 0 | 0 | 0 | 547 | 1 | 0 | 546 | 0 | 6040 | 6040 | 6040 | 0 |  |  | 2022-12-12 17:00:00 | 2021-01-07 07:00:00 | 2022-12-12 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12464852 | 0 | 0 | 0 | 0 | 0 | 0 | 12464852 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
523 | 5424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 30 | 0 | 480 | 480 | 480 | 0 |  |  | 2022-11-14 17:00:00 | 2022-09-20 07:00:00 | 2022-11-14 17:00:00 | 2022-09-20 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
523 | 5295 | 0 | 0 | 0 | 12464852 | 0 | 0 | 0 | 0 | 0 | 511 | 0 | 0 | 511 | 0 | 5700 | 5700 | 5700 | 100 |  |  | 2022-11-02 17:00:00 | 2021-01-07 07:00:00 | 2022-11-02 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12464852 | 0 | 0 | 0 | 0 | 0 | 0 | 12464852 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
523 | 5294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 9 | 0 | 4020 | 4020 | 4020 | 780 |  |  | 2022-08-01 17:00:00 | 2021-04-20 07:00:00 | 2022-08-01 17:00:00 | 2021-04-20 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
523 | 5293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 1140 | 1140 | 1140 | 4280 |  |  | 2021-05-19 17:00:00 | 2021-01-07 07:00:00 | 2021-05-19 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
523 | 5292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 5800 | 5800 | 5800 | 0 |  |  | 2022-11-14 17:00:00 | 2021-01-07 07:00:00 | 2022-11-14 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
523 | 5291 | 0 | 0 | 0 | 12464852 | 0 | 0 | 0 | 0 | 0 | 556 | 1 | 0 | 555 | 0 | 5800 | 5800 | 5800 | 0 |  |  | 2022-11-14 17:00:00 | 2021-01-07 07:00:00 | 2022-11-14 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12464852 | 0 | 0 | 0 | 0 | 0 | 0 | 12464852 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
526 | 5604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
577 | 6193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 30 | 0 | 480 | 480 | 480 | 0 |  |  | 2022-11-14 17:00:00 | 2022-09-20 07:00:00 | 2022-11-14 17:00:00 | 2022-09-20 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
577 | 6064 | 0 | 0 | 233890 | 12464852 | 233890 | 0 | 0 | 0 | 0 | 511 | 0 | 0 | 511 | 0 | 5700 | 5700 | 5700 | 100 |  |  | 2022-11-02 17:00:00 | 2021-01-07 07:00:00 | 2022-11-02 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12464852 | 0 | 0 | 1680 | 233890 | 233890 | 0 | 12464852 | 0 | 0 | 1680 |  | NotPrmUser |  | NotPrmUser
577 | 6059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 9 | 0 | 4020 | 4020 | 4020 | 780 |  |  | 2022-08-01 17:00:00 | 2021-04-20 07:00:00 | 2022-08-01 17:00:00 | 2021-04-20 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
577 | 6057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 1140 | 1140 | 1140 | 4280 |  |  | 2021-05-19 17:00:00 | 2021-01-07 07:00:00 | 2021-05-19 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
577 | 6056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 5800 | 5800 | 5800 | 0 |  |  | 2022-11-14 17:00:00 | 2021-01-07 07:00:00 | 2022-11-14 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
577 | 6055 | 0 | 0 | 233890 | 12464852 | 233890 | 0 | 0 | 0 | 0 | 556 | 1 | 0 | 555 | 0 | 5800 | 5800 | 5800 | 0 |  |  | 2022-11-14 17:00:00 | 2021-01-07 07:00:00 | 2022-11-14 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12464852 | 0 | 0 | 1680 | 233890 | 233890 | 0 | 12464852 | 0 | 0 | 1680 |  | NotPrmUser |  | NotPrmUser
580 | 6664 | 0 | 0 | 3600 | 0 | 3600 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 30 | 0 | 480 | 480 | 480 | 0 |  |  | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 3600 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
580 | 6535 | 0 | 0 | 159830 | 12464852 | 159830 | 0 | 0 | 0 | 0 | 511 | 0 | 0 | 511 | 0 | 5240 | 5240 | 5240 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12464852 | 0 | 0 | 1680 | 159830 | 159830 | 0 | 12464852 | 0 | 0 | 1680 |  | NotPrmUser |  | NotPrmUser
580 | 6530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 56 | 0 | 1200 | 1200 | 1200 | 3740 |  |  | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
580 | 6528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 820 | 820 | 820 | 3560 |  |  | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
580 | 6527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 5240 | 5240 | 5240 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
580 | 6526 | 0 | 0 | 163430 | 12464852 | 163430 | 0 | 0 | 0 | 0 | 607 | 1 | 0 | 606 | 0 | 5240 | 5240 | 5240 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12464852 | 0 | 0 | 1680 | 163430 | 163430 | 0 | 12464852 | 0 | 0 | 1680 |  | NotPrmUser |  | NotPrmUser
581 | 6729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 14 | 0 | 1024 | 1024 | 1024 | 0 |  |  | 2021-11-30 17:00:00 | 2021-07-05 08:00:00 | 2021-11-30 17:00:00 | 2021-07-05 08:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
581 | 6728 | 0 | 0 | 46720 | 16010720.97 | 46720 | 0 | 0 | 0 | 0 | 417 | 0 | 0 | 417 | 0 | 1520 | 1520 | 1520 | 512 |  |  | 2021-09-16 16:00:00 | 2021-02-08 08:00:00 | 2021-09-16 16:00:00 | 2021-02-08 08:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16010720.97 | 0 | 944 | 46720 | 46720 | 0 | 0 | 16010720.97 | 0 | 944 |  | NotPrmUser |  | NotPrmUser
581 | 6727 | 0 | 0 | 20592 | 0 | 20592 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 5 | 0 | 2288 | 2288 | 2288 | 0 |  |  | 2021-11-30 17:00:00 | 2021-01-02 08:00:00 | 2021-11-30 17:00:00 | 2021-01-02 08:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20592 | 20592 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
581 | 6726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 0 | 52 | 0 | 1312 | 1312 | 1312 | 872 |  |  | 2021-07-15 16:00:00 | 2021-01-06 08:00:00 | 2021-07-15 16:00:00 | 2021-01-06 08:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
581 | 6725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 36 | 0 | 1056 | 1056 | 1056 | 312 |  |  | 2021-06-03 16:00:00 | 2021-01-02 08:00:00 | 2021-06-03 16:00:00 | 2021-01-02 08:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
581 | 6724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 2288 | 2288 | 2288 | 0 |  |  | 2021-11-30 17:00:00 | 2021-01-02 08:00:00 | 2021-11-30 17:00:00 | 2021-01-02 08:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
581 | 6723 | 0 | 0 | 67312 | 16010720.97 | 67312 | 0 | 0 | 0 | 0 | 532 | 0 | 0 | 532 | 0 | 2288 | 2288 | 2288 | 0 |  |  | 2021-11-30 17:00:00 | 2021-01-02 08:00:00 | 2021-11-30 17:00:00 | 2021-01-02 08:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16010720.97 | 0 | 944 | 67312 | 67312 | 0 | 0 | 16010720.97 | 0 | 944 |  | NotPrmUser |  | NotPrmUser
631 | 7181 | 0 | 0 | 3600 | 0 | 3600 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 30 | 0 | 480 | 480 | 480 | 0 |  |  | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 3600 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
631 | 7052 | 0 | 0 | 159830 | 9726772.6 | 159830 | 0 | 0 | 0 | 0 | 511 | 0 | 0 | 511 | 0 | 5240 | 5240 | 5240 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9726772.6 | 0 | 0 | 1680 | 159830 | 159830 | 0 | 9726772.6 | 0 | 0 | 1680 |  | NotPrmUser |  | NotPrmUser
631 | 7030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 56 | 0 | 1200 | 1200 | 1200 | 3740 |  |  | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
631 | 7025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 820 | 820 | 820 | 3560 |  |  | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
631 | 7024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 5240 | 5240 | 5240 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
631 | 7023 | 0 | 0 | 163430 | 9726772.6 | 163430 | 0 | 0 | 0 | 0 | 607 | 1 | 0 | 606 | 0 | 5240 | 5240 | 5240 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9726772.6 | 0 | 0 | 1680 | 163430 | 163430 | 0 | 9726772.6 | 0 | 0 | 1680 |  | NotPrmUser |  | NotPrmUser
633 | 7359 | 0 | 0 | 3600 | 0 | 3600 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 30 | 0 | 480 | 480 | 480 | 0 |  |  | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 3600 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
633 | 7230 | 0 | 0 | 159830 | 11361935 | 159830 | 0 | 0 | 0 | 0 | 511 | 0 | 0 | 511 | 0 | 5240 | 5240 | 5240 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11361935 | 0 | 0 | 1680 | 159830 | 159830 | 0 | 11361935 | 0 | 0 | 1680 |  | NotPrmUser |  | NotPrmUser
633 | 7208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 56 | 0 | 1200 | 1200 | 1200 | 3740 |  |  | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
633 | 7203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 820 | 820 | 820 | 3560 |  |  | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
633 | 7202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 5240 | 5240 | 5240 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
633 | 7201 | 0 | 0 | 163430 | 11361935 | 163430 | 0 | 0 | 0 | 0 | 607 | 1 | 0 | 606 | 0 | 5240 | 5240 | 5240 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11361935 | 0 | 0 | 1680 | 163430 | 163430 | 0 | 11361935 | 0 | 0 | 1680 |  | NotPrmUser |  | NotPrmUser
634 | 7536 | 0 | 0 | 1680 | 0 | 1680 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 14 | 0 | 520 | 520 | 520 | 0 |  |  | 2022-01-05 17:00:00 | 2021-11-07 07:00:00 | 2022-01-05 17:00:00 | 2021-11-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1680 | 1680 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
634 | 7407 | 0 | 0 | 85270 | 5250032 | 85270 | 0 | 0 | 0 | 0 | 283 | 0 | 0 | 283 | 0 | 3100 | 3100 | 3100 | 20 |  |  | 2022-01-03 17:00:00 | 2021-01-07 07:00:00 | 2022-01-03 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5250032 | 0 | 0 | 1600 | 85270 | 85270 | 0 | 5250032 | 0 | 0 | 1600 |  | NotPrmUser |  | NotPrmUser
634 | 7385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 56 | 0 | 1200 | 1200 | 1200 | 1620 |  |  | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
634 | 7380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 820 | 820 | 820 | 1430 |  |  | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
634 | 7379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 3120 | 3120 | 3120 | 0 |  |  | 2022-01-05 17:00:00 | 2021-01-07 07:00:00 | 2022-01-05 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
634 | 7378 | 0 | 0 | 86950 | 5250032 | 86950 | 0 | 0 | 0 | 0 | 363 | 1 | 0 | 362 | 0 | 3120 | 3120 | 3120 | 0 |  |  | 2022-01-05 17:00:00 | 2021-01-07 07:00:00 | 2022-01-05 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5250032 | 0 | 0 | 1600 | 86950 | 86950 | 0 | 5250032 | 0 | 0 | 1600 |  | NotPrmUser |  | NotPrmUser
637 | 7715 | 0 | 0 | 3600 | 0 | 3600 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 30 | 0 | 480 | 480 | 480 | 0 |  |  | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 3600 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
637 | 7586 | 0 | 0 | 159830 | 12464852 | 159830 | 0 | 0 | 0 | 0 | 511 | 0 | 0 | 511 | 0 | 5240 | 5240 | 5240 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12464852 | 0 | 0 | 1680 | 159830 | 159830 | 0 | 12464852 | 0 | 0 | 1680 |  | NotPrmUser |  | NotPrmUser
637 | 7564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 56 | 0 | 1200 | 1200 | 1200 | 3740 |  |  | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
637 | 7559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 820 | 820 | 820 | 3560 |  |  | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
637 | 7558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 5240 | 5240 | 5240 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
637 | 7557 | 0 | 0 | 163430 | 12464852 | 163430 | 0 | 0 | 0 | 0 | 607 | 1 | 0 | 606 | 0 | 5240 | 5240 | 5240 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12464852 | 0 | 0 | 1680 | 163430 | 163430 | 0 | 12464852 | 0 | 0 | 1680 |  | NotPrmUser |  | NotPrmUser
638 | 7892 | 0 | 0 | 3600 | 0 | 3600 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 30 | 0 | 480 | 480 | 480 | 0 |  |  | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 3600 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
638 | 7763 | 0 | 0 | 159830 | 12464852 | 159830 | 0 | 0 | 0 | 0 | 511 | 0 | 0 | 511 | 0 | 5240 | 5240 | 5240 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12464852 | 0 | 0 | 1680 | 159830 | 159830 | 0 | 12464852 | 0 | 0 | 1680 |  | NotPrmUser |  | NotPrmUser
638 | 7741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 56 | 0 | 1200 | 1200 | 1200 | 3740 |  |  | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
638 | 7736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 820 | 820 | 820 | 3560 |  |  | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
638 | 7735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 5240 | 5240 | 5240 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
638 | 7734 | 0 | 0 | 163430 | 12464852 | 163430 | 0 | 0 | 0 | 0 | 607 | 1 | 0 | 606 | 0 | 5240 | 5240 | 5240 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12464852 | 0 | 0 | 1680 | 163430 | 163430 | 0 | 12464852 | 0 | 0 | 1680 |  | NotPrmUser |  | NotPrmUser
639 | 8069 | 0 | 0 | 3600 | 0 | 3600 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 30 | 0 | 480 | 480 | 480 | 0 |  |  | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 3600 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
639 | 7940 | 0 | 0 | 159830 | 12464852 | 159830 | 0 | 0 | 0 | 0 | 511 | 0 | 0 | 511 | 0 | 5240 | 5240 | 5240 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12464852 | 0 | 0 | 1680 | 159830 | 159830 | 0 | 12464852 | 0 | 0 | 1680 |  | NotPrmUser |  | NotPrmUser
639 | 7918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 56 | 0 | 1200 | 1200 | 1200 | 3740 |  |  | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
639 | 7913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 820 | 820 | 820 | 3560 |  |  | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
639 | 7912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 5240 | 5240 | 5240 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
639 | 7911 | 0 | 0 | 163430 | 12464852 | 163430 | 0 | 0 | 0 | 0 | 607 | 1 | 0 | 606 | 0 | 5240 | 5240 | 5240 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12464852 | 0 | 0 | 1680 | 163430 | 163430 | 0 | 12464852 | 0 | 0 | 1680 |  | NotPrmUser |  | NotPrmUser
640 | 8246 | 0 | 0 | 3600 | 0 | 3600 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 30 | 0 | 480 | 480 | 480 | 0 |  |  | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 3600 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
640 | 8117 | 0 | 0 | 159830 | 12464852 | 159830 | 0 | 0 | 0 | 0 | 511 | 0 | 0 | 511 | 0 | 5240 | 5240 | 5240 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12464852 | 0 | 0 | 1680 | 159830 | 159830 | 0 | 12464852 | 0 | 0 | 1680 |  | NotPrmUser |  | NotPrmUser
640 | 8095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 56 | 0 | 1200 | 1200 | 1200 | 3740 |  |  | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
640 | 8090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 820 | 820 | 820 | 3560 |  |  | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
640 | 8089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 5240 | 5240 | 5240 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
640 | 8088 | 0 | 0 | 163430 | 12464852 | 163430 | 0 | 0 | 0 | 0 | 607 | 1 | 0 | 606 | 0 | 5240 | 5240 | 5240 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12464852 | 0 | 0 | 1680 | 163430 | 163430 | 0 | 12464852 | 0 | 0 | 1680 |  | NotPrmUser |  | NotPrmUser
641 | 8423 | 0 | 0 | 3600 | 0 | 3600 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 30 | 0 | 480 | 480 | 480 | 0 |  |  | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 3600 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
641 | 8294 | 0 | 0 | 159830 | 9726772.6 | 159830 | 0 | 0 | 0 | 0 | 511 | 0 | 0 | 511 | 0 | 5240 | 5240 | 5240 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9726772.6 | 0 | 0 | 1680 | 159830 | 159830 | 0 | 9726772.6 | 0 | 0 | 1680 |  | NotPrmUser |  | NotPrmUser
641 | 8272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 56 | 0 | 1200 | 1200 | 1200 | 3740 |  |  | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
641 | 8267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 820 | 820 | 820 | 3560 |  |  | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
641 | 8266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 5240 | 5240 | 5240 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
641 | 8265 | 0 | 0 | 163430 | 9726772.6 | 163430 | 0 | 0 | 0 | 0 | 607 | 1 | 0 | 606 | 0 | 5240 | 5240 | 5240 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9726772.6 | 0 | 0 | 1680 | 163430 | 163430 | 0 | 9726772.6 | 0 | 0 | 1680 |  | NotPrmUser |  | NotPrmUser
642 | 8600 | 0 | 0 | 3600 | 0 | 3600 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 30 | 0 | 480 | 480 | 480 | 0 |  |  | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 3600 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
642 | 8471 | 0 | 0 | 159830 | 9726772.6 | 159830 | 0 | 0 | 0 | 0 | 511 | 0 | 0 | 511 | 0 | 5240 | 5240 | 5240 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9726772.6 | 0 | 0 | 1680 | 159830 | 159830 | 0 | 9726772.6 | 0 | 0 | 1680 |  | NotPrmUser |  | NotPrmUser
642 | 8449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 56 | 0 | 1200 | 1200 | 1200 | 3740 |  |  | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
642 | 8444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 820 | 820 | 820 | 3560 |  |  | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
642 | 8443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 5240 | 5240 | 5240 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
642 | 8442 | 0 | 0 | 163430 | 9726772.6 | 163430 | 0 | 0 | 0 | 0 | 607 | 1 | 0 | 606 | 0 | 5240 | 5240 | 5240 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9726772.6 | 0 | 0 | 1680 | 163430 | 163430 | 0 | 9726772.6 | 0 | 0 | 1680 |  | NotPrmUser |  | NotPrmUser
643 | 8777 | 0 | 0 | 3600 | 0 | 3600 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 30 | 0 | 480 | 480 | 480 | 0 |  |  | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 3600 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
643 | 8648 | 0 | 0 | 159830 | 9726772.6 | 159830 | 0 | 0 | 0 | 0 | 511 | 0 | 0 | 511 | 0 | 5240 | 5240 | 5240 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9726772.6 | 0 | 0 | 1680 | 159830 | 159830 | 0 | 9726772.6 | 0 | 0 | 1680 |  | NotPrmUser |  | NotPrmUser
643 | 8626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 56 | 0 | 1200 | 1200 | 1200 | 3740 |  |  | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
643 | 8621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 820 | 820 | 820 | 3560 |  |  | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
643 | 8620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 5240 | 5240 | 5240 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
643 | 8619 | 0 | 0 | 163430 | 9726772.6 | 163430 | 0 | 0 | 0 | 0 | 607 | 1 | 0 | 606 | 0 | 5240 | 5240 | 5240 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9726772.6 | 0 | 0 | 1680 | 163430 | 163430 | 0 | 9726772.6 | 0 | 0 | 1680 |  | NotPrmUser |  | NotPrmUser
644 | 8954 | 0 | 0 | 3600 | 0 | 3600 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 30 | 0 | 480 | 480 | 480 | 0 |  |  | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 3600 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
644 | 8825 | 0 | 0 | 159830 | 9726772.6 | 159830 | 0 | 0 | 0 | 0 | 511 | 0 | 0 | 511 | 0 | 5240 | 5240 | 5240 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9726772.6 | 0 | 0 | 1680 | 159830 | 159830 | 0 | 9726772.6 | 0 | 0 | 1680 |  | NotPrmUser |  | NotPrmUser
644 | 8803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 56 | 0 | 1200 | 1200 | 1200 | 3740 |  |  | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
644 | 8798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 820 | 820 | 820 | 3560 |  |  | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
644 | 8797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 5240 | 5240 | 5240 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
644 | 8796 | 0 | 0 | 163430 | 9726772.6 | 163430 | 0 | 0 | 0 | 0 | 607 | 1 | 0 | 606 | 0 | 5240 | 5240 | 5240 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9726772.6 | 0 | 0 | 1680 | 163430 | 163430 | 0 | 9726772.6 | 0 | 0 | 1680 |  | NotPrmUser |  | NotPrmUser
645 | 9131 | 0 | 0 | 3600 | 0 | 3600 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 30 | 0 | 480 | 480 | 480 | 0 |  |  | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 3600 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
645 | 9002 | 0 | 0 | 159830 | 11361935 | 159830 | 0 | 0 | 0 | 0 | 511 | 0 | 0 | 511 | 0 | 5240 | 5240 | 5240 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11361935 | 0 | 0 | 1680 | 159830 | 159830 | 0 | 11361935 | 0 | 0 | 1680 |  | NotPrmUser |  | NotPrmUser
645 | 8980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 56 | 0 | 1200 | 1200 | 1200 | 3740 |  |  | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
645 | 8975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 820 | 820 | 820 | 3560 |  |  | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
645 | 8974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 5240 | 5240 | 5240 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
645 | 8973 | 0 | 0 | 163430 | 11361935 | 163430 | 0 | 0 | 0 | 0 | 607 | 1 | 0 | 606 | 0 | 5240 | 5240 | 5240 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11361935 | 0 | 0 | 1680 | 163430 | 163430 | 0 | 11361935 | 0 | 0 | 1680 |  | NotPrmUser |  | NotPrmUser
646 | 9308 | 0 | 0 | 3600 | 0 | 3600 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 30 | 0 | 480 | 480 | 480 | 0 |  |  | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 3600 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
646 | 9179 | 0 | 0 | 159830 | 11361935 | 159830 | 0 | 0 | 0 | 0 | 511 | 0 | 0 | 511 | 0 | 5240 | 5240 | 5240 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11361935 | 0 | 0 | 1680 | 159830 | 159830 | 0 | 11361935 | 0 | 0 | 1680 |  | NotPrmUser |  | NotPrmUser
646 | 9157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 56 | 0 | 1200 | 1200 | 1200 | 3740 |  |  | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
646 | 9152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 820 | 820 | 820 | 3560 |  |  | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
646 | 9151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 5240 | 5240 | 5240 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
646 | 9150 | 0 | 0 | 163430 | 11361935 | 163430 | 0 | 0 | 0 | 0 | 607 | 1 | 0 | 606 | 0 | 5240 | 5240 | 5240 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11361935 | 0 | 0 | 1680 | 163430 | 163430 | 0 | 11361935 | 0 | 0 | 1680 |  | NotPrmUser |  | NotPrmUser
647 | 9437 | 0 | 0 | 1680 | 0 | 1680 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 14 | 0 | 520 | 520 | 520 | 0 |  |  | 2022-01-05 17:00:00 | 2021-11-07 07:00:00 | 2022-01-05 17:00:00 | 2021-11-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1680 | 1680 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
647 | 9356 | 0 | 0 | 85270 | 5250032 | 85270 | 0 | 0 | 0 | 0 | 283 | 0 | 0 | 283 | 0 | 3100 | 3100 | 3100 | 20 |  |  | 2022-01-03 17:00:00 | 2021-01-07 07:00:00 | 2022-01-03 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5250032 | 0 | 0 | 1600 | 85270 | 85270 | 0 | 5250032 | 0 | 0 | 1600 |  | NotPrmUser |  | NotPrmUser
647 | 9334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 56 | 0 | 1200 | 1200 | 1200 | 1620 |  |  | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
647 | 9329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 820 | 820 | 820 | 1430 |  |  | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
647 | 9328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 3120 | 3120 | 3120 | 0 |  |  | 2022-01-05 17:00:00 | 2021-01-07 07:00:00 | 2022-01-05 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
647 | 9327 | 0 | 0 | 86950 | 5250032 | 86950 | 0 | 0 | 0 | 0 | 363 | 1 | 0 | 362 | 0 | 3120 | 3120 | 3120 | 0 |  |  | 2022-01-05 17:00:00 | 2021-01-07 07:00:00 | 2022-01-05 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5250032 | 0 | 0 | 1600 | 86950 | 86950 | 0 | 5250032 | 0 | 0 | 1600 |  | NotPrmUser |  | NotPrmUser
648 | 9558 | 0 | 0 | 1680 | 0 | 1680 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 14 | 0 | 520 | 520 | 520 | 0 |  |  | 2022-01-05 17:00:00 | 2021-11-07 07:00:00 | 2022-01-05 17:00:00 | 2021-11-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1680 | 1680 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
648 | 9477 | 0 | 0 | 85270 | 5250032 | 85270 | 0 | 0 | 0 | 0 | 283 | 0 | 0 | 283 | 0 | 3100 | 3100 | 3100 | 20 |  |  | 2022-01-03 17:00:00 | 2021-01-07 07:00:00 | 2022-01-03 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5250032 | 0 | 0 | 1600 | 85270 | 85270 | 0 | 5250032 | 0 | 0 | 1600 |  | NotPrmUser |  | NotPrmUser
648 | 9455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 56 | 0 | 1200 | 1200 | 1200 | 1620 |  |  | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
648 | 9450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 820 | 820 | 820 | 1430 |  |  | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
648 | 9449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 3120 | 3120 | 3120 | 0 |  |  | 2022-01-05 17:00:00 | 2021-01-07 07:00:00 | 2022-01-05 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
648 | 9448 | 0 | 0 | 86950 | 5250032 | 86950 | 0 | 0 | 0 | 0 | 363 | 1 | 0 | 362 | 0 | 3120 | 3120 | 3120 | 0 |  |  | 2022-01-05 17:00:00 | 2021-01-07 07:00:00 | 2022-01-05 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5250032 | 0 | 0 | 1600 | 86950 | 86950 | 0 | 5250032 | 0 | 0 | 1600 |  | NotPrmUser |  | NotPrmUser
649 | 9571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 | 0 | 4 | 0 | 1010 | 1010 | 1010 | 1040 |  |  | 2023-08-30 17:00:00 | 2023-05-01 07:00:00 | 2023-08-30 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
649 | 9570 | 0 | 0 | 23870 | 0 | 23870 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 12 | 0 | 2050 | 2050 | 2050 | 0 |  |  | 2023-12-31 17:00:00 | 2023-05-01 07:00:00 | 2023-12-31 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8990 | 23870 | 23870 | 0 | 0 | 0 | 0 | 8990 |  | NotPrmUser |  | NotPrmUser
649 | 9575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 2 | 0 | 2050 | 2050 | 2050 | 0 |  |  | 2023-12-31 17:00:00 | 2023-05-01 07:00:00 | 2023-12-31 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
649 | 9569 | 0 | 0 | 23870 | 0 | 23870 | 0 | 0 | 0 | 0 | 21 | 3 | 0 | 18 | 0 | 2050 | 2050 | 2050 | 0 |  |  | 2023-12-31 17:00:00 | 2023-05-01 07:00:00 | 2023-12-31 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8990 | 23870 | 23870 | 0 | 0 | 0 | 0 | 8990 |  | NotPrmUser |  | NotPrmUser
651 | 9592 | 0 | 0 | 677590 | 49859407.9996 | 677590 | 0 | 0 | 0 | 0 | 2449 | 0 | 0 | 2449 | 0 | 5240 | 5240 | 5240 | 0 |  |  | 2024-12-08 17:00:00 | 2023-03-16 07:00:00 | 2024-12-08 17:00:00 | 2023-03-16 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49859407.9996 | 0 | 0 | 15710 | 677590 | 677590 | 0 | 49859407.9996 | 0 | 0 | 15710 |  | NotPrmUser |  | NotPrmUser
651 | 9593 | 0 | 0 | 1178350 | 72131024.3966 | 1178350 | 0 | 0 | 0 | 0 | 4389 | 2 | 0 | 4387 | 0 | 10990 | 10990 | 10990 | 1080 |  |  | 2024-08-03 17:00:00 | 2021-01-07 07:00:00 | 2024-08-03 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72131024.3966 | 0 | 0 | 22270 | 1178350 | 1178350 | 0 | 72131024.3966 | 0 | 0 | 22270 |  | NotPrmUser |  | NotPrmUser
651 | 9577 | 0 | 0 | 1855940 | 121990432.3962 | 1855940 | 0 | 0 | 0 | 0 | 6838 | 2 | 0 | 6836 | 0 | 12070 | 12070 | 12070 | 0 |  |  | 2024-12-08 17:00:00 | 2021-01-07 07:00:00 | 2024-12-08 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121990432.3962 | 0 | 0 | 37980 | 1855940 | 1855940 | 0 | 121990432.3962 | 0 | 0 | 37980 |  | NotPrmUser |  | NotPrmUser
652 | 9584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 | 0 | 4 | 0 | 1010 | 1010 | 1010 | 1040 |  |  | 2023-08-30 17:00:00 | 2023-05-01 07:00:00 | 2023-08-30 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
652 | 9580 | 0 | 0 | 23870 | 0 | 23870 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 12 | 0 | 2050 | 2050 | 2050 | 0 |  |  | 2023-12-31 17:00:00 | 2023-05-01 07:00:00 | 2023-12-31 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8990 | 23870 | 23870 | 0 | 0 | 0 | 0 | 8990 |  | NotPrmUser |  | NotPrmUser
652 | 9579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 2 | 0 | 2050 | 2050 | 2050 | 0 |  |  | 2023-12-31 17:00:00 | 2023-05-01 07:00:00 | 2023-12-31 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
652 | 9578 | 0 | 0 | 23870 | 0 | 23870 | 0 | 0 | 0 | 0 | 21 | 3 | 0 | 18 | 0 | 2050 | 2050 | 2050 | 0 |  |  | 2023-12-31 17:00:00 | 2023-05-01 07:00:00 | 2023-12-31 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8990 | 23870 | 23870 | 0 | 0 | 0 | 0 | 8990 |  | NotPrmUser |  | NotPrmUser
653 | 9591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1 | 0 | 4 | 0 | 1010 | 1010 | 1010 | 1040 |  |  | 2023-08-30 17:00:00 | 2023-05-01 07:00:00 | 2023-08-30 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
653 | 9587 | 0 | 0 | 23870 | 0 | 23870 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 12 | 0 | 2050 | 2050 | 2050 | 0 |  |  | 2023-12-31 17:00:00 | 2023-05-01 07:00:00 | 2023-12-31 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8990 | 23870 | 23870 | 0 | 0 | 0 | 0 | 8990 |  | NotPrmUser |  | NotPrmUser
653 | 9586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 2 | 0 | 2050 | 2050 | 2050 | 0 |  |  | 2023-12-31 17:00:00 | 2023-05-01 07:00:00 | 2023-12-31 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
653 | 9585 | 0 | 0 | 23870 | 0 | 23870 | 0 | 0 | 0 | 0 | 21 | 3 | 0 | 18 | 0 | 2050 | 2050 | 2050 | 0 |  |  | 2023-12-31 17:00:00 | 2023-05-01 07:00:00 | 2023-12-31 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8990 | 23870 | 23870 | 0 | 0 | 0 | 0 | 8990 |  | NotPrmUser |  | NotPrmUser
1356 | 17377 | 0 | 0 | 677590 | 49859407.9996 | 677590 | 0 | 0 | 0 | 0 | 2449 | 0 | 0 | 2449 | 0 | 5240 | 5240 | 5240 | 0 |  |  | 2024-12-08 17:00:00 | 2023-03-16 07:00:00 | 2024-12-08 17:00:00 | 2023-03-16 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49859407.9996 | 0 | 0 | 15710 | 677590 | 677590 | 0 | 49859407.9996 | 0 | 0 | 15710 |  | NotPrmUser |  | NotPrmUser
1356 | 16062 | 9500063.9974 | 0 | 1012050 | 72131024.3966 | 1012050 | 166300 | 0 | 724 | 0 | 3665 | 2 | 0 | 4387 | 3120 | 10990 | 10990 | 8310 | 1080 |  | 2021-01-07 07:00:00 | 2024-08-03 17:00:00 | 2021-01-07 07:00:00 | 2024-08-03 17:00:00 | 2021-11-16 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72131024.3966 | 0 | 0 | 22270 | 1178350 | 1012050 | 0 | 72131024.3966 | 0 | 0 | 19070 |  | NotPrmUser |  | NotPrmUser
1356 | 16061 | 9500063.9974 | 0 | 1689640 | 121990432.3962 | 1689640 | 166300 | 0 | 724 | 0 | 6114 | 2 | 0 | 6836 | 3120 | 12070 | 12070 | 9390 | 0 |  | 2021-01-07 07:00:00 | 2024-12-08 17:00:00 | 2021-01-07 07:00:00 | 2024-12-08 17:00:00 | 2021-11-16 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121990432.3962 | 0 | 0 | 37980 | 1855940 | 1689640 | 0 | 121990432.3962 | 0 | 0 | 34780 |  | NotPrmUser |  | NotPrmUser
1357 | 19409 | 0 | 0 | 677590 | 49859407.9996 | 677590 | 0 | 0 | 0 | 0 | 2449 | 0 | 0 | 2449 | 0 | 5240 | 5240 | 5240 | 0 |  |  | 2024-12-08 17:00:00 | 2023-03-16 07:00:00 | 2024-12-08 17:00:00 | 2023-03-16 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49859407.9996 | 0 | 0 | 15710 | 677590 | 677590 | 0 | 49859407.9996 | 0 | 0 | 15710 |  | NotPrmUser |  | NotPrmUser
1357 | 18094 | 23588863.9978 | 0 | 809970 | 72131024.3966 | 809970 | 368380 | 0 | 1291 | 0 | 3098 | 2 | 0 | 4387 | 7670 | 10990 | 10990 | 8310 | 1080 |  | 2021-01-07 07:00:00 | 2024-08-03 17:00:00 | 2021-01-07 07:00:00 | 2024-08-03 17:00:00 | 2021-11-16 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72131024.3966 | 0 | 0 | 22270 | 1178350 | 809970 | 0 | 72131024.3966 | 0 | 0 | 12350 |  | NotPrmUser |  | NotPrmUser
1357 | 18093 | 23588863.9978 | 0 | 1487560 | 121990432.3962 | 1487560 | 368380 | 0 | 1291 | 0 | 5547 | 2 | 0 | 6836 | 7670 | 12070 | 12070 | 9390 | 0 |  | 2021-01-07 07:00:00 | 2024-12-08 17:00:00 | 2021-01-07 07:00:00 | 2024-12-08 17:00:00 | 2021-11-16 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121990432.3962 | 0 | 0 | 37980 | 1855940 | 1487560 | 0 | 121990432.3962 | 0 | 0 | 28060 |  | NotPrmUser |  | NotPrmUser
1358 | 21441 | 0 | 0 | 677590 | 49859407.9996 | 677590 | 0 | 0 | 0 | 0 | 2449 | 0 | 0 | 2449 | 0 | 5240 | 5240 | 5240 | 0 |  |  | 2024-12-08 17:00:00 | 2023-03-16 07:00:00 | 2024-12-08 17:00:00 | 2023-03-16 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49859407.9996 | 0 | 0 | 15710 | 677590 | 677590 | 0 | 49859407.9996 | 0 | 0 | 15710 |  | NotPrmUser |  | NotPrmUser
1358 | 20126 | 25845663.9978 | 0 | 792930 | 72131024.3966 | 792930 | 385420 | 0 | 1343 | 0 | 3046 | 2 | 0 | 4387 | 10320 | 10990 | 10990 | 8310 | 1080 |  | 2021-01-07 07:00:00 | 2024-08-03 17:00:00 | 2021-01-07 07:00:00 | 2024-08-03 17:00:00 | 2021-11-16 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72131024.3966 | 0 | 0 | 22270 | 1178350 | 792930 | 0 | 72131024.3966 | 0 | 0 | 9310 |  | NotPrmUser |  | NotPrmUser
1358 | 20125 | 25845663.9978 | 0 | 1470520 | 121990432.3962 | 1470520 | 385420 | 0 | 1343 | 0 | 5495 | 2 | 0 | 6836 | 10320 | 12070 | 12070 | 9390 | 0 |  | 2021-01-07 07:00:00 | 2024-12-08 17:00:00 | 2021-01-07 07:00:00 | 2024-12-08 17:00:00 | 2021-11-16 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121990432.3962 | 0 | 0 | 37980 | 1855940 | 1470520 | 0 | 121990432.3962 | 0 | 0 | 25020 |  | NotPrmUser |  | NotPrmUser
1359 | 23473 | 1270000 | 0 | 666870 | 49859407.9996 | 666870 | 10720 | 0 | 24 | 0 | 2425 | 0 | 0 | 2449 | 420 | 5240 | 5240 | 5240 | 0 |  | 2023-03-16 07:00:00 | 2024-12-08 17:00:00 | 2023-03-16 07:00:00 | 2024-12-08 17:00:00 | 2023-03-16 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49859407.9996 | 0 | 0 | 15710 | 677590 | 666870 | 0 | 49859407.9996 | 0 | 0 | 11670 |  | NotPrmUser |  | NotPrmUser
1359 | 22158 | 25845663.9978 | 0 | 792930 | 72131024.3966 | 792930 | 385420 | 0 | 1343 | 0 | 3046 | 2 | 0 | 4387 | 10320 | 10990 | 10990 | 8310 | 1080 |  | 2021-01-07 07:00:00 | 2024-08-03 17:00:00 | 2021-01-07 07:00:00 | 2024-08-03 17:00:00 | 2021-11-16 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72131024.3966 | 0 | 0 | 22270 | 1178350 | 792930 | 0 | 72131024.3966 | 0 | 0 | 9310 |  | NotPrmUser |  | NotPrmUser
1359 | 22157 | 27115663.9978 | 0 | 1459800 | 121990432.3962 | 1459800 | 396140 | 0 | 1367 | 0 | 5471 | 2 | 0 | 6836 | 10320 | 12070 | 12070 | 9390 | 0 |  | 2021-01-07 07:00:00 | 2024-12-08 17:00:00 | 2021-01-07 07:00:00 | 2024-12-08 17:00:00 | 2021-11-16 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121990432.3962 | 0 | 0 | 37980 | 1855940 | 1459800 | 0 | 121990432.3962 | 0 | 0 | 20980 |  | NotPrmUser |  | NotPrmUser
1360 | 25505 | 1270000 | 0 | 666870 | 49859407.9996 | 666870 | 10720 | 0 | 24 | 0 | 2425 | 0 | 0 | 2449 | 420 | 5240 | 5240 | 5240 | 0 |  | 2023-03-16 07:00:00 | 2024-12-08 17:00:00 | 2023-03-16 07:00:00 | 2024-12-08 17:00:00 | 2023-03-16 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49859407.9996 | 0 | 0 | 15710 | 677590 | 666870 | 0 | 49859407.9996 | 0 | 0 | 11670 |  | NotPrmUser |  | NotPrmUser
1360 | 24190 | 25296668.9976 | 0 | 808850 | 72131024.3966 | 808850 | 371580 | 0 | 1311 | 1 | 3077 | 2 | 0 | 4387 | 10320 | 10990 | 10990 | 8310 | 1080 |  | 2021-01-07 07:00:00 | 2024-08-03 17:00:00 | 2021-01-07 07:00:00 | 2024-08-03 17:00:00 | 2021-11-16 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72131024.3966 | 0 | 0 | 22270 | 1178350 | 808850 | 0 | 72131024.3966 | 0 | 0 | 9310 |  | NotPrmUser |  | NotPrmUser
1360 | 24189 | 26566668.9976 | 0 | 1475720 | 121990432.3962 | 1475720 | 382300 | 0 | 1335 | 1 | 5502 | 2 | 0 | 6836 | 10320 | 12070 | 12070 | 9390 | 0 |  | 2021-01-07 07:00:00 | 2024-12-08 17:00:00 | 2021-01-07 07:00:00 | 2024-12-08 17:00:00 | 2021-11-16 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121990432.3962 | 0 | 0 | 37980 | 1855940 | 1475720 | 0 | 121990432.3962 | 0 | 0 | 20980 |  | NotPrmUser |  | NotPrmUser
1361 | 27537 | 0 | 0 | 677590 | 49859407.9996 | 677590 | 0 | 0 | 0 | 0 | 2449 | 0 | 0 | 2449 | 0 | 5240 | 5240 | 5240 | 0 |  |  | 2024-11-25 17:00:00 | 2023-03-04 07:00:00 | 2024-11-25 17:00:00 | 2023-03-04 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49859407.9996 | 0 | 0 | 15710 | 677590 | 677590 | 0 | 49859407.9996 | 0 | 0 | 15710 |  | NotPrmUser |  | NotPrmUser
1361 | 26222 | 0 | 0 | 1178350 | 72131024.3966 | 1178350 | 0 | 0 | 0 | 0 | 4389 | 2 | 0 | 4387 | 0 | 10850 | 10850 | 10850 | 1110 |  |  | 2024-07-17 17:00:00 | 2021-01-07 07:00:00 | 2024-07-17 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72131024.3966 | 0 | 0 | 22270 | 1178350 | 1178350 | 0 | 72131024.3966 | 0 | 0 | 22270 |  | NotPrmUser |  | NotPrmUser
1361 | 26221 | 0 | 0 | 1855940 | 121990432.3962 | 1855940 | 0 | 0 | 0 | 0 | 6838 | 2 | 0 | 6836 | 0 | 11960 | 11960 | 11960 | 0 |  |  | 2024-11-25 17:00:00 | 2021-01-07 07:00:00 | 2024-11-25 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121990432.3962 | 0 | 0 | 37980 | 1855940 | 1855940 | 0 | 121990432.3962 | 0 | 0 | 37980 |  | NotPrmUser |  | NotPrmUser
1362 | 29569 | 0 | 0 | 662390 | 50048597.96 | 662390 | 0 | 0 | 0 | 0 | 2447 | 0 | 0 | 2447 | 0 | 5240 | 5240 | 5240 | 0 |  |  | 2024-11-25 17:00:00 | 2023-03-04 07:00:00 | 2024-11-25 17:00:00 | 2023-03-04 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50048597.96 | 0 | 0 | 15710 | 662390 | 662390 | 0 | 50048597.96 | 0 | 0 | 15710 |  | NotPrmUser |  | NotPrmUser
1362 | 28254 | 0 | 0 | 1147950 | 71941834.46 | 1147950 | 0 | 0 | 0 | 0 | 4383 | 2 | 0 | 4381 | 0 | 10850 | 10850 | 10850 | 1110 |  |  | 2024-07-17 17:00:00 | 2021-01-07 07:00:00 | 2024-07-17 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71941834.46 | 0 | 0 | 22270 | 1147950 | 1147950 | 0 | 71941834.46 | 0 | 0 | 22270 |  | NotPrmUser |  | NotPrmUser
1362 | 28253 | 0 | 0 | 1810340 | 121990432.42 | 1810340 | 0 | 0 | 0 | 0 | 6830 | 2 | 0 | 6828 | 0 | 11960 | 11960 | 11960 | 0 |  |  | 2024-11-25 17:00:00 | 2021-01-07 07:00:00 | 2024-11-25 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121990432.42 | 0 | 0 | 37980 | 1810340 | 1810340 | 0 | 121990432.42 | 0 | 0 | 37980 |  | NotPrmUser |  | NotPrmUser
1363 | 31593 | 1785625 | 0 | 649910 | 50048597.96 | 649910 | 12480 | 0 | 26 | 0 | 2421 | 0 | 0 | 2447 | 540 | 5240 | 5240 | 5240 | 0 |  | 2023-03-04 07:00:00 | 2024-11-25 17:00:00 | 2023-03-04 07:00:00 | 2024-11-25 17:00:00 | 2023-03-04 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50048597.96 | 0 | 0 | 15710 | 662390 | 649910 | 0 | 50048597.96 | 0 | 0 | 11670 |  | NotPrmUser |  | NotPrmUser
1363 | 30286 | 41896665.6665 | 0 | 578590 | 71941834.46 | 578590 | 679967.8586 | 0 | 1883 | 318 | 2182 | 2 | 0 | 4381 | 9830 | 10850 | 10850 | 8190 | 1110 |  | 2021-01-07 07:00:00 | 2024-07-17 17:00:00 | 2021-01-07 07:00:00 | 2024-07-17 17:00:00 | 2021-11-14 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71941834.46 | 0 | 0 | 22270 | 1147950 | 578590 | 0 | 71941834.46 | 0 | 0 | 9100 |  | NotPrmUser |  | NotPrmUser
1363 | 30285 | 43682290.6665 | 0 | 1228500 | 121990432.42 | 1228500 | 692447.8586 | 0 | 1909 | 318 | 4603 | 2 | 0 | 6828 | 9830 | 11960 | 11960 | 9300 | 0 |  | 2021-01-07 07:00:00 | 2024-11-25 17:00:00 | 2021-01-07 07:00:00 | 2024-11-25 17:00:00 | 2021-11-14 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121990432.42 | 0 | 0 | 37980 | 1810340 | 1228500 | 0 | 121990432.42 | 0 | 0 | 20770 |  | NotPrmUser |  | NotPrmUser
1364 | 33613 | 1785625 | 0 | 649910 | 50048597.96 | 649910 | 12480 | 0 | 30 | 68 | 2349 | 0 | 0 | 2447 | 660 | 5240 | 5240 | 5240 | 0 |  | 2023-03-04 07:00:00 | 2024-11-25 17:00:00 | 2023-03-04 07:00:00 | 2024-11-25 17:00:00 | 2023-03-04 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50048597.96 | 0 | 0 | 15710 | 662390 | 649910 | 0 | 50048597.96 | 0 | 0 | 11670 |  | NotPrmUser |  | NotPrmUser
1364 | 32306 | 41896666.282 | 0 | 578590 | 71941834.46 | 578590 | 679967.864 | 0 | 2071 | 400 | 1912 | 2 | 0 | 4381 | 9830 | 10850 | 10850 | 8130 | 1110 |  | 2021-01-07 07:00:00 | 2024-07-17 17:00:00 | 2021-01-07 07:00:00 | 2024-07-17 17:00:00 | 2021-11-21 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71941834.46 | 0 | 0 | 22270 | 1147950 | 578590 | 0 | 71941834.46 | 0 | 0 | 9100 |  | NotPrmUser |  | NotPrmUser
1364 | 32305 | 43682291.282 | 0 | 1228500 | 121990432.42 | 1228500 | 692447.864 | 0 | 2101 | 468 | 4261 | 2 | 0 | 6828 | 9830 | 11960 | 11960 | 9240 | 0 |  | 2021-01-07 07:00:00 | 2024-11-25 17:00:00 | 2021-01-07 07:00:00 | 2024-11-25 17:00:00 | 2021-11-21 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121990432.42 | 0 | 0 | 37980 | 1810340 | 1228500 | 0 | 121990432.42 | 0 | 0 | 20770 |  | NotPrmUser |  | NotPrmUser
1365 | 35633 | 0 | 0 | 662390 | 50048597.96 | 662390 | 0 | 0 | 0 | 0 | 2447 | 0 | 0 | 2447 | 0 | 5240 | 5240 | 5240 | 0 |  |  | 2024-12-08 17:00:00 | 2023-03-16 07:00:00 | 2024-12-08 17:00:00 | 2023-03-16 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50048597.96 | 0 | 0 | 15710 | 662390 | 662390 | 0 | 50048597.96 | 0 | 0 | 15710 |  | NotPrmUser |  | NotPrmUser
1365 | 34326 | 0 | 0 | 1147950 | 71941834.46 | 1147950 | 0 | 0 | 0 | 0 | 4383 | 2 | 0 | 4381 | 0 | 10990 | 10990 | 10990 | 1080 |  |  | 2024-08-03 17:00:00 | 2021-01-07 07:00:00 | 2024-08-03 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71941834.46 | 0 | 0 | 22270 | 1147950 | 1147950 | 0 | 71941834.46 | 0 | 0 | 22270 |  | NotPrmUser |  | NotPrmUser
1365 | 36345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 3 | 0 | 9 | 0 | 12070 | 12070 | 12070 | 0 |  |  | 2024-12-08 17:00:00 | 2021-01-07 07:00:00 | 2024-12-08 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1365 | 34325 | 0 | 0 | 1810340 | 121990432.42 | 1810340 | 0 | 0 | 0 | 0 | 6842 | 5 | 0 | 6837 | 0 | 12070 | 12070 | 12070 | 0 |  |  | 2024-12-08 17:00:00 | 2021-01-07 07:00:00 | 2024-12-08 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121990432.42 | 0 | 0 | 37980 | 1810340 | 1810340 | 0 | 121990432.42 | 0 | 0 | 37980 |  | NotPrmUser |  | NotPrmUser
1366 | 37655 | 1785625 | 0 | 649910 | 50048597.96 | 649910 | 12480 | 0 | 30 | 68 | 2349 | 0 | 0 | 2447 | 660 | 5240 | 5240 | 5240 | 0 |  | 2023-03-16 07:00:00 | 2024-12-08 17:00:00 | 2023-03-16 07:00:00 | 2024-12-08 17:00:00 | 2023-03-16 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50048597.96 | 0 | 0 | 15710 | 662390 | 649910 | 0 | 50048597.96 | 0 | 0 | 11670 |  | NotPrmUser |  | NotPrmUser
1366 | 36348 | 41896666.282 | 0 | 578590 | 71941834.46 | 578590 | 679967.864 | 0 | 2071 | 400 | 1912 | 2 | 0 | 4381 | 9980 | 10990 | 10990 | 8250 | 1080 |  | 2021-01-07 07:00:00 | 2024-08-03 17:00:00 | 2021-01-07 07:00:00 | 2024-08-03 17:00:00 | 2021-11-23 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71941834.46 | 0 | 0 | 22270 | 1147950 | 578590 | 0 | 71941834.46 | 0 | 0 | 9100 |  | NotPrmUser |  | NotPrmUser
1366 | 36347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 5 | 3 | 0 | 9 | 6830 | 12070 | 12070 | 4160 | 0 |  | 2021-01-07 07:00:00 | 2024-12-08 17:00:00 | 2021-01-07 07:00:00 | 2024-12-08 17:00:00 | 2023-07-29 17:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1366 | 36346 | 43682291.282 | 0 | 1228500 | 121990432.42 | 1228500 | 692447.864 | 0 | 2108 | 468 | 4266 | 5 | 0 | 6837 | 9980 | 12070 | 12070 | 9330 | 0 |  | 2021-01-07 07:00:00 | 2024-12-08 17:00:00 | 2021-01-07 07:00:00 | 2024-12-08 17:00:00 | 2021-11-23 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121990432.42 | 0 | 0 | 37980 | 1810340 | 1228500 | 0 | 121990432.42 | 0 | 0 | 20770 |  | NotPrmUser |  | NotPrmUser
1367 | 39676 | 1785625 | 200000 | 649910 | 50048597.96 | 649910 | 12480 | 2080 | 30 | 68 | 2349 | 4 | 20 | 2423 | 1390 | 5860 | 5860 | 4980 | 0 |  | 2023-03-16 07:00:00 | 2025-02-19 17:00:00 | 2023-03-16 07:00:00 | 2025-02-19 17:00:00 | 2023-07-06 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50048597.96 | 0 | 0 | 15710 | 662390 | 649910 | 0 | 50048597.96 | 0 | 0 | 11670 |  | NotPrmUser |  | NotPrmUser
1367 | 38369 | 41896666.282 | 35417785.8268 | 578590 | 71941834.46 | 578590 | 679967.864 | 608180 | 2071 | 400 | 1912 | 2203 | 28 | 2152 | 9220 | 9770 | 10240 | 2810 | 2920 |  | 2021-01-07 07:00:00 | 2024-05-02 17:00:00 | 2021-01-07 07:00:00 | 2024-03-04 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71941834.46 | 0 | 0 | 22270 | 1147950 | 578590 | 0 | 71941834.46 | 0 | 0 | 9100 |  | NotPrmUser |  | NotPrmUser
1367 | 38368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 5 | 7 | 0 | 5 | 6830 | 12690 | 12690 | 4160 | 0 |  | 2021-01-07 07:00:00 | 2025-02-19 17:00:00 | 2021-01-07 07:00:00 | 2025-02-19 17:00:00 | 2023-10-10 17:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1367 | 38367 | 43682291.282 | 35617785.8268 | 1228500 | 121990432.42 | 1228500 | 692447.864 | 610260 | 2108 | 468 | 4266 | 2214 | 48 | 4580 | 9220 | 12690 | 12690 | 5730 | 0 |  | 2021-01-07 07:00:00 | 2025-02-19 17:00:00 | 2021-01-07 07:00:00 | 2025-02-19 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121990432.42 | 0 | 0 | 37980 | 1810340 | 1228500 | 0 | 121990432.42 | 0 | 0 | 20770 |  | NotPrmUser |  | NotPrmUser
1368 | 41697 | 1785625 | 200000 | 649910 | 50048597.96 | 649910 | 12480 | 2080 | 30 | 68 | 2349 | 4 | 20 | 2423 | 260 | 5140 | 5010 | 4880 | 0 |  | 2023-03-01 07:00:00 | 2024-11-11 17:00:00 | 2023-03-16 07:00:00 | 2024-11-11 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50048597.96 | 0 | 0 | 15710 | 662390 | 649910 | 0 | 50048597.96 | 0 | 0 | 11670 |  | NotPrmUser |  | NotPrmUser
1368 | 40390 | 41896666.282 | 35417785.8268 | 578590 | 71941834.46 | 578590 | 679967.864 | 608180 | 2071 | 400 | 1912 | 2203 | 28 | 2152 | 6960 | 9290 | 10240 | 2330 | 2550 |  | 2021-01-07 07:00:00 | 2024-05-02 17:00:00 | 2021-01-07 07:00:00 | 2024-01-07 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71941834.46 | 0 | 0 | 22270 | 1147950 | 578590 | 0 | 71941834.46 | 0 | 0 | 9100 |  | NotPrmUser |  | NotPrmUser
1368 | 40389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 5 | 7 | 0 | 5 | 6830 | 11840 | 11840 | 3370 | 0 |  | 2021-01-07 07:00:00 | 2024-11-11 17:00:00 | 2021-01-07 07:00:00 | 2024-11-11 17:00:00 | 2023-10-03 17:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1368 | 40388 | 43682291.282 | 35617785.8268 | 1228500 | 121990432.42 | 1228500 | 692447.864 | 610260 | 2108 | 468 | 4266 | 2214 | 48 | 4580 | 6960 | 11840 | 11840 | 4880 | 0 |  | 2021-01-07 07:00:00 | 2024-11-11 17:00:00 | 2021-01-07 07:00:00 | 2024-11-11 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121990432.42 | 0 | 0 | 37980 | 1810340 | 1228500 | 0 | 121990432.42 | 0 | 0 | 20770 |  | NotPrmUser |  | NotPrmUser
1369 | 43718 | 1785625 | 200000 | 649910 | 50048597.96 | 649910 | 12480 | 2080 | 30 | 68 | 2349 | 4 | 20 | 2423 | 260 | 5120 | 4990 | 4860 | 0 |  | 2023-03-01 07:00:00 | 2024-11-09 17:00:00 | 2023-03-16 07:00:00 | 2024-11-09 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50048597.96 | 0 | 0 | 15710 | 662390 | 649910 | 0 | 50048597.96 | 0 | 0 | 11670 |  | NotPrmUser |  | NotPrmUser
1369 | 42411 | 41896666.282 | 35417785.8268 | 578590 | 71941834.46 | 578590 | 679967.864 | 608180 | 2071 | 400 | 1912 | 2203 | 28 | 2152 | 6960 | 9220 | 10240 | 2260 | 2600 |  | 2021-01-07 07:00:00 | 2024-05-02 17:00:00 | 2021-01-07 07:00:00 | 2023-12-30 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71941834.46 | 0 | 0 | 22270 | 1147950 | 578590 | 0 | 71941834.46 | 0 | 0 | 9100 |  | NotPrmUser |  | NotPrmUser
1369 | 42410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 5 | 7 | 0 | 5 | 6830 | 11820 | 11820 | 3440 | 0 |  | 2021-01-07 07:00:00 | 2024-11-09 17:00:00 | 2021-01-07 07:00:00 | 2024-11-09 17:00:00 | 2023-09-21 17:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1369 | 42409 | 43682291.282 | 35617785.8268 | 1228500 | 121990432.42 | 1228500 | 692447.864 | 610260 | 2108 | 468 | 4266 | 2214 | 48 | 4580 | 6960 | 11820 | 11820 | 4860 | 0 |  | 2021-01-07 07:00:00 | 2024-11-09 17:00:00 | 2021-01-07 07:00:00 | 2024-11-09 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121990432.42 | 0 | 0 | 37980 | 1810340 | 1228500 | 0 | 121990432.42 | 0 | 0 | 20770 |  | NotPrmUser |  | NotPrmUser
1370 | 45739 | 1785625 | 200000 | 649910 | 50048597.96 | 649910 | 12480 | 2080 | 30 | 68 | 2349 | 4 | 20 | 2423 | 130 | 4990 | 4990 | 4860 | 0 |  | 2023-03-16 07:00:00 | 2024-11-09 17:00:00 | 2023-03-16 07:00:00 | 2024-11-09 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50048597.96 | 0 | 0 | 15710 | 662390 | 649910 | 0 | 50048597.96 | 0 | 0 | 11670 |  | NotPrmUser |  | NotPrmUser
1370 | 44432 | 41896666.282 | 35417785.8268 | 578590 | 71941834.46 | 578590 | 679967.864 | 608180 | 2073 | 398 | 1912 | 2203 | 28 | 2152 | 6960 | 9120 | 10240 | 2160 | 2700 |  | 2021-01-07 07:00:00 | 2024-05-02 17:00:00 | 2021-01-07 07:00:00 | 2023-12-18 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71941834.46 | 0 | 0 | 22270 | 1147950 | 578590 | 0 | 71941834.46 | 0 | 0 | 9100 |  | NotPrmUser |  | NotPrmUser
1370 | 44431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 5 | 7 | 0 | 5 | 6830 | 11820 | 11820 | 3500 | 0 |  | 2021-01-07 07:00:00 | 2024-11-09 17:00:00 | 2021-01-07 07:00:00 | 2024-11-09 17:00:00 | 2023-09-14 17:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1370 | 44430 | 43682291.282 | 35617785.8268 | 1228500 | 121990432.42 | 1228500 | 692447.864 | 610260 | 2110 | 466 | 4266 | 2214 | 48 | 4580 | 6960 | 11820 | 11820 | 4860 | 0 |  | 2021-01-07 07:00:00 | 2024-11-09 17:00:00 | 2021-01-07 07:00:00 | 2024-11-09 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121990432.42 | 0 | 0 | 37980 | 1810340 | 1228500 | 0 | 121990432.42 | 0 | 0 | 20770 |  | NotPrmUser |  | NotPrmUser
1371 | 47760 | 1785625 | 1785625 | 649910 | 48262973.32 | 649910 | 12480 | 12480 | 30 | 68 | 2349 | 30 | 68 | 2349 | 130 | 4990 | 4990 | 4860 | 0 |  | 2023-03-16 07:00:00 | 2024-11-09 17:00:00 | 2023-03-16 07:00:00 | 2024-11-09 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 1785625 | 0 | 0 | 0 | 0 | 0 | 50048598.32 | 0 | 0 | 15710 | 662390 | 649910 | 0 | 48262973.32 | 0 | 0 | 11670 |  | NotPrmUser |  | NotPrmUser
1371 | 46453 | 41896666.3044 | 41531241.9788 | 578590 | 30045168.5756 | 578590 | 679967.864 | 676171.8623 | 2073 | 398 | 1912 | 2073 | 398 | 1912 | 6960 | 9120 | 9120 | 2160 | 2700 |  | 2021-01-07 07:00:00 | 2023-12-18 17:00:00 | 2021-01-07 07:00:00 | 2023-12-18 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 41896666.3044 | 0 | 0 | 0 | 0 | 0 | 71941834.88 | 0 | 0 | 22270 | 1147950 | 578590 | 0 | 30045168.5756 | 0 | 0 | 9100 |  | NotPrmUser |  | NotPrmUser
1371 | 46452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 5 | 7 | 0 | 5 | 6830 | 11820 | 11820 | 3500 | 0 |  | 2021-01-07 07:00:00 | 2024-11-09 17:00:00 | 2021-01-07 07:00:00 | 2024-11-09 17:00:00 | 2023-09-14 17:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1371 | 46451 | 43682291.3044 | 43316866.9788 | 1228500 | 78308141.8956 | 1228500 | 692447.864 | 688651.8623 | 2110 | 466 | 4266 | 2110 | 466 | 4266 | 6960 | 11820 | 11820 | 4860 | 0 |  | 2021-01-07 07:00:00 | 2024-11-09 17:00:00 | 2021-01-07 07:00:00 | 2024-11-09 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 43682291.3044 | 0 | 0 | 0 | 0 | 0 | 121990433.2 | 0 | 0 | 37980 | 1810340 | 1228500 | 0 | 78308141.8956 | 0 | 0 | 20770 |  | NotPrmUser |  | NotPrmUser
1373 | 51802 | 1785625 | 1785625 | 649910 | 48262973.32 | 649910 | 12480 | 12480 | 30 | 68 | 2349 | 30 | 68 | 2349 | 130 | 5430 | 5430 | 5300 | 0 |  | 2023-03-16 07:00:00 | 2024-12-30 17:00:00 | 2023-03-16 07:00:00 | 2024-12-30 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 1785625 | 0 | 0 | 0 | 0 | 0 | 50048598.32 | 0 | 0 | 15710 | 662390 | 649910 | 0 | 48262973.32 | 0 | 0 | 11670 |  | NotPrmUser |  | NotPrmUser
1373 | 50495 | 41896666.3044 | 41531241.9788 | 578590 | 30045168.5756 | 578590 | 679967.864 | 676171.8623 | 2073 | 398 | 1912 | 2073 | 398 | 1912 | 6960 | 10700 | 10700 | 3740 | 1560 |  | 2021-01-07 07:00:00 | 2024-06-30 17:00:00 | 2021-01-07 07:00:00 | 2024-06-30 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 41896666.3044 | 0 | 0 | 0 | 0 | 0 | 71941834.88 | 0 | 0 | 22270 | 1147950 | 578590 | 0 | 30045168.5756 | 0 | 0 | 9100 |  | NotPrmUser |  | NotPrmUser
1373 | 50494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 5 | 7 | 0 | 5 | 6830 | 12260 | 12260 | 3660 | 0 |  | 2021-01-07 07:00:00 | 2024-12-30 17:00:00 | 2021-01-07 07:00:00 | 2024-12-30 17:00:00 | 2023-10-18 17:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1373 | 50493 | 43682291.3044 | 43316866.9788 | 1228500 | 78308141.8956 | 1228500 | 692447.864 | 688651.8623 | 2110 | 466 | 4266 | 2110 | 466 | 4266 | 6960 | 12260 | 12260 | 5300 | 0 |  | 2021-01-07 07:00:00 | 2024-12-30 17:00:00 | 2021-01-07 07:00:00 | 2024-12-30 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 43682291.3044 | 0 | 0 | 0 | 0 | 0 | 121990433.2 | 0 | 0 | 37980 | 1810340 | 1228500 | 0 | 78308141.8956 | 0 | 0 | 20770 |  | NotPrmUser |  | NotPrmUser
1374 | 53823 | 1785625 | 1785625 | 649910 | 48262973.32 | 649910 | 12480 | 12480 | 30 | 68 | 2349 | 30 | 68 | 2349 | 130 | 5430 | 5430 | 5300 | 0 |  | 2023-03-16 07:00:00 | 2024-12-30 17:00:00 | 2023-03-16 07:00:00 | 2024-12-30 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 1785625 | 0 | 0 | 0 | 0 | 0 | 50048598.32 | 0 | 0 | 15710 | 662390 | 649910 | 0 | 48262973.32 | 0 | 0 | 11670 |  | NotPrmUser |  | NotPrmUser
1374 | 52516 | 41896666.3044 | 41882132.5913 | 578590 | 30045168.5756 | 578590 | 679967.864 | 677694.5225 | 2073 | 398 | 1912 | 2073 | 398 | 1912 | 6960 | 10700 | 10700 | 3740 | 1560 |  | 2021-01-07 07:00:00 | 2024-06-30 17:00:00 | 2021-01-07 07:00:00 | 2024-06-30 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 41896666.3044 | 0 | 0 | 0 | 0 | 0 | 71941834.88 | 0 | 0 | 22270 | 1147950 | 578590 | 0 | 30045168.5756 | 0 | 0 | 9100 |  | NotPrmUser |  | NotPrmUser
1374 | 52515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 5 | 7 | 0 | 5 | 6830 | 12260 | 12260 | 3660 | 0 |  | 2021-01-07 07:00:00 | 2024-12-30 17:00:00 | 2021-01-07 07:00:00 | 2024-12-30 17:00:00 | 2023-10-18 17:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1374 | 52514 | 43682291.3044 | 43667757.5913 | 1228500 | 78308141.8956 | 1228500 | 692447.864 | 690174.5225 | 2110 | 466 | 4266 | 2110 | 466 | 4266 | 6960 | 12260 | 12260 | 5300 | 0 |  | 2021-01-07 07:00:00 | 2024-12-30 17:00:00 | 2021-01-07 07:00:00 | 2024-12-30 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 43682291.3044 | 0 | 0 | 0 | 0 | 0 | 121990433.2 | 0 | 0 | 37980 | 1810340 | 1228500 | 0 | 78308141.8956 | 0 | 0 | 20770 |  | NotPrmUser |  | NotPrmUser
1375 | 55844 | 1785625 | 1785625 | 649910 | 48262973.32 | 649910 | 12480 | 12480 | 30 | 68 | 2349 | 30 | 68 | 2349 | 130 | 5430 | 5430 | 5300 | 0 |  | 2023-03-16 07:00:00 | 2024-12-30 17:00:00 | 2023-03-16 07:00:00 | 2024-12-30 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 1785625 | 0 | 0 | 0 | 0 | 0 | 50048598.32 | 0 | 0 | 15710 | 662390 | 649910 | 0 | 48262973.32 | 0 | 0 | 11670 |  | NotPrmUser |  | NotPrmUser
1375 | 54537 | 41896666.3044 | 41882132.5913 | 578590 | 30045168.5756 | 578590 | 679967.864 | 677694.5225 | 2073 | 398 | 1912 | 2073 | 398 | 1912 | 6960 | 10700 | 10700 | 3740 | 1560 |  | 2021-01-07 07:00:00 | 2024-06-30 17:00:00 | 2021-01-07 07:00:00 | 2024-06-30 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 41896666.3044 | 0 | 0 | 0 | 0 | 0 | 71941834.88 | 0 | 0 | 22270 | 1147950 | 578590 | 0 | 30045168.5756 | 0 | 0 | 9100 |  | NotPrmUser |  | NotPrmUser
1375 | 54536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 5 | 7 | 0 | 5 | 6830 | 12260 | 12260 | 3590 | 0 |  | 2021-01-07 07:00:00 | 2024-12-30 17:00:00 | 2021-01-07 07:00:00 | 2024-12-30 17:00:00 | 2023-10-26 17:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1375 | 54535 | 43682291.3044 | 43667757.5913 | 1228500 | 78308141.8956 | 1228500 | 692447.864 | 690174.5225 | 2110 | 466 | 4266 | 2110 | 466 | 4266 | 6960 | 12260 | 12260 | 5300 | 0 |  | 2021-01-07 07:00:00 | 2024-12-30 17:00:00 | 2021-01-07 07:00:00 | 2024-12-30 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 43682291.3044 | 0 | 0 | 0 | 0 | 0 | 121990433.2 | 0 | 0 | 37980 | 1810340 | 1228500 | 0 | 78308141.8956 | 0 | 0 | 20770 |  | NotPrmUser |  | NotPrmUser
1376 | 57865 | 1785625 | 1785625 | 649910 | 48262973.32 | 649910 | 12480 | 12480 | 30 | 68 | 2349 | 30 | 68 | 2349 | 130 | 5430 | 5430 | 5300 | 0 |  | 2023-03-16 07:00:00 | 2024-12-30 17:00:00 | 2023-03-16 07:00:00 | 2024-12-30 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 1785625 | 0 | 0 | 0 | 0 | 0 | 50048598.32 | 0 | 0 | 15710 | 662390 | 649910 | 0 | 48262973.32 | 0 | 0 | 11670 |  | NotPrmUser |  | NotPrmUser
1376 | 56558 | 41896666.3044 | 41882132.5913 | 578590 | 30045168.5756 | 578590 | 679967.864 | 677694.5225 | 2073 | 398 | 1912 | 2073 | 398 | 1912 | 6960 | 10700 | 10700 | 3740 | 1560 |  | 2021-01-07 07:00:00 | 2024-06-30 17:00:00 | 2021-01-07 07:00:00 | 2024-06-30 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 41896666.3044 | 0 | 0 | 0 | 0 | 0 | 71941834.88 | 0 | 0 | 22270 | 1147950 | 578590 | 0 | 30045168.5756 | 0 | 0 | 9100 |  | NotPrmUser |  | NotPrmUser
1376 | 56557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 5 | 7 | 0 | 5 | 6830 | 12260 | 12260 | 3590 | 0 |  | 2021-01-07 07:00:00 | 2024-12-30 17:00:00 | 2021-01-07 07:00:00 | 2024-12-30 17:00:00 | 2023-10-26 17:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1376 | 56556 | 43682291.3044 | 43667757.5913 | 1228500 | 78308141.8956 | 1228500 | 692447.864 | 690174.5225 | 2110 | 466 | 4266 | 2110 | 466 | 4266 | 6960 | 12260 | 12260 | 5300 | 0 |  | 2021-01-07 07:00:00 | 2024-12-30 17:00:00 | 2021-01-07 07:00:00 | 2024-12-30 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 43682291.3044 | 0 | 0 | 0 | 0 | 0 | 121990433.2 | 0 | 0 | 37980 | 1810340 | 1228500 | 0 | 78308141.8956 | 0 | 0 | 20770 |  | NotPrmUser |  | NotPrmUser
1377 | 59885 | 0 | 0 | 662390 | 50048597.96 | 662390 | 0 | 0 | 0 | 0 | 2447 | 0 | 0 | 2447 | 0 | 5160 | 5160 | 5160 | 0 |  |  | 2025-07-03 17:00:00 | 2023-10-19 07:00:00 | 2025-07-03 17:00:00 | 2023-10-19 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50048597.96 | 0 | 0 | 15710 | 662390 | 662390 | 0 | 50048597.96 | 0 | 0 | 15710 |  | NotPrmUser |  | NotPrmUser
1377 | 58578 | 0 | 0 | 1147950 | 71941834.46 | 1147950 | 0 | 0 | 0 | 0 | 4383 | 2 | 0 | 4381 | 0 | 12800 | 12800 | 12800 | 960 |  |  | 2025-03-04 17:00:00 | 2021-01-07 07:00:00 | 2025-03-04 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71941834.46 | 0 | 0 | 22270 | 1147950 | 1147950 | 0 | 71941834.46 | 0 | 0 | 22270 |  | NotPrmUser |  | NotPrmUser
1377 | 58577 | 0 | 0 | 1810340 | 121990432.42 | 1810340 | 0 | 0 | 0 | 0 | 6830 | 2 | 0 | 6828 | 0 | 13760 | 13760 | 13760 | 0 |  |  | 2025-07-03 17:00:00 | 2021-01-07 07:00:00 | 2025-07-03 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121990432.42 | 0 | 0 | 37980 | 1810340 | 1810340 | 0 | 121990432.42 | 0 | 0 | 37980 |  | NotPrmUser |  | NotPrmUser
1378 | 61906 | 1785625 | 1785625 | 521950 | 48262973.32 | 511430 | 10520 | 10520 | 30 | 68 | 2349 | 30 | 68 | 2349 | 130 | 5430 | 5430 | 5300 | 0 |  | 2023-03-16 07:00:00 | 2024-12-30 17:00:00 | 2023-03-16 07:00:00 | 2024-12-30 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 1785625 | 0 | 0 | 4040 | 10520 | 0 | 50048598.32 | 0 | 0 | 15710 | 521950 | 511430 | 0 | 48262973.32 | 0 | 0 | 11670 |  | NotPrmUser |  | NotPrmUser
1378 | 60599 | 41896666.3044 | 41882132.5913 | 899390 | 30045168.5756 | 377132.983 | 522257.017 | 520930.7934 | 2073 | 398 | 1912 | 2073 | 398 | 1912 | 6960 | 10700 | 10700 | 3740 | 1560 |  | 2021-01-07 07:00:00 | 2024-06-30 17:00:00 | 2021-01-07 07:00:00 | 2024-06-30 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 41896666.3044 | 0 | 0 | 13170 | 522257.017 | 0 | 71941834.88 | 0 | 0 | 22270 | 899390 | 377132.983 | 0 | 30045168.5756 | 0 | 0 | 9100 |  | NotPrmUser |  | NotPrmUser
1378 | 60598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 5 | 7 | 0 | 5 | 6830 | 12260 | 12260 | 3590 | 0 |  | 2021-01-07 07:00:00 | 2024-12-30 17:00:00 | 2021-01-07 07:00:00 | 2024-12-30 17:00:00 | 2023-10-26 17:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1378 | 60597 | 43682291.3044 | 43667757.5913 | 1421340 | 78308141.8956 | 888562.983 | 532777.017 | 531450.7934 | 2110 | 466 | 4266 | 2110 | 466 | 4266 | 6960 | 12260 | 12260 | 5300 | 0 |  | 2021-01-07 07:00:00 | 2024-12-30 17:00:00 | 2021-01-07 07:00:00 | 2024-12-30 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 43682291.3044 | 0 | 0 | 17210 | 532777.017 | 0 | 121990433.2 | 0 | 0 | 37980 | 1421340 | 888562.983 | 0 | 78308141.8956 | 0 | 0 | 20770 |  | NotPrmUser |  | NotPrmUser
1379 | 63934 | 0 | 0 | 39070 | 2000000 | 39070 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 25 | 0 | 2050 | 2050 | 2050 | 10 |  |  | 2024-12-07 17:00:00 | 2024-04-02 07:00:00 | 2024-12-07 17:00:00 | 2024-04-02 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 0 | 0 | 8990 | 39070 | 39070 | 0 | 2000000 | 0 | 0 | 8990 |  | NotPrmUser |  | NotPrmUser
1379 | 62619 | 0 | 0 | 54270 | 4000000 | 54270 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 29 | 0 | 2050 | 2050 | 2050 | 1080 |  |  | 2024-08-03 17:00:00 | 2023-11-28 07:00:00 | 2024-08-03 17:00:00 | 2023-11-28 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000000 | 0 | 0 | 8990 | 54270 | 54270 | 0 | 4000000 | 0 | 0 | 8990 |  | NotPrmUser |  | NotPrmUser
1379 | 62618 | 0 | 0 | 93340 | 6000000 | 93340 | 0 | 0 | 0 | 0 | 54 | 0 | 0 | 54 | 0 | 3120 | 3120 | 3120 | 10 |  |  | 2024-12-07 17:00:00 | 2023-11-28 07:00:00 | 2024-12-07 17:00:00 | 2023-11-28 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000000 | 0 | 0 | 17980 | 93340 | 93340 | 0 | 6000000 | 0 | 0 | 17980 |  | NotPrmUser |  | NotPrmUser
1380 | 64807 | 0 | 0 | 3800 | 500000 | 3800 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 380 | 380 | 380 | 4860 |  |  | 2021-02-20 17:00:00 | 2021-01-07 07:00:00 | 2021-02-20 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 3800 | 3800 | 0 | 500000 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1380 | 64806 | 0 | 0 | 1040 | 500000 | 1040 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 260 | 260 | 260 | 420 |  |  | 2022-07-16 17:00:00 | 2022-06-16 07:00:00 | 2022-07-16 17:00:00 | 2022-06-16 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 1040 | 1040 | 0 | 500000 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1380 | 64785 | 0 | 0 | 19570 | 788494 | 19570 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 80 | 0 | 3720 | 3720 | 3720 | 410 |  |  | 2022-07-20 17:00:00 | 2021-05-13 07:00:00 | 2022-07-20 17:00:00 | 2021-05-13 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 788494 | 0 | 0 | 0 | 19570 | 19570 | 0 | 788494 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1380 | 64754 | 0 | 0 | 27580 | 1108593 | 27580 | 0 | 0 | 0 | 0 | 85 | 0 | 0 | 85 | 0 | 4080 | 4080 | 4080 | 430 |  |  | 2022-07-20 17:00:00 | 2021-04-01 07:00:00 | 2022-07-20 17:00:00 | 2021-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1108593 | 0 | 0 | 0 | 27580 | 27580 | 0 | 1108593 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1380 | 64712 | 0 | 0 | 73880 | 5780965 | 73880 | 0 | 0 | 0 | 0 | 238 | 0 | 0 | 238 | 0 | 3740 | 3740 | 3740 | 0 |  |  | 2022-09-10 17:00:00 | 2021-07-01 07:00:00 | 2022-09-10 17:00:00 | 2021-07-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5780965 | 0 | 0 | 0 | 73880 | 73880 | 0 | 5780965 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1380 | 64681 | 0 | 0 | 32920 | 3686800 | 32920 | 0 | 0 | 0 | 0 | 105 | 0 | 0 | 105 | 0 | 4310 | 4310 | 4310 | 670 |  |  | 2022-06-23 17:00:00 | 2021-02-07 07:00:00 | 2022-06-23 17:00:00 | 2021-02-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3686800 | 0 | 0 | 1680 | 32920 | 32920 | 0 | 3686800 | 0 | 0 | 1680 |  | NotPrmUser |  | NotPrmUser
1380 | 64680 | 0 | 0 | 1040 | 100000 | 1040 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 260 | 260 | 260 | 0 |  |  | 2021-02-06 17:00:00 | 2021-01-07 07:00:00 | 2021-02-06 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 1040 | 1040 | 0 | 100000 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1380 | 64650 | 0 | 0 | 159830 | 12464852 | 159830 | 0 | 0 | 0 | 0 | 511 | 0 | 0 | 511 | 0 | 5240 | 5240 | 5240 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12464852 | 0 | 0 | 1680 | 159830 | 159830 | 0 | 12464852 | 0 | 0 | 1680 |  | NotPrmUser |  | NotPrmUser
1381 | 64985 | 0 | 0 | 3600 | 0 | 3600 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 30 | 0 | 480 | 480 | 480 | 0 |  |  | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 3600 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1381 | 64856 | 0 | 0 | 159830 | 12464852 | 159830 | 0 | 0 | 0 | 0 | 511 | 0 | 0 | 511 | 0 | 5240 | 5240 | 5240 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12464852 | 0 | 0 | 1680 | 159830 | 159830 | 0 | 12464852 | 0 | 0 | 1680 |  | NotPrmUser |  | NotPrmUser
1381 | 64834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 56 | 0 | 1200 | 1200 | 1200 | 3740 |  |  | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1381 | 64829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 820 | 820 | 820 | 3560 |  |  | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1381 | 64828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 5240 | 5240 | 5240 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1381 | 64827 | 0 | 0 | 163430 | 12464852 | 163430 | 0 | 0 | 0 | 0 | 607 | 1 | 0 | 606 | 0 | 5240 | 5240 | 5240 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12464852 | 0 | 0 | 1680 | 163430 | 163430 | 0 | 12464852 | 0 | 0 | 1680 |  | NotPrmUser |  | NotPrmUser
1383 | 66434 | 1785625 | 1785625 | 662390 | 48262973.32 | 649910 | 12480 | 12480 | 12 | 86 | 2349 | 30 | 68 | 2349 | 130 | 5430 | 5430 | 5300 | 0 |  | 2023-03-16 07:00:00 | 2024-12-30 17:00:00 | 2023-03-16 07:00:00 | 2024-12-30 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 1785625 | 0 | 0 | 4040 | 12480 | 0 | 50048598.32 | 0 | 0 | 15710 | 662390 | 649910 | 0 | 48262973.32 | 0 | 0 | 11670 |  | NotPrmUser |  | NotPrmUser
1383 | 65127 | 41896666.2179 | 41882132.5048 | 1147950 | 30045168.4923 | 471342.136 | 676607.864 | 674334.5225 | 386 | 2055 | 1942 | 2043 | 398 | 1942 | 5720 | 9460 | 9460 | 3740 | 1560 |  | 2021-06-01 07:00:00 | 2024-06-30 17:00:00 | 2021-06-01 07:00:00 | 2024-06-30 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 41896666.2877 | 0 | 0 | 13170 | 676607.864 | 0 | 71941834.7935 | 0 | 0 | 22270 | 1147950 | 471342.136 | 0 | 30045168.4923 | 0 | 0 | 9100 |  | NotPrmUser |  | NotPrmUser
1383 | 65126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 6 | 6 | 0 | 6 | 5590 | 11020 | 12260 | 5050 | 0 |  | 2021-06-01 07:00:00 | 2024-12-30 17:00:00 | 2021-01-07 07:00:00 | 2024-12-30 17:00:00 | 2023-05-03 17:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1383 | 65125 | 43682291.2179 | 43667757.5048 | 1810340 | 78308141.8123 | 1121252.136 | 689087.864 | 686814.5225 | 404 | 2141 | 4297 | 2079 | 466 | 4297 | 5720 | 11020 | 12260 | 5300 | 0 |  | 2021-06-01 07:00:00 | 2024-12-30 17:00:00 | 2021-01-07 07:00:00 | 2024-12-30 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 43682291.2877 | 0 | 0 | 17210 | 689087.864 | 0 | 121990433.1135 | 0 | 0 | 37980 | 1810340 | 1121252.136 | 0 | 78308141.8123 | 0 | 0 | 20770 |  | NotPrmUser |  | NotPrmUser
1385 | 67673 | 0 | 0 | 1680 | 0 | 1680 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 14 | 0 | 230 | 230 | 230 | 0 |  |  | 2023-05-01 17:00:00 | 2023-04-01 07:00:00 | 2023-05-01 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1680 | 1680 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1385 | 67592 | 0 | 0 | 81470 | 4750032 | 81470 | 0 | 0 | 0 | 0 | 282 | 0 | 0 | 282 | 0 | 5720 | 5720 | 5720 | 230 |  |  | 2023-03-30 17:00:00 | 2021-06-01 07:00:00 | 2023-03-30 17:00:00 | 2021-06-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4750032 | 0 | 0 | 1600 | 81470 | 81470 | 0 | 4750032 | 0 | 0 | 1600 |  | NotPrmUser |  | NotPrmUser
1385 | 67570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 56 | 0 | 1200 | 1200 | 1200 | 4450 |  |  | 2021-11-22 17:00:00 | 2021-07-06 07:00:00 | 2021-11-22 17:00:00 | 2021-07-06 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1385 | 67565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 820 | 820 | 820 | 1420 |  |  | 2021-09-04 17:00:00 | 2021-06-01 07:00:00 | 2021-09-04 17:00:00 | 2021-06-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1385 | 67564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 5950 | 5950 | 5950 | 0 |  |  | 2023-05-01 17:00:00 | 2021-06-01 07:00:00 | 2023-05-01 17:00:00 | 2021-06-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1385 | 67563 | 0 | 0 | 83150 | 4750032 | 83150 | 0 | 0 | 0 | 0 | 362 | 1 | 0 | 361 | 0 | 5950 | 5950 | 5950 | 0 |  |  | 2023-05-01 17:00:00 | 2021-06-01 07:00:00 | 2023-05-01 17:00:00 | 2021-06-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4750032 | 0 | 0 | 1600 | 83150 | 83150 | 0 | 4750032 | 0 | 0 | 1600 |  | NotPrmUser |  | NotPrmUser
1386 | 67928 | 1785625 | 1785625 | 662390 | 48262973.32 | 649910 | 12480 | 12480 | 30 | 68 | 2349 | 30 | 68 | 2349 | 130 | 5430 | 5430 | 5300 | 0 |  | 2023-03-16 07:00:00 | 2024-12-30 17:00:00 | 2023-03-16 07:00:00 | 2024-12-30 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 1785625 | 0 | 0 | 4040 | 12480 | 0 | 50048598.32 | 0 | 0 | 15710 | 662390 | 649910 | 0 | 48262973.32 | 0 | 0 | 11670 |  | NotPrmUser |  | NotPrmUser
1386 | 67927 | 41896666.2044 | 41882132.4913 | 1147950 | 30045168.52 | 471342.136 | 676607.864 | 674334.5225 | 2043 | 398 | 1942 | 2043 | 398 | 1942 | 5720 | 9460 | 9460 | 3740 | 1560 |  | 2021-06-01 07:00:00 | 2024-06-30 17:00:00 | 2021-06-01 07:00:00 | 2024-06-30 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 41896666.26 | 0 | 0 | 13170 | 676607.864 | 0 | 71941834.78 | 0 | 0 | 22270 | 1147950 | 471342.136 | 0 | 30045168.52 | 0 | 0 | 9100 |  | NotPrmUser |  | NotPrmUser
1386 | 67926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 6 | 6 | 0 | 6 | 5590 | 11020 | 12260 | 5070 | 0 |  | 2021-06-01 07:00:00 | 2024-12-30 17:00:00 | 2021-01-07 07:00:00 | 2024-12-30 17:00:00 | 2023-05-01 17:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1386 | 67925 | 43682291.2044 | 43667757.4913 | 1810340 | 78308141.84 | 1121252.136 | 689087.864 | 686814.5225 | 2079 | 466 | 4297 | 2079 | 466 | 4297 | 5720 | 11020 | 12260 | 5300 | 0 |  | 2021-06-01 07:00:00 | 2024-12-30 17:00:00 | 2021-01-07 07:00:00 | 2024-12-30 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 43682291.26 | 0 | 0 | 17210 | 689087.864 | 0 | 121990433.1 | 0 | 0 | 37980 | 1810340 | 1121252.136 | 0 | 78308141.84 | 0 | 0 | 20770 |  | NotPrmUser |  | NotPrmUser
1437 | 73305 | 1785625 | 1785625 | 662390 | 48262973.32 | 649910 | 12480 | 12480 | 30 | 68 | 2349 | 30 | 68 | 2349 | 130 | 5430 | 5430 | 5300 | 0 |  | 2023-03-16 07:00:00 | 2024-12-30 17:00:00 | 2023-03-16 07:00:00 | 2024-12-30 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 1785625 | 0 | 0 | 4040 | 12480 | 0 | 50048598.32 | 0 | 0 | 15710 | 662390 | 649910 | 0 | 48262973.32 | 0 | 0 | 11670 |  | NotPrmUser |  | NotPrmUser
1437 | 71998 | 41896666.2044 | 41882132.4913 | 1147950 | 30045168.52 | 471342.136 | 676607.864 | 674334.5225 | 2043 | 398 | 1942 | 2043 | 398 | 1942 | 5380 | 9120 | 10758 | 3740 | 1560 |  | 2021-07-11 00:00:00 | 2024-06-30 17:00:00 | 2021-01-01 08:00:00 | 2024-06-30 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 41896666.26 | 0 | 0 | 13170 | 676607.864 | 0 | 71941834.78 | 0 | 0 | 22270 | 1147950 | 471342.136 | 0 | 30045168.52 | 0 | 0 | 9100 |  | NotPrmUser |  | NotPrmUser
1437 | 71997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 6 | 6 | 0 | 6 | 5250 | 10680 | 12318 | 5070 | 0 |  | 2021-07-11 00:00:00 | 2024-12-30 17:00:00 | 2021-01-01 08:00:00 | 2024-12-30 17:00:00 | 2023-05-01 17:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1437 | 71996 | 43682291.2044 | 43667757.4913 | 1810340 | 78308141.84 | 1121252.136 | 689087.864 | 686814.5225 | 2079 | 466 | 4297 | 2079 | 466 | 4297 | 5380 | 10680 | 12318 | 5300 | 0 |  | 2021-07-11 00:00:00 | 2024-12-30 17:00:00 | 2021-01-01 08:00:00 | 2024-12-30 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 43682291.26 | 0 | 0 | 17210 | 689087.864 | 0 | 121990433.1 | 0 | 0 | 37980 | 1810340 | 1121252.136 | 0 | 78308141.84 | 0 | 0 | 20770 |  | NotPrmUser |  | NotPrmUser
1441 | 76046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 240 | 240 | 240 | 0 |  |  | 2024-09-29 17:00:00 | 2024-09-01 07:00:00 | 2024-09-29 17:00:00 | 2024-09-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1441 | 76045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0 | 160 | 160 | 160 | 0 |  |  | 2024-09-14 17:00:00 | 2024-08-27 07:00:00 | 2024-09-14 17:00:00 | 2024-08-27 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1441 | 76044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 297 | 1 | 0 | 296 | 0 | 3030 | 3030 | 3030 | 0 |  |  | 2024-09-29 17:00:00 | 2023-10-01 07:00:00 | 2024-09-29 17:00:00 | 2023-10-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1441 | 76043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128 | 0 | 0 | 128 | 0 | 1080 | 1080 | 1080 | 1690 |  |  | 2024-02-03 17:00:00 | 2023-10-01 07:00:00 | 2024-02-03 17:00:00 | 2023-10-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1441 | 76042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 0 | 0 | 68 | 0 | 300 | 300 | 300 | 2730 |  |  | 2023-11-04 17:00:00 | 2023-10-01 07:00:00 | 2023-11-04 17:00:00 | 2023-10-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1441 | 76041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 3030 | 3030 | 3030 | 0 |  |  | 2024-09-29 17:00:00 | 2023-10-01 07:00:00 | 2024-09-29 17:00:00 | 2023-10-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1441 | 76040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 2 | 0 | 498 | 0 | 3030 | 3030 | 3030 | 0 |  |  | 2024-09-29 17:00:00 | 2023-10-01 07:00:00 | 2024-09-29 17:00:00 | 2023-10-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1445 | 76345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 20 | 20 | 20 | 0 |  |  | 2024-02-29 17:00:00 | 2024-02-28 07:00:00 | 2024-02-29 17:00:00 | 2024-02-28 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1445 | 76343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0 | 60 | 60 | 60 | 0 |  |  | 2024-02-28 17:00:00 | 2024-02-21 07:00:00 | 2024-02-28 17:00:00 | 2024-02-21 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1445 | 76278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 294 | 0 | 0 | 294 | 0 | 1010 | 1010 | 1010 | 0 |  |  | 2024-02-27 17:00:00 | 2023-11-01 07:00:00 | 2024-02-27 17:00:00 | 2023-11-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1445 | 76199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 1030 | 1030 | 1030 | 0 |  |  | 2024-02-29 17:00:00 | 2023-11-01 07:00:00 | 2024-02-29 17:00:00 | 2023-11-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1445 | 76198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 301 | 1 | 0 | 300 | 0 | 1030 | 1030 | 1030 | 0 |  |  | 2024-02-29 17:00:00 | 2023-11-01 07:00:00 | 2024-02-29 17:00:00 | 2023-11-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1446 | 76494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 240 | 240 | 240 | 0 |  |  | 2025-07-16 17:00:00 | 2025-06-19 07:00:00 | 2025-07-16 17:00:00 | 2025-06-19 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1446 | 76492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 9 | 0 | 380 | 380 | 380 | 0 |  |  | 2025-07-02 17:00:00 | 2025-05-15 07:00:00 | 2025-07-02 17:00:00 | 2025-05-15 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1446 | 76427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 891 | 3 | 0 | 888 | 0 | 5420 | 5420 | 5420 | 0 |  |  | 2025-07-16 17:00:00 | 2023-10-01 07:00:00 | 2025-07-16 17:00:00 | 2023-10-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1446 | 76387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128 | 0 | 0 | 128 | 0 | 1080 | 1080 | 1080 | 3980 |  |  | 2024-02-03 17:00:00 | 2023-10-01 07:00:00 | 2024-02-03 17:00:00 | 2023-10-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1446 | 76349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 0 | 0 | 68 | 0 | 300 | 300 | 300 | 5120 |  |  | 2023-11-04 17:00:00 | 2023-10-01 07:00:00 | 2023-11-04 17:00:00 | 2023-10-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1446 | 76348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 5420 | 5420 | 5420 | 0 |  |  | 2025-07-16 17:00:00 | 2023-10-01 07:00:00 | 2025-07-16 17:00:00 | 2023-10-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1446 | 76347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1104 | 4 | 0 | 1100 | 0 | 5420 | 5420 | 5420 | 0 |  |  | 2025-07-16 17:00:00 | 2023-10-01 07:00:00 | 2025-07-16 17:00:00 | 2023-10-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1447 | 76905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 3930 | 3930 | 3930 | 0 |  |  | 2026-04-30 17:00:00 | 2025-01-09 07:00:00 | 2026-04-30 17:00:00 | 2025-01-09 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1447 | 76901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 9 | 0 | 4150 | 4150 | 4150 | 0 |  |  | 2026-04-23 17:00:00 | 2024-12-08 07:00:00 | 2026-04-23 17:00:00 | 2024-12-08 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1447 | 76708 | 0 | 0 | 934920 | 59790826.4 | 934920 | 0 | 0 | 0 | 0 | 891 | 1 | 0 | 890 | 0 | 7830 | 7830 | 7830 | 0 |  |  | 2026-04-30 17:00:00 | 2023-10-01 07:00:00 | 2026-04-30 17:00:00 | 2023-10-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59790826.4 | 0 | 0 | 21600 | 934920 | 934920 | 0 | 59790826.4 | 0 | 0 | 21600 |  | NotPrmUser |  | NotPrmUser
1447 | 76668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128 | 0 | 0 | 128 | 0 | 1080 | 1080 | 1080 | 6510 |  |  | 2024-02-03 17:00:00 | 2023-10-01 07:00:00 | 2024-02-03 17:00:00 | 2023-10-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1447 | 76630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 0 | 0 | 68 | 0 | 300 | 300 | 300 | 7530 |  |  | 2023-11-04 17:00:00 | 2023-10-01 07:00:00 | 2023-11-04 17:00:00 | 2023-10-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1447 | 76629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 7830 | 7830 | 7830 | 0 |  |  | 2026-04-30 17:00:00 | 2023-10-01 07:00:00 | 2026-04-30 17:00:00 | 2023-10-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1447 | 76628 | 0 | 0 | 934920 | 59790826.4 | 934920 | 0 | 0 | 0 | 0 | 1104 | 2 | 0 | 1102 | 0 | 7830 | 7830 | 7830 | 0 |  |  | 2026-04-30 17:00:00 | 2023-10-01 07:00:00 | 2026-04-30 17:00:00 | 2023-10-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59790826.4 | 0 | 0 | 21600 | 934920 | 934920 | 0 | 59790826.4 | 0 | 0 | 21600 |  | NotPrmUser |  | NotPrmUser
1448 | 77186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 3890 | 3890 | 3890 | 0 |  |  | 2026-04-30 17:00:00 | 2025-01-14 07:00:00 | 2026-04-30 17:00:00 | 2025-01-14 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1448 | 77182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 9 | 0 | 3990 | 3990 | 3990 | 0 |  |  | 2026-04-23 17:00:00 | 2024-12-26 07:00:00 | 2026-04-23 17:00:00 | 2024-12-26 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1448 | 76989 | 0 | 0 | 752260 | 43460000 | 752260 | 0 | 0 | 0 | 0 | 774 | 1 | 0 | 773 | 0 | 7830 | 7830 | 7830 | 0 |  |  | 2026-04-30 17:00:00 | 2023-10-01 07:00:00 | 2026-04-30 17:00:00 | 2023-10-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43460000 | 0 | 0 | 20040 | 752260 | 752260 | 0 | 43460000 | 0 | 0 | 20040 |  | NotPrmUser |  | NotPrmUser
1448 | 76949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124 | 0 | 0 | 124 | 0 | 1080 | 1080 | 1080 | 6510 |  |  | 2024-02-03 17:00:00 | 2023-10-01 07:00:00 | 2024-02-03 17:00:00 | 2023-10-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1448 | 76911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 0 | 0 | 62 | 0 | 300 | 300 | 300 | 7290 |  |  | 2023-11-04 17:00:00 | 2023-10-01 07:00:00 | 2023-11-04 17:00:00 | 2023-10-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1448 | 76910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 7830 | 7830 | 7830 | 0 |  |  | 2026-04-30 17:00:00 | 2023-10-01 07:00:00 | 2026-04-30 17:00:00 | 2023-10-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1448 | 76909 | 0 | 0 | 752260 | 43460000 | 752260 | 0 | 0 | 0 | 0 | 977 | 2 | 0 | 975 | 0 | 7830 | 7830 | 7830 | 0 |  |  | 2026-04-30 17:00:00 | 2023-10-01 07:00:00 | 2026-04-30 17:00:00 | 2023-10-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43460000 | 0 | 0 | 20040 | 752260 | 752260 | 0 | 43460000 | 0 | 0 | 20040 |  | NotPrmUser |  | NotPrmUser
1449 | 77256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 30 | 30 | 30 | 0 |  |  | 2024-02-10 17:00:00 | 2024-02-07 07:00:00 | 2024-02-10 17:00:00 | 2024-02-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1449 | 77255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0 | 70 | 70 | 70 | 0 |  |  | 2024-02-08 17:00:00 | 2024-02-01 07:00:00 | 2024-02-08 17:00:00 | 2024-02-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1449 | 77192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 294 | 0 | 0 | 294 | 0 | 1030 | 1030 | 1030 | 0 |  |  | 2024-02-06 17:00:00 | 2023-10-10 07:00:00 | 2024-02-06 17:00:00 | 2023-10-10 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1449 | 77191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 1060 | 1060 | 1060 | 0 |  |  | 2024-02-10 17:00:00 | 2023-10-10 07:00:00 | 2024-02-10 17:00:00 | 2023-10-10 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1449 | 77190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 301 | 1 | 0 | 300 | 0 | 1060 | 1060 | 1060 | 0 |  |  | 2024-02-10 17:00:00 | 2023-10-10 07:00:00 | 2024-02-10 17:00:00 | 2023-10-10 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1450 | 77518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 5150 | 5150 | 5150 | 0 |  |  | 2026-04-30 17:00:00 | 2024-08-19 07:00:00 | 2026-04-30 17:00:00 | 2024-08-19 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1450 | 77514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 9 | 0 | 5250 | 5250 | 5250 | 0 |  |  | 2026-04-23 17:00:00 | 2024-07-31 07:00:00 | 2026-04-23 17:00:00 | 2024-07-31 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1450 | 77333 | 0 | 0 | 752260 | 43460000 | 752260 | 0 | 0 | 0 | 0 | 774 | 1 | 0 | 773 | 0 | 9090 | 9090 | 9090 | 0 |  |  | 2026-04-30 17:00:00 | 2023-05-01 07:00:00 | 2026-04-30 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43460000 | 0 | 0 | 20040 | 752260 | 752260 | 0 | 43460000 | 0 | 0 | 20040 |  | NotPrmUser |  | NotPrmUser
1450 | 77294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124 | 0 | 0 | 124 | 0 | 1080 | 1080 | 1080 | 7770 |  |  | 2023-09-07 17:00:00 | 2023-05-01 07:00:00 | 2023-09-07 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1450 | 77259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 0 | 0 | 62 | 0 | 300 | 300 | 300 | 8550 |  |  | 2023-06-04 17:00:00 | 2023-05-01 07:00:00 | 2023-06-04 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1450 | 77258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 9090 | 9090 | 9090 | 0 |  |  | 2026-04-30 17:00:00 | 2023-05-01 07:00:00 | 2026-04-30 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1450 | 77257 | 0 | 0 | 752260 | 43460000 | 752260 | 0 | 0 | 0 | 0 | 977 | 2 | 0 | 975 | 0 | 9090 | 9090 | 9090 | 0 |  |  | 2026-04-30 17:00:00 | 2023-05-01 07:00:00 | 2026-04-30 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43460000 | 0 | 0 | 20040 | 752260 | 752260 | 0 | 43460000 | 0 | 0 | 20040 |  | NotPrmUser |  | NotPrmUser
1451 | 77783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 5150 | 5150 | 5150 | 0 |  |  | 2026-04-30 17:00:00 | 2024-08-19 07:00:00 | 2026-04-30 17:00:00 | 2024-08-19 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1451 | 77787 | 0 | 0 | 1920 | 0 | 1920 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 9 | 0 | 5140 | 5140 | 5140 | 70 |  |  | 2026-04-22 17:00:00 | 2024-08-12 07:00:00 | 2026-04-22 17:00:00 | 2024-08-12 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1920 | 1920 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1451 | 77779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 9 | 0 | 5250 | 5250 | 5250 | 0 |  |  | 2026-04-23 17:00:00 | 2024-07-31 07:00:00 | 2026-04-23 17:00:00 | 2024-07-31 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1451 | 77598 | 0 | 0 | 752260 | 43460000 | 752260 | 0 | 0 | 0 | 0 | 774 | 1 | 0 | 773 | 0 | 9090 | 9090 | 9090 | 0 |  |  | 2026-04-30 17:00:00 | 2023-05-01 07:00:00 | 2026-04-30 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43460000 | 0 | 0 | 20040 | 752260 | 752260 | 0 | 43460000 | 0 | 0 | 20040 |  | NotPrmUser |  | NotPrmUser
1451 | 77559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124 | 0 | 0 | 124 | 0 | 1080 | 1080 | 1080 | 7770 |  |  | 2023-09-07 17:00:00 | 2023-05-01 07:00:00 | 2023-09-07 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1451 | 77524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 0 | 0 | 62 | 0 | 300 | 300 | 300 | 8550 |  |  | 2023-06-04 17:00:00 | 2023-05-01 07:00:00 | 2023-06-04 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1451 | 77523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 9090 | 9090 | 9090 | 0 |  |  | 2026-04-30 17:00:00 | 2023-05-01 07:00:00 | 2026-04-30 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1451 | 77522 | 0 | 0 | 754180 | 43460000 | 754180 | 0 | 0 | 0 | 0 | 986 | 2 | 0 | 984 | 0 | 9090 | 9090 | 9090 | 0 |  |  | 2026-04-30 17:00:00 | 2023-05-01 07:00:00 | 2026-04-30 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43460000 | 0 | 0 | 20040 | 754180 | 754180 | 0 | 43460000 | 0 | 0 | 20040 |  | NotPrmUser |  | NotPrmUser
1453 | 78325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 120 | 120 | 120 | 0 |  |  | 2026-04-30 17:00:00 | 2026-04-18 07:00:00 | 2026-04-30 17:00:00 | 2026-04-18 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1453 | 78317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 9 | 0 | 60 | 60 | 60 | 0 |  |  | 2026-04-23 17:00:00 | 2026-04-18 07:00:00 | 2026-04-23 17:00:00 | 2026-04-18 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1453 | 78321 | 0 | 0 | 1920 | 0 | 1920 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 9 | 0 | 110 | 110 | 110 | 0 |  |  | 2026-04-16 17:00:00 | 2026-04-05 07:00:00 | 2026-04-16 17:00:00 | 2026-04-05 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1920 | 1920 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1453 | 78136 | 0 | 0 | 752260 | 43460000 | 752260 | 0 | 0 | 0 | 0 | 774 | 1 | 0 | 773 | 0 | 8970 | 8970 | 8970 | 120 |  |  | 2026-04-16 17:00:00 | 2023-05-01 07:00:00 | 2026-04-16 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43460000 | 0 | 0 | 20040 | 752260 | 752260 | 0 | 43460000 | 0 | 0 | 20040 |  | NotPrmUser |  | NotPrmUser
1453 | 78097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124 | 0 | 0 | 124 | 0 | 1080 | 1080 | 1080 | 7890 |  |  | 2023-09-07 17:00:00 | 2023-05-01 07:00:00 | 2023-09-07 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1453 | 78062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 0 | 0 | 62 | 0 | 300 | 300 | 300 | 8670 |  |  | 2023-06-04 17:00:00 | 2023-05-01 07:00:00 | 2023-06-04 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1453 | 78061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 9090 | 9090 | 9090 | 0 |  |  | 2026-04-30 17:00:00 | 2023-05-01 07:00:00 | 2026-04-30 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1453 | 78060 | 0 | 0 | 754180 | 43460000 | 754180 | 0 | 0 | 0 | 0 | 986 | 2 | 0 | 984 | 0 | 9090 | 9090 | 9090 | 0 |  |  | 2026-04-30 17:00:00 | 2023-05-01 07:00:00 | 2026-04-30 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43460000 | 0 | 0 | 20040 | 754180 | 754180 | 0 | 43460000 | 0 | 0 | 20040 |  | NotPrmUser |  | NotPrmUser
1455 | 78332 | 0 | 0 | 163200 | 14303603.61 | 163200 | 0 | 0 | 0 | 0 | 839 | 1 | 0 | 838 | 0 | 3860 | 3860 | 3860 | 0 |  |  | 2024-10-15 17:00:00 | 2023-07-11 07:00:00 | 2024-10-15 17:00:00 | 2023-07-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14303603.61 | 0 | 0 | 2340 | 163200 | 163200 | 0 | 14303603.61 | 0 | 0 | 2340 |  | NotPrmUser |  | NotPrmUser
1455 | 78331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1455 | 78330 | 0 | 0 | 163200 | 14303603.61 | 163200 | 0 | 0 | 0 | 0 | 839 | 1 | 0 | 838 | 0 | 3860 | 3860 | 3860 | 0 |  |  | 2024-10-15 17:00:00 | 2023-07-11 07:00:00 | 2024-10-15 17:00:00 | 2023-07-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14303603.61 | 0 | 0 | 2340 | 163200 | 163200 | 0 | 14303603.61 | 0 | 0 | 2340 |  | NotPrmUser |  | NotPrmUser
1457 | 79074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 120 | 120 | 120 | 0 |  |  | 2026-04-30 17:00:00 | 2026-04-18 07:00:00 | 2026-04-30 17:00:00 | 2026-04-18 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1457 | 79070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 9 | 0 | 60 | 60 | 60 | 0 |  |  | 2026-04-23 17:00:00 | 2026-04-18 07:00:00 | 2026-04-23 17:00:00 | 2026-04-18 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1457 | 79066 | 0 | 0 | 1920 | 0 | 1920 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 9 | 0 | 110 | 110 | 110 | 0 |  |  | 2026-04-16 17:00:00 | 2026-04-05 07:00:00 | 2026-04-16 17:00:00 | 2026-04-05 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1920 | 1920 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1457 | 78885 | 0 | 0 | 752260 | 56498000.24 | 752260 | 0 | 0 | 0 | 0 | 774 | 1 | 0 | 773 | 0 | 8970 | 8970 | 8970 | 120 |  |  | 2026-04-16 17:00:00 | 2023-05-01 07:00:00 | 2026-04-16 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56498000.24 | 0 | 0 | 20040 | 752260 | 752260 | 0 | 56498000.24 | 0 | 0 | 20040 |  | NotPrmUser |  | NotPrmUser
1457 | 78846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124 | 0 | 0 | 124 | 0 | 1080 | 1080 | 1080 | 7890 |  |  | 2023-09-07 17:00:00 | 2023-05-01 07:00:00 | 2023-09-07 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1457 | 78811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 0 | 0 | 62 | 0 | 300 | 300 | 300 | 8670 |  |  | 2023-06-04 17:00:00 | 2023-05-01 07:00:00 | 2023-06-04 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1457 | 78810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 9090 | 9090 | 9090 | 0 |  |  | 2026-04-30 17:00:00 | 2023-05-01 07:00:00 | 2026-04-30 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1457 | 78809 | 0 | 0 | 754180 | 56498000.24 | 754180 | 0 | 0 | 0 | 0 | 986 | 2 | 0 | 984 | 0 | 9090 | 9090 | 9090 | 0 |  |  | 2026-04-30 17:00:00 | 2023-05-01 07:00:00 | 2026-04-30 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56498000.24 | 0 | 0 | 20040 | 754180 | 754180 | 0 | 56498000.24 | 0 | 0 | 20040 |  | NotPrmUser |  | NotPrmUser
1458 | 79080 | 0 | 0 | 225610 | 14303603.61 | 225610 | 0 | 0 | 0 | 0 | 839 | 1 | 0 | 838 | 0 | 3860 | 3860 | 3860 | 0 |  |  | 2024-10-15 17:00:00 | 2023-07-11 07:00:00 | 2024-10-15 17:00:00 | 2023-07-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14303603.61 | 0 | 0 | 4250 | 225610 | 225610 | 0 | 14303603.61 | 0 | 0 | 4250 |  | NotPrmUser |  | NotPrmUser
1458 | 79079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1458 | 79078 | 0 | 0 | 225610 | 14303603.61 | 225610 | 0 | 0 | 0 | 0 | 839 | 1 | 0 | 838 | 0 | 3860 | 3860 | 3860 | 0 |  |  | 2024-10-15 17:00:00 | 2023-07-11 07:00:00 | 2024-10-15 17:00:00 | 2023-07-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14303603.61 | 0 | 0 | 4250 | 225610 | 225610 | 0 | 14303603.61 | 0 | 0 | 4250 |  | NotPrmUser |  | NotPrmUser
1460 | 79287 | 0 | 0 | 1110 | 0 | 1110 | 0 | 0 | 0 | 0 | 296 | 0 | 0 | 296 | 0 | 3114 | 3114 | 3114 | -2 |  |  | 2024-08-29 14:00:00 | 2023-05-11 10:00:00 | 2024-08-29 14:00:00 | 2023-05-11 10:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1480 | 1110 | 1110 | 0 | 0 | 0 | 0 | 1480 |  | NotPrmUser |  | NotPrmUser
1460 | 79286 | 167835206.0756 | 179988861.5538 | 3136330.4549 | 251600627.9244 | 1651398.4963 | 1484931.9586 | 1651674.7165 | 169 | 175 | 701 | 337 | 7 | 701 | 2936 | 6714 | 6714 | 3778 | -2 |  | 2021-10-10 08:00:00 | 2024-08-05 14:00:00 | 2021-10-10 08:00:00 | 2024-08-05 14:00:00 | 2022-12-31 08:00:00 | 0 | 1484931.9586 | 0 | 0 | 167835206.0756 | 0 | 0 | 167835206.0756 | 0 | 0 | 1484931.9586 | 0 | 0 | 419435834 | 0 | 8 | 3136330.4549 | 1651398.4963 | 0 | 0 | 251600627.9244 | 0 | 8 |  | NotPrmUser |  | NotPrmUser
1460 | 79285 | 90508890.2 | 94932785.1556 | 0 | 4763625.8 | 0 | 0 | 0 | 6 | 75 | 0 | 78 | 3 | 0 | 2688 | 2706 | 2720 | 18 | 3368 |  | 2021-11-15 08:00:00 | 2023-01-03 16:00:00 | 2021-11-15 08:00:00 | 2023-01-02 10:00:00 | 2022-12-31 08:00:00 | 0 | 0 | 0 | 0 | 90508890.2 | 0 | 0 | 90508890.2 | 0 | 0 | 0 | 0 | 0 | 95272516 | 0 | 0 | 0 | 0 | 0 | 0 | 4763625.8 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1460 | 79284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0 | 750 | 0 | 0 | 480 | 480 | 480 | 0 |  | 2021-10-10 16:00:00 | 2021-08-01 08:00:00 | 2021-10-10 16:00:00 | 2021-08-01 08:00:00 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1460 | 79283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0 | 720 | 720 | 720 | 0 |  | 2021-11-14 16:00:00 | 2021-08-01 08:00:00 | 2021-11-14 16:00:00 | 2021-08-01 08:00:00 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1460 | 79282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 0 | 38 | 38 | 0 | 38 | 2224 | 7354 | 7354 | 416 | -2 |  | 2021-08-01 08:00:00 | 2024-08-29 14:00:00 | 2021-08-01 08:00:00 | 2024-08-29 14:00:00 | 2024-06-30 14:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1460 | 79281 | 258344096.2756 | 274921646.7094 | 3137440.4549 | 256364253.7244 | 1652508.4963 | 1484931.9586 | 1651674.7165 | 969 | 250 | 1035 | 1209 | 10 | 1035 | 3408 | 7354 | 7354 | 3946 | -2 |  | 2021-08-01 08:00:00 | 2024-08-29 14:00:00 | 2021-08-01 08:00:00 | 2024-08-29 14:00:00 | 2022-12-31 08:00:00 | 0 | 1484931.9586 | 0 | 0 | 258344096.2756 | 0 | 0 | 258344096.2756 | 0 | 0 | 1484931.9586 | 0 | 0 | 514708350 | 0 | 1488 | 3137440.4549 | 1652508.4963 | 0 | 0 | 256364253.7244 | 0 | 1488 |  | NotPrmUser |  | NotPrmUser
1461 | 80837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 262 | 0 | 0 | 262 | 0 | 1079 | 1079 | 1079 | -1 |  |  | 2021-12-16 17:00:00 | 2021-08-14 08:00:00 | 2021-12-16 17:00:00 | 2021-08-14 08:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1461 | 80836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 | 0 | 6 | 0 | 1079 | 1079 | 1079 | -1 |  |  | 2021-12-16 17:00:00 | 2021-08-14 08:00:00 | 2021-12-16 17:00:00 | 2021-08-14 08:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1461 | 80835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 269 | 1 | 0 | 268 | 0 | 1079 | 1079 | 1079 | -1 |  |  | 2021-12-16 17:00:00 | 2021-08-14 08:00:00 | 2021-12-16 17:00:00 | 2021-08-14 08:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1462 | 80987 | 0 | 0 | 225610 | 14303603.61 | 225610 | 0 | 0 | 0 | 0 | 839 | 1 | 0 | 838 | 0 | 3860 | 3860 | 3860 | 0 |  |  | 2024-10-15 17:00:00 | 2023-07-11 07:00:00 | 2024-10-15 17:00:00 | 2023-07-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14303603.61 | 0 | 0 | 4250 | 225610 | 225610 | 0 | 14303603.61 | 0 | 0 | 4250 |  | NotPrmUser |  | NotPrmUser
1462 | 80986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1462 | 80985 | 0 | 0 | 225610 | 14303603.61 | 225610 | 0 | 0 | 0 | 0 | 839 | 1 | 0 | 838 | 0 | 3860 | 3860 | 3860 | 0 |  |  | 2024-10-15 17:00:00 | 2023-07-11 07:00:00 | 2024-10-15 17:00:00 | 2023-07-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14303603.61 | 0 | 0 | 4250 | 225610 | 225610 | 0 | 14303603.61 | 0 | 0 | 4250 |  | NotPrmUser |  | NotPrmUser
1463 | 82593 | 0 | 0 | 1250940 | 129353453.42 | 1250940 | 0 | 0 | 0 | 0 | 839 | 0 | 0 | 839 | 0 | 5190 | 5190 | 5190 | 0 |  |  | 2026-05-25 17:00:00 | 2024-09-08 07:00:00 | 2026-05-25 17:00:00 | 2024-09-08 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129353453.42 | 0 | 0 | 4920 | 1250940 | 1250940 | 0 | 129353453.42 | 0 | 0 | 4920 |  | NotPrmUser |  | NotPrmUser
1463 | 82592 | 0 | 0 | 911710 | 91910143.1 | 911710 | 0 | 0 | 0 | 0 | 839 | 0 | 0 | 839 | 0 | 4550 | 4550 | 4550 | 1680 |  |  | 2025-11-04 17:00:00 | 2024-05-05 07:00:00 | 2025-11-04 17:00:00 | 2024-05-05 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91910143.1 | 0 | 0 | 4920 | 911710 | 911710 | 0 | 91910143.1 | 0 | 0 | 4920 |  | NotPrmUser |  | NotPrmUser
1463 | 82591 | 0 | 0 | 820940 | 79409029.3203 | 820940 | 0 | 0 | 0 | 0 | 1678 | 0 | 0 | 1678 | 0 | 5200 | 5200 | 5200 | 1730 |  |  | 2025-10-29 17:00:00 | 2024-02-07 07:00:00 | 2025-10-29 17:00:00 | 2024-02-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79409029.3203 | 0 | 0 | 9840 | 820940 | 820940 | 0 | 79409029.3203 | 0 | 0 | 9840 |  | NotPrmUser |  | NotPrmUser
1463 | 82590 | 0 | 0 | 760120 | 76876265.32 | 760120 | 0 | 0 | 0 | 0 | 839 | 0 | 0 | 839 | 0 | 4440 | 4440 | 4440 | 2490 |  |  | 2025-07-31 17:00:00 | 2024-02-07 07:00:00 | 2025-07-31 17:00:00 | 2024-02-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76876265.32 | 0 | 0 | 4920 | 760120 | 760120 | 0 | 76876265.32 | 0 | 0 | 4920 |  | NotPrmUser |  | NotPrmUser
1463 | 82589 | 0 | 0 | 555000 | 77850670.5804 | 555000 | 0 | 0 | 0 | 0 | 1678 | 1 | 0 | 1677 | 0 | 5730 | 5730 | 5730 | 3000 |  |  | 2025-05-28 17:00:00 | 2023-07-11 07:00:00 | 2025-05-28 17:00:00 | 2023-07-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77850670.5804 | 0 | 0 | 10170 | 555000 | 555000 | 0 | 77850670.5804 | 0 | 0 | 10170 |  | NotPrmUser |  | NotPrmUser
1463 | 81188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 2 | 0 | 10 | 0 | 8730 | 8730 | 8730 | 0 |  |  | 2026-05-25 17:00:00 | 2023-07-11 07:00:00 | 2026-05-25 17:00:00 | 2023-07-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1463 | 81187 | 0 | 0 | 4298710 | 455399561.7407 | 4298710 | 0 | 0 | 0 | 0 | 5885 | 3 | 0 | 5882 | 0 | 8730 | 8730 | 8730 | 0 |  |  | 2026-05-25 17:00:00 | 2023-07-11 07:00:00 | 2026-05-25 17:00:00 | 2023-07-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 455399561.7407 | 0 | 0 | 34770 | 4298710 | 4298710 | 0 | 455399561.7407 | 0 | 0 | 34770 |  | NotPrmUser |  | NotPrmUser
1464 | 83800 | 0 | 0 | 1250940 | 129353453.42 | 1250940 | 0 | 0 | 0 | 0 | 839 | 0 | 0 | 839 | 0 | 7200 | 7200 | 7200 | 0 |  |  | 2026-07-10 17:00:00 | 2024-02-17 07:00:00 | 2026-07-10 17:00:00 | 2024-02-17 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129353453.42 | 0 | 0 | 4920 | 1250940 | 1250940 | 0 | 129353453.42 | 0 | 0 | 4920 |  | NotPrmUser |  | NotPrmUser
1464 | 83599 | 0 | 0 | 911710 | 91910143.1 | 911710 | 0 | 0 | 0 | 0 | 839 | 0 | 0 | 839 | 0 | 6380 | 6380 | 6380 | 230 |  |  | 2026-06-14 17:00:00 | 2024-05-01 07:00:00 | 2026-06-14 17:00:00 | 2024-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91910143.1 | 0 | 0 | 4920 | 911710 | 911710 | 0 | 91910143.1 | 0 | 0 | 4920 |  | NotPrmUser |  | NotPrmUser
1464 | 83198 | 0 | 0 | 820940 | 79409029.3203 | 820940 | 0 | 0 | 0 | 0 | 1678 | 0 | 0 | 1678 | 0 | 6610 | 6610 | 6610 | 720 |  |  | 2026-04-12 17:00:00 | 2024-02-01 07:00:00 | 2026-04-12 17:00:00 | 2024-02-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79409029.3203 | 0 | 0 | 9840 | 820940 | 820940 | 0 | 79409029.3203 | 0 | 0 | 9840 |  | NotPrmUser |  | NotPrmUser
1464 | 82997 | 0 | 0 | 760120 | 76876265.32 | 760120 | 0 | 0 | 0 | 0 | 839 | 0 | 0 | 839 | 0 | 6070 | 6070 | 6070 | 1260 |  |  | 2026-02-02 17:00:00 | 2024-02-01 07:00:00 | 2026-02-02 17:00:00 | 2024-02-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76876265.32 | 0 | 0 | 4920 | 760120 | 760120 | 0 | 76876265.32 | 0 | 0 | 4920 |  | NotPrmUser |  | NotPrmUser
1464 | 82596 | 0 | 0 | 871300 | 77850670.5804 | 871300 | 0 | 0 | 0 | 0 | 1678 | 1 | 0 | 1677 | 0 | 6410 | 6410 | 6410 | 2670 |  |  | 2025-08-20 17:00:00 | 2023-07-11 07:00:00 | 2025-08-20 17:00:00 | 2023-07-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77850670.5804 | 0 | 0 | 9600 | 871300 | 871300 | 0 | 77850670.5804 | 0 | 0 | 9600 |  | NotPrmUser |  | NotPrmUser
1464 | 82595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 2 | 0 | 10 | 0 | 9080 | 9080 | 9080 | 0 |  |  | 2026-07-10 17:00:00 | 2023-07-11 07:00:00 | 2026-07-10 17:00:00 | 2023-07-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1464 | 82594 | 0 | 0 | 4615010 | 455399561.7407 | 4615010 | 0 | 0 | 0 | 0 | 5885 | 3 | 0 | 5882 | 0 | 9080 | 9080 | 9080 | 0 |  |  | 2026-07-10 17:00:00 | 2023-07-11 07:00:00 | 2026-07-10 17:00:00 | 2023-07-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 455399561.7407 | 0 | 0 | 34200 | 4615010 | 4615010 | 0 | 455399561.7407 | 0 | 0 | 34200 |  | NotPrmUser |  | NotPrmUser
1466 | 84005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 0 | 0 | 51 | 0 | 2300 | 2300 | 2300 | 0 |  |  | 2024-11-17 17:00:00 | 2024-04-02 07:00:00 | 2024-11-17 17:00:00 | 2024-04-02 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1466 | 84004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 196 | 196 | 196 | 284 |  |  | 2024-04-21 13:00:00 | 2024-04-02 07:00:00 | 2024-04-21 13:00:00 | 2024-04-02 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1466 | 84003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 300 | 300 | 300 | 284 |  |  | 2024-04-02 07:00:00 | 2024-03-03 07:00:00 | 2024-04-02 07:00:00 | 2024-03-03 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1466 | 84002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 0 | 0 | 59 | 0 | 2600 | 2600 | 2600 | 0 |  |  | 2024-11-17 17:00:00 | 2024-03-03 07:00:00 | 2024-11-17 17:00:00 | 2024-03-03 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1468 | 84056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 0 | 55 | 0 | 2300 | 2300 | 2300 | 0 |  |  | 2024-10-18 17:00:00 | 2024-03-03 07:00:00 | 2024-10-18 17:00:00 | 2024-03-03 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1468 | 84055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 2300 | 2300 | 2300 | 0 |  |  | 2024-10-18 17:00:00 | 2024-03-03 07:00:00 | 2024-10-18 17:00:00 | 2024-03-03 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1468 | 84054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 0 | 0 | 57 | 0 | 2300 | 2300 | 2300 | 0 |  |  | 2024-10-18 17:00:00 | 2024-03-03 07:00:00 | 2024-10-18 17:00:00 | 2024-03-03 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1469 | 84080 | 200 | 300 | 0 | 1000 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 30 | 110 | 100 | 80 | 0 |  | 2024-06-01 07:00:00 | 2024-06-11 17:00:00 | 2024-06-01 07:00:00 | 2024-06-12 17:00:00 | 2024-06-04 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
1471 | 84082 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 100 | 100 | 100 | 0 |  |  | 2024-06-11 17:00:00 | 2024-06-01 07:00:00 | 2024-06-11 17:00:00 | 2024-06-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser

## Result 1
WBS_ID | PROJ_ID | COMPLETE_CNT | ACTIVE_CNT | NOTSTARTED_CNT | BASE_COMPLETE_CNT | BASE_ACTIVE_CNT | BASE_NOTSTARTED_CNT | ACT_DRTN_HR_CNT | ACT_EQUIP_QTY | ACT_WORK_QTY | TOTAL_DRTN_HR_CNT | BASE_DRTN_HR_CNT | BASE_WORK_QTY | BASE_EQUIP_QTY | ETC_WORK_QTY | REMAIN_DRTN_HR_CNT | REMAIN_WORK_QTY | REMAIN_EQUIP_QTY | TOTAL_FLOAT_HR_CNT | ACT_EXPENSE_COST | ACT_WORK_COST | ACT_EQUIP_COST | BASE_EXPENSE_COST | BASE_WORK_COST | BASE_EQUIP_COST | BCWP | ETC | BCWS | REMAIN_EXPENSE_COST | REMAIN_WORK_COST | REMAIN_EQUIP_COST | PERFM_WORK_QTY | SCHED_WORK_QTY | ACT_END_DATE | ACT_START_DATE | BASE_END_DATE | BASE_START_DATE | REEND_DATE | RESTART_DATE | ACT_THIS_PER_WORK_COST | ACT_THIS_PER_WORK_QTY | ACT_THIS_PER_EQUIP_COST | ACT_THIS_PER_EQUIP_QTY | BASE_MAT_COST | REMAIN_MAT_COST | ACT_MAT_COST | ACT_THIS_PER_MAT_COST | EAC_WORK_QTY | CREATE_DATE | CREATE_USER | UPDATE_DATE | UPDATE_USER | DELETE_SESSION_ID | DELETE_DATE
3684 | 368 | 0 | 0 | 353 | 0 | 0 | 353 | 0 | 0 | 0 | 5630 | 5630 | 0 | 0 | 0 | 5630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2024-12-31 17:00:00 | 2023-03-16 07:00:00 | 2024-12-31 17:00:00 | 2023-03-16 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
3683 | 368 | 0 | 0 | 353 | 0 | 0 | 353 | 0 | 0 | 0 | 5630 | 5630 | 0 | 0 | 0 | 5630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2024-12-31 17:00:00 | 2023-03-16 07:00:00 | 2024-12-31 17:00:00 | 2023-03-16 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
3682 | 368 | 0 | 0 | 353 | 0 | 0 | 353 | 0 | 0 | 0 | 5630 | 5630 | 0 | 0 | 0 | 5630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2024-12-31 17:00:00 | 2023-03-16 07:00:00 | 2024-12-31 17:00:00 | 2023-03-16 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
3681 | 368 | 0 | 0 | 353 | 0 | 0 | 353 | 0 | 0 | 0 | 5630 | 5630 | 0 | 0 | 0 | 5630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2024-12-31 17:00:00 | 2023-03-16 07:00:00 | 2024-12-31 17:00:00 | 2023-03-16 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
3680 | 368 | 0 | 0 | 1412 | 0 | 0 | 1412 | 0 | 0 | 0 | 5630 | 5630 | 0 | 0 | 0 | 5630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2024-12-31 17:00:00 | 2023-03-16 07:00:00 | 2024-12-31 17:00:00 | 2023-03-16 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
4033 | 418 | 0 | 0 | 352 | 0 | 0 | 352 | 0 | 0 | 0 | 5080 | 5080 | 0 | 0 | 0 | 5080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2024-06-30 11:00:00 | 2022-11-15 11:00:00 | 2024-06-30 11:00:00 | 2022-11-15 11:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
4032 | 418 | 0 | 0 | 352 | 0 | 0 | 352 | 0 | 0 | 0 | 5770 | 5770 | 0 | 0 | 0 | 5770 | 0 | 0 | 2610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-08-30 11:00:00 | 2021-10-17 11:00:00 | 2023-08-30 11:00:00 | 2021-10-17 11:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
4031 | 418 | 0 | 0 | 206 | 0 | 0 | 206 | 0 | 0 | 0 | 5880 | 5880 | 0 | 0 | 0 | 5880 | 0 | 0 | 3650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-05-01 11:00:00 | 2021-06-01 07:00:00 | 2023-05-01 11:00:00 | 2021-06-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
4030 | 418 | 0 | 0 | 910 | 0 | 0 | 910 | 0 | 0 | 0 | 9530 | 9530 | 0 | 0 | 0 | 9530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2024-06-30 11:00:00 | 2021-06-01 07:00:00 | 2024-06-30 11:00:00 | 2021-06-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
4585 | 518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
4584 | 518 | 0 | 0 | 511 | 0 | 0 | 511 | 0 | 0 | 0 | 3980 | 3980 | 0 | 0 | 0 | 3980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2022-04-16 17:00:00 | 2021-01-07 07:00:00 | 2022-04-16 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
4583 | 518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
4582 | 518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
4581 | 518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
4580 | 518 | 0 | 0 | 511 | 0 | 0 | 511 | 0 | 0 | 0 | 3980 | 3980 | 0 | 0 | 0 | 3980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2022-04-16 17:00:00 | 2021-01-07 07:00:00 | 2022-04-16 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
4984 | 520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
4855 | 520 | 0 | 0 | 511 | 0 | 0 | 511 | 0 | 0 | 0 | 3980 | 3980 | 0 | 0 | 0 | 3980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2022-04-16 17:00:00 | 2021-01-07 07:00:00 | 2022-04-16 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
4854 | 520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
4853 | 520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
4852 | 520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
4851 | 520 | 0 | 0 | 511 | 0 | 0 | 511 | 0 | 0 | 0 | 3980 | 3980 | 0 | 0 | 0 | 3980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2022-04-16 17:00:00 | 2021-01-07 07:00:00 | 2022-04-16 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
5118 | 521 | 0 | 0 | 34 | 0 | 0 | 34 | 0 | 0 | 0 | 320 | 340 | 0 | 0 | 0 | 320 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2022-12-07 17:00:00 | 2022-10-30 07:00:00 | 2022-12-05 17:00:00 | 2022-10-30 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
4989 | 521 | 0 | 0 | 511 | 0 | 0 | 511 | 0 | 0 | 0 | 6040 | 6040 | 0 | 0 | 0 | 6040 | 0 | 0 | 0 | 0 | 0 | 0 | 12464852 | 0 | 0 | 0 | 12464852 | 0 | 12464852 | 0 | 0 | 0 | 0 |  |  | 2022-12-12 17:00:00 | 2021-01-07 07:00:00 | 2022-12-12 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
4988 | 521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
4987 | 521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
4986 | 521 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 6040 | 6040 | 0 | 0 | 0 | 6040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2022-12-12 17:00:00 | 2021-01-07 07:00:00 | 2022-12-12 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
4985 | 521 | 0 | 0 | 547 | 1 | 0 | 546 | 0 | 0 | 0 | 6040 | 6040 | 0 | 0 | 0 | 6040 | 0 | 0 | 0 | 0 | 0 | 0 | 12464852 | 0 | 0 | 0 | 12464852 | 0 | 12464852 | 0 | 0 | 0 | 0 |  |  | 2022-12-12 17:00:00 | 2021-01-07 07:00:00 | 2022-12-12 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
5271 | 522 | 0 | 0 | 34 | 0 | 0 | 34 | 0 | 0 | 0 | 320 | 340 | 0 | 0 | 0 | 320 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2022-12-07 17:00:00 | 2022-10-30 07:00:00 | 2022-12-05 17:00:00 | 2022-10-30 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
5142 | 522 | 0 | 0 | 511 | 0 | 0 | 511 | 0 | 0 | 0 | 6040 | 6040 | 0 | 0 | 0 | 6040 | 0 | 0 | 0 | 0 | 0 | 0 | 12464852 | 0 | 0 | 0 | 12464852 | 0 | 12464852 | 0 | 0 | 0 | 0 |  |  | 2022-12-12 17:00:00 | 2021-01-07 07:00:00 | 2022-12-12 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
5141 | 522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
5140 | 522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
5139 | 522 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 6040 | 6040 | 0 | 0 | 0 | 6040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2022-12-12 17:00:00 | 2021-01-07 07:00:00 | 2022-12-12 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
5138 | 522 | 0 | 0 | 547 | 1 | 0 | 546 | 0 | 0 | 0 | 6040 | 6040 | 0 | 0 | 0 | 6040 | 0 | 0 | 0 | 0 | 0 | 0 | 12464852 | 0 | 0 | 0 | 12464852 | 0 | 12464852 | 0 | 0 | 0 | 0 |  |  | 2022-12-12 17:00:00 | 2021-01-07 07:00:00 | 2022-12-12 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
5424 | 523 | 0 | 0 | 30 | 0 | 0 | 30 | 0 | 0 | 0 | 480 | 480 | 0 | 0 | 0 | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2022-11-14 17:00:00 | 2022-09-20 07:00:00 | 2022-11-14 17:00:00 | 2022-09-20 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
5295 | 523 | 0 | 0 | 511 | 0 | 0 | 511 | 0 | 0 | 0 | 5700 | 5700 | 0 | 0 | 0 | 5700 | 0 | 0 | 100 | 0 | 0 | 0 | 12464852 | 0 | 0 | 0 | 12464852 | 0 | 12464852 | 0 | 0 | 0 | 0 |  |  | 2022-11-02 17:00:00 | 2021-01-07 07:00:00 | 2022-11-02 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
5294 | 523 | 0 | 0 | 9 | 0 | 0 | 9 | 0 | 0 | 0 | 4020 | 4020 | 0 | 0 | 0 | 4020 | 0 | 0 | 780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2022-08-01 17:00:00 | 2021-04-20 07:00:00 | 2022-08-01 17:00:00 | 2021-04-20 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
5293 | 523 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 1140 | 1140 | 0 | 0 | 0 | 1140 | 0 | 0 | 4280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2021-05-19 17:00:00 | 2021-01-07 07:00:00 | 2021-05-19 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
5292 | 523 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 5800 | 5800 | 0 | 0 | 0 | 5800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2022-11-14 17:00:00 | 2021-01-07 07:00:00 | 2022-11-14 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
5291 | 523 | 0 | 0 | 556 | 1 | 0 | 555 | 0 | 0 | 0 | 5800 | 5800 | 0 | 0 | 0 | 5800 | 0 | 0 | 0 | 0 | 0 | 0 | 12464852 | 0 | 0 | 0 | 12464852 | 0 | 12464852 | 0 | 0 | 0 | 0 |  |  | 2022-11-14 17:00:00 | 2021-01-07 07:00:00 | 2022-11-14 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
5604 | 526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
6193 | 577 | 0 | 0 | 30 | 0 | 0 | 30 | 0 | 0 | 0 | 480 | 480 | 0 | 0 | 0 | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2022-11-14 17:00:00 | 2022-09-20 07:00:00 | 2022-11-14 17:00:00 | 2022-09-20 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
6064 | 577 | 0 | 0 | 511 | 0 | 0 | 511 | 0 | 0 | 0 | 5700 | 5700 | 233890 | 1680 | 233890 | 5700 | 233890 | 1680 | 100 | 0 | 0 | 0 | 12464852 | 0 | 0 | 0 | 12464852 | 0 | 12464852 | 0 | 0 | 0 | 0 |  |  | 2022-11-02 17:00:00 | 2021-01-07 07:00:00 | 2022-11-02 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 233890 |  | NotPrmUser |  | NotPrmUser
6059 | 577 | 0 | 0 | 9 | 0 | 0 | 9 | 0 | 0 | 0 | 4020 | 4020 | 0 | 0 | 0 | 4020 | 0 | 0 | 780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2022-08-01 17:00:00 | 2021-04-20 07:00:00 | 2022-08-01 17:00:00 | 2021-04-20 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
6057 | 577 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 1140 | 1140 | 0 | 0 | 0 | 1140 | 0 | 0 | 4280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2021-05-19 17:00:00 | 2021-01-07 07:00:00 | 2021-05-19 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
6056 | 577 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 5800 | 5800 | 0 | 0 | 0 | 5800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2022-11-14 17:00:00 | 2021-01-07 07:00:00 | 2022-11-14 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
6055 | 577 | 0 | 0 | 556 | 1 | 0 | 555 | 0 | 0 | 0 | 5800 | 5800 | 233890 | 1680 | 233890 | 5800 | 233890 | 1680 | 0 | 0 | 0 | 0 | 12464852 | 0 | 0 | 0 | 12464852 | 0 | 12464852 | 0 | 0 | 0 | 0 |  |  | 2022-11-14 17:00:00 | 2021-01-07 07:00:00 | 2022-11-14 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 233890 |  | NotPrmUser |  | NotPrmUser
6664 | 580 | 0 | 0 | 30 | 0 | 0 | 30 | 0 | 0 | 0 | 480 | 480 | 3600 | 0 | 3600 | 480 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 |  | NotPrmUser |  | NotPrmUser
6535 | 580 | 0 | 0 | 511 | 0 | 0 | 511 | 0 | 0 | 0 | 5240 | 5240 | 159830 | 1680 | 159830 | 5240 | 159830 | 1680 | 0 | 0 | 0 | 0 | 12464852 | 0 | 0 | 0 | 12464852 | 0 | 12464852 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159830 |  | NotPrmUser |  | NotPrmUser
6530 | 580 | 0 | 0 | 56 | 0 | 0 | 56 | 0 | 0 | 0 | 1200 | 1200 | 0 | 0 | 0 | 1200 | 0 | 0 | 3740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
6528 | 580 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 820 | 820 | 0 | 0 | 0 | 820 | 0 | 0 | 3560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
6527 | 580 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 5240 | 5240 | 0 | 0 | 0 | 5240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
6526 | 580 | 0 | 0 | 607 | 1 | 0 | 606 | 0 | 0 | 0 | 5240 | 5240 | 163430 | 1680 | 163430 | 5240 | 163430 | 1680 | 0 | 0 | 0 | 0 | 12464852 | 0 | 0 | 0 | 12464852 | 0 | 12464852 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163430 |  | NotPrmUser |  | NotPrmUser
6729 | 581 | 0 | 0 | 14 | 0 | 0 | 14 | 0 | 0 | 0 | 1024 | 1024 | 0 | 0 | 0 | 1024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2021-11-30 17:00:00 | 2021-07-05 08:00:00 | 2021-11-30 17:00:00 | 2021-07-05 08:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
6728 | 581 | 0 | 0 | 417 | 0 | 0 | 417 | 0 | 0 | 0 | 1520 | 1520 | 46720 | 944 | 46720 | 1520 | 46720 | 944 | 512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16010720.97 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2021-09-16 16:00:00 | 2021-02-08 08:00:00 | 2021-09-16 16:00:00 | 2021-02-08 08:00:00 | 0 | 0 | 0 | 0 | 16010720.97 | 16010720.97 | 0 | 0 | 46720 |  | NotPrmUser |  | NotPrmUser
6727 | 581 | 0 | 0 | 5 | 0 | 0 | 5 | 0 | 0 | 0 | 2288 | 2288 | 20592 | 0 | 20592 | 2288 | 20592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2021-11-30 17:00:00 | 2021-01-02 08:00:00 | 2021-11-30 17:00:00 | 2021-01-02 08:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20592 |  | NotPrmUser |  | NotPrmUser
6726 | 581 | 0 | 0 | 52 | 0 | 0 | 52 | 0 | 0 | 0 | 1312 | 1312 | 0 | 0 | 0 | 1312 | 0 | 0 | 872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2021-07-15 16:00:00 | 2021-01-06 08:00:00 | 2021-07-15 16:00:00 | 2021-01-06 08:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
6725 | 581 | 0 | 0 | 36 | 0 | 0 | 36 | 0 | 0 | 0 | 1056 | 1056 | 0 | 0 | 0 | 1056 | 0 | 0 | 312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2021-06-03 16:00:00 | 2021-01-02 08:00:00 | 2021-06-03 16:00:00 | 2021-01-02 08:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
6724 | 581 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 2288 | 2288 | 0 | 0 | 0 | 2288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2021-11-30 17:00:00 | 2021-01-02 08:00:00 | 2021-11-30 17:00:00 | 2021-01-02 08:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
6723 | 581 | 0 | 0 | 532 | 0 | 0 | 532 | 0 | 0 | 0 | 2288 | 2288 | 67312 | 944 | 67312 | 2288 | 67312 | 944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16010720.97 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2021-11-30 17:00:00 | 2021-01-02 08:00:00 | 2021-11-30 17:00:00 | 2021-01-02 08:00:00 | 0 | 0 | 0 | 0 | 16010720.97 | 16010720.97 | 0 | 0 | 67312 |  | NotPrmUser |  | NotPrmUser
7181 | 631 | 0 | 0 | 30 | 0 | 0 | 30 | 0 | 0 | 0 | 480 | 480 | 3600 | 0 | 3600 | 480 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 |  | NotPrmUser |  | NotPrmUser
7052 | 631 | 0 | 0 | 511 | 0 | 0 | 511 | 0 | 0 | 0 | 5240 | 5240 | 159830 | 1680 | 159830 | 5240 | 159830 | 1680 | 0 | 0 | 0 | 0 | 9726772.6 | 0 | 0 | 0 | 9726772.6 | 0 | 9726772.6 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159830 |  | NotPrmUser |  | NotPrmUser
7030 | 631 | 0 | 0 | 56 | 0 | 0 | 56 | 0 | 0 | 0 | 1200 | 1200 | 0 | 0 | 0 | 1200 | 0 | 0 | 3740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
7025 | 631 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 820 | 820 | 0 | 0 | 0 | 820 | 0 | 0 | 3560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
7024 | 631 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 5240 | 5240 | 0 | 0 | 0 | 5240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
7023 | 631 | 0 | 0 | 607 | 1 | 0 | 606 | 0 | 0 | 0 | 5240 | 5240 | 163430 | 1680 | 163430 | 5240 | 163430 | 1680 | 0 | 0 | 0 | 0 | 9726772.6 | 0 | 0 | 0 | 9726772.6 | 0 | 9726772.6 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163430 |  | NotPrmUser |  | NotPrmUser
7359 | 633 | 0 | 0 | 30 | 0 | 0 | 30 | 0 | 0 | 0 | 480 | 480 | 3600 | 0 | 3600 | 480 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 |  | NotPrmUser |  | NotPrmUser
7230 | 633 | 0 | 0 | 511 | 0 | 0 | 511 | 0 | 0 | 0 | 5240 | 5240 | 159830 | 1680 | 159830 | 5240 | 159830 | 1680 | 0 | 0 | 0 | 0 | 11361935 | 0 | 0 | 0 | 11361935 | 0 | 11361935 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159830 |  | NotPrmUser |  | NotPrmUser
7208 | 633 | 0 | 0 | 56 | 0 | 0 | 56 | 0 | 0 | 0 | 1200 | 1200 | 0 | 0 | 0 | 1200 | 0 | 0 | 3740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
7203 | 633 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 820 | 820 | 0 | 0 | 0 | 820 | 0 | 0 | 3560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
7202 | 633 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 5240 | 5240 | 0 | 0 | 0 | 5240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
7201 | 633 | 0 | 0 | 607 | 1 | 0 | 606 | 0 | 0 | 0 | 5240 | 5240 | 163430 | 1680 | 163430 | 5240 | 163430 | 1680 | 0 | 0 | 0 | 0 | 11361935 | 0 | 0 | 0 | 11361935 | 0 | 11361935 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163430 |  | NotPrmUser |  | NotPrmUser
7536 | 634 | 0 | 0 | 14 | 0 | 0 | 14 | 0 | 0 | 0 | 520 | 520 | 1680 | 0 | 1680 | 520 | 1680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2022-01-05 17:00:00 | 2021-11-07 07:00:00 | 2022-01-05 17:00:00 | 2021-11-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1680 |  | NotPrmUser |  | NotPrmUser
7407 | 634 | 0 | 0 | 283 | 0 | 0 | 283 | 0 | 0 | 0 | 3100 | 3100 | 85270 | 1600 | 85270 | 3100 | 85270 | 1600 | 20 | 0 | 0 | 0 | 5250032 | 0 | 0 | 0 | 5250032 | 0 | 5250032 | 0 | 0 | 0 | 0 |  |  | 2022-01-03 17:00:00 | 2021-01-07 07:00:00 | 2022-01-03 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85270 |  | NotPrmUser |  | NotPrmUser
7385 | 634 | 0 | 0 | 56 | 0 | 0 | 56 | 0 | 0 | 0 | 1200 | 1200 | 0 | 0 | 0 | 1200 | 0 | 0 | 1620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
7380 | 634 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 820 | 820 | 0 | 0 | 0 | 820 | 0 | 0 | 1430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
7379 | 634 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 3120 | 3120 | 0 | 0 | 0 | 3120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2022-01-05 17:00:00 | 2021-01-07 07:00:00 | 2022-01-05 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
7378 | 634 | 0 | 0 | 363 | 1 | 0 | 362 | 0 | 0 | 0 | 3120 | 3120 | 86950 | 1600 | 86950 | 3120 | 86950 | 1600 | 0 | 0 | 0 | 0 | 5250032 | 0 | 0 | 0 | 5250032 | 0 | 5250032 | 0 | 0 | 0 | 0 |  |  | 2022-01-05 17:00:00 | 2021-01-07 07:00:00 | 2022-01-05 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86950 |  | NotPrmUser |  | NotPrmUser
7715 | 637 | 0 | 0 | 30 | 0 | 0 | 30 | 0 | 0 | 0 | 480 | 480 | 3600 | 0 | 3600 | 480 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 |  | NotPrmUser |  | NotPrmUser
7586 | 637 | 0 | 0 | 511 | 0 | 0 | 511 | 0 | 0 | 0 | 5240 | 5240 | 159830 | 1680 | 159830 | 5240 | 159830 | 1680 | 0 | 0 | 0 | 0 | 12464852 | 0 | 0 | 0 | 12464852 | 0 | 12464852 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159830 |  | NotPrmUser |  | NotPrmUser
7564 | 637 | 0 | 0 | 56 | 0 | 0 | 56 | 0 | 0 | 0 | 1200 | 1200 | 0 | 0 | 0 | 1200 | 0 | 0 | 3740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
7559 | 637 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 820 | 820 | 0 | 0 | 0 | 820 | 0 | 0 | 3560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
7558 | 637 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 5240 | 5240 | 0 | 0 | 0 | 5240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
7557 | 637 | 0 | 0 | 607 | 1 | 0 | 606 | 0 | 0 | 0 | 5240 | 5240 | 163430 | 1680 | 163430 | 5240 | 163430 | 1680 | 0 | 0 | 0 | 0 | 12464852 | 0 | 0 | 0 | 12464852 | 0 | 12464852 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163430 |  | NotPrmUser |  | NotPrmUser
7892 | 638 | 0 | 0 | 30 | 0 | 0 | 30 | 0 | 0 | 0 | 480 | 480 | 3600 | 0 | 3600 | 480 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 |  | NotPrmUser |  | NotPrmUser
7763 | 638 | 0 | 0 | 511 | 0 | 0 | 511 | 0 | 0 | 0 | 5240 | 5240 | 159830 | 1680 | 159830 | 5240 | 159830 | 1680 | 0 | 0 | 0 | 0 | 12464852 | 0 | 0 | 0 | 12464852 | 0 | 12464852 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159830 |  | NotPrmUser |  | NotPrmUser
7741 | 638 | 0 | 0 | 56 | 0 | 0 | 56 | 0 | 0 | 0 | 1200 | 1200 | 0 | 0 | 0 | 1200 | 0 | 0 | 3740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
7736 | 638 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 820 | 820 | 0 | 0 | 0 | 820 | 0 | 0 | 3560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
7735 | 638 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 5240 | 5240 | 0 | 0 | 0 | 5240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
7734 | 638 | 0 | 0 | 607 | 1 | 0 | 606 | 0 | 0 | 0 | 5240 | 5240 | 163430 | 1680 | 163430 | 5240 | 163430 | 1680 | 0 | 0 | 0 | 0 | 12464852 | 0 | 0 | 0 | 12464852 | 0 | 12464852 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163430 |  | NotPrmUser |  | NotPrmUser
8069 | 639 | 0 | 0 | 30 | 0 | 0 | 30 | 0 | 0 | 0 | 480 | 480 | 3600 | 0 | 3600 | 480 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 |  | NotPrmUser |  | NotPrmUser
7940 | 639 | 0 | 0 | 511 | 0 | 0 | 511 | 0 | 0 | 0 | 5240 | 5240 | 159830 | 1680 | 159830 | 5240 | 159830 | 1680 | 0 | 0 | 0 | 0 | 12464852 | 0 | 0 | 0 | 12464852 | 0 | 12464852 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159830 |  | NotPrmUser |  | NotPrmUser
7918 | 639 | 0 | 0 | 56 | 0 | 0 | 56 | 0 | 0 | 0 | 1200 | 1200 | 0 | 0 | 0 | 1200 | 0 | 0 | 3740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
7913 | 639 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 820 | 820 | 0 | 0 | 0 | 820 | 0 | 0 | 3560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
7912 | 639 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 5240 | 5240 | 0 | 0 | 0 | 5240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
7911 | 639 | 0 | 0 | 607 | 1 | 0 | 606 | 0 | 0 | 0 | 5240 | 5240 | 163430 | 1680 | 163430 | 5240 | 163430 | 1680 | 0 | 0 | 0 | 0 | 12464852 | 0 | 0 | 0 | 12464852 | 0 | 12464852 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163430 |  | NotPrmUser |  | NotPrmUser
8246 | 640 | 0 | 0 | 30 | 0 | 0 | 30 | 0 | 0 | 0 | 480 | 480 | 3600 | 0 | 3600 | 480 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 |  | NotPrmUser |  | NotPrmUser
8117 | 640 | 0 | 0 | 511 | 0 | 0 | 511 | 0 | 0 | 0 | 5240 | 5240 | 159830 | 1680 | 159830 | 5240 | 159830 | 1680 | 0 | 0 | 0 | 0 | 12464852 | 0 | 0 | 0 | 12464852 | 0 | 12464852 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159830 |  | NotPrmUser |  | NotPrmUser
8095 | 640 | 0 | 0 | 56 | 0 | 0 | 56 | 0 | 0 | 0 | 1200 | 1200 | 0 | 0 | 0 | 1200 | 0 | 0 | 3740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
8090 | 640 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 820 | 820 | 0 | 0 | 0 | 820 | 0 | 0 | 3560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
8089 | 640 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 5240 | 5240 | 0 | 0 | 0 | 5240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
8088 | 640 | 0 | 0 | 607 | 1 | 0 | 606 | 0 | 0 | 0 | 5240 | 5240 | 163430 | 1680 | 163430 | 5240 | 163430 | 1680 | 0 | 0 | 0 | 0 | 12464852 | 0 | 0 | 0 | 12464852 | 0 | 12464852 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163430 |  | NotPrmUser |  | NotPrmUser
8423 | 641 | 0 | 0 | 30 | 0 | 0 | 30 | 0 | 0 | 0 | 480 | 480 | 3600 | 0 | 3600 | 480 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 |  | NotPrmUser |  | NotPrmUser
8294 | 641 | 0 | 0 | 511 | 0 | 0 | 511 | 0 | 0 | 0 | 5240 | 5240 | 159830 | 1680 | 159830 | 5240 | 159830 | 1680 | 0 | 0 | 0 | 0 | 9726772.6 | 0 | 0 | 0 | 9726772.6 | 0 | 9726772.6 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159830 |  | NotPrmUser |  | NotPrmUser
8272 | 641 | 0 | 0 | 56 | 0 | 0 | 56 | 0 | 0 | 0 | 1200 | 1200 | 0 | 0 | 0 | 1200 | 0 | 0 | 3740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
8267 | 641 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 820 | 820 | 0 | 0 | 0 | 820 | 0 | 0 | 3560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
8266 | 641 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 5240 | 5240 | 0 | 0 | 0 | 5240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
8265 | 641 | 0 | 0 | 607 | 1 | 0 | 606 | 0 | 0 | 0 | 5240 | 5240 | 163430 | 1680 | 163430 | 5240 | 163430 | 1680 | 0 | 0 | 0 | 0 | 9726772.6 | 0 | 0 | 0 | 9726772.6 | 0 | 9726772.6 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163430 |  | NotPrmUser |  | NotPrmUser
8600 | 642 | 0 | 0 | 30 | 0 | 0 | 30 | 0 | 0 | 0 | 480 | 480 | 3600 | 0 | 3600 | 480 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 |  | NotPrmUser |  | NotPrmUser
8471 | 642 | 0 | 0 | 511 | 0 | 0 | 511 | 0 | 0 | 0 | 5240 | 5240 | 159830 | 1680 | 159830 | 5240 | 159830 | 1680 | 0 | 0 | 0 | 0 | 9726772.6 | 0 | 0 | 0 | 9726772.6 | 0 | 9726772.6 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159830 |  | NotPrmUser |  | NotPrmUser
8449 | 642 | 0 | 0 | 56 | 0 | 0 | 56 | 0 | 0 | 0 | 1200 | 1200 | 0 | 0 | 0 | 1200 | 0 | 0 | 3740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
8444 | 642 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 820 | 820 | 0 | 0 | 0 | 820 | 0 | 0 | 3560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
8443 | 642 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 5240 | 5240 | 0 | 0 | 0 | 5240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
8442 | 642 | 0 | 0 | 607 | 1 | 0 | 606 | 0 | 0 | 0 | 5240 | 5240 | 163430 | 1680 | 163430 | 5240 | 163430 | 1680 | 0 | 0 | 0 | 0 | 9726772.6 | 0 | 0 | 0 | 9726772.6 | 0 | 9726772.6 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163430 |  | NotPrmUser |  | NotPrmUser
8777 | 643 | 0 | 0 | 30 | 0 | 0 | 30 | 0 | 0 | 0 | 480 | 480 | 3600 | 0 | 3600 | 480 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 |  | NotPrmUser |  | NotPrmUser
8648 | 643 | 0 | 0 | 511 | 0 | 0 | 511 | 0 | 0 | 0 | 5240 | 5240 | 159830 | 1680 | 159830 | 5240 | 159830 | 1680 | 0 | 0 | 0 | 0 | 9726772.6 | 0 | 0 | 0 | 9726772.6 | 0 | 9726772.6 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159830 |  | NotPrmUser |  | NotPrmUser
8626 | 643 | 0 | 0 | 56 | 0 | 0 | 56 | 0 | 0 | 0 | 1200 | 1200 | 0 | 0 | 0 | 1200 | 0 | 0 | 3740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
8621 | 643 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 820 | 820 | 0 | 0 | 0 | 820 | 0 | 0 | 3560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
8620 | 643 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 5240 | 5240 | 0 | 0 | 0 | 5240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
8619 | 643 | 0 | 0 | 607 | 1 | 0 | 606 | 0 | 0 | 0 | 5240 | 5240 | 163430 | 1680 | 163430 | 5240 | 163430 | 1680 | 0 | 0 | 0 | 0 | 9726772.6 | 0 | 0 | 0 | 9726772.6 | 0 | 9726772.6 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163430 |  | NotPrmUser |  | NotPrmUser
8954 | 644 | 0 | 0 | 30 | 0 | 0 | 30 | 0 | 0 | 0 | 480 | 480 | 3600 | 0 | 3600 | 480 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 |  | NotPrmUser |  | NotPrmUser
8825 | 644 | 0 | 0 | 511 | 0 | 0 | 511 | 0 | 0 | 0 | 5240 | 5240 | 159830 | 1680 | 159830 | 5240 | 159830 | 1680 | 0 | 0 | 0 | 0 | 9726772.6 | 0 | 0 | 0 | 9726772.6 | 0 | 9726772.6 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159830 |  | NotPrmUser |  | NotPrmUser
8803 | 644 | 0 | 0 | 56 | 0 | 0 | 56 | 0 | 0 | 0 | 1200 | 1200 | 0 | 0 | 0 | 1200 | 0 | 0 | 3740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
8798 | 644 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 820 | 820 | 0 | 0 | 0 | 820 | 0 | 0 | 3560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
8797 | 644 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 5240 | 5240 | 0 | 0 | 0 | 5240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
8796 | 644 | 0 | 0 | 607 | 1 | 0 | 606 | 0 | 0 | 0 | 5240 | 5240 | 163430 | 1680 | 163430 | 5240 | 163430 | 1680 | 0 | 0 | 0 | 0 | 9726772.6 | 0 | 0 | 0 | 9726772.6 | 0 | 9726772.6 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163430 |  | NotPrmUser |  | NotPrmUser
9131 | 645 | 0 | 0 | 30 | 0 | 0 | 30 | 0 | 0 | 0 | 480 | 480 | 3600 | 0 | 3600 | 480 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 |  | NotPrmUser |  | NotPrmUser
9002 | 645 | 0 | 0 | 511 | 0 | 0 | 511 | 0 | 0 | 0 | 5240 | 5240 | 159830 | 1680 | 159830 | 5240 | 159830 | 1680 | 0 | 0 | 0 | 0 | 11361935 | 0 | 0 | 0 | 11361935 | 0 | 11361935 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159830 |  | NotPrmUser |  | NotPrmUser
8980 | 645 | 0 | 0 | 56 | 0 | 0 | 56 | 0 | 0 | 0 | 1200 | 1200 | 0 | 0 | 0 | 1200 | 0 | 0 | 3740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
8975 | 645 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 820 | 820 | 0 | 0 | 0 | 820 | 0 | 0 | 3560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
8974 | 645 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 5240 | 5240 | 0 | 0 | 0 | 5240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
8973 | 645 | 0 | 0 | 607 | 1 | 0 | 606 | 0 | 0 | 0 | 5240 | 5240 | 163430 | 1680 | 163430 | 5240 | 163430 | 1680 | 0 | 0 | 0 | 0 | 11361935 | 0 | 0 | 0 | 11361935 | 0 | 11361935 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163430 |  | NotPrmUser |  | NotPrmUser
9308 | 646 | 0 | 0 | 30 | 0 | 0 | 30 | 0 | 0 | 0 | 480 | 480 | 3600 | 0 | 3600 | 480 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 |  | NotPrmUser |  | NotPrmUser
9179 | 646 | 0 | 0 | 511 | 0 | 0 | 511 | 0 | 0 | 0 | 5240 | 5240 | 159830 | 1680 | 159830 | 5240 | 159830 | 1680 | 0 | 0 | 0 | 0 | 11361935 | 0 | 0 | 0 | 11361935 | 0 | 11361935 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159830 |  | NotPrmUser |  | NotPrmUser
9157 | 646 | 0 | 0 | 56 | 0 | 0 | 56 | 0 | 0 | 0 | 1200 | 1200 | 0 | 0 | 0 | 1200 | 0 | 0 | 3740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
9152 | 646 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 820 | 820 | 0 | 0 | 0 | 820 | 0 | 0 | 3560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
9151 | 646 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 5240 | 5240 | 0 | 0 | 0 | 5240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
9150 | 646 | 0 | 0 | 607 | 1 | 0 | 606 | 0 | 0 | 0 | 5240 | 5240 | 163430 | 1680 | 163430 | 5240 | 163430 | 1680 | 0 | 0 | 0 | 0 | 11361935 | 0 | 0 | 0 | 11361935 | 0 | 11361935 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163430 |  | NotPrmUser |  | NotPrmUser
9437 | 647 | 0 | 0 | 14 | 0 | 0 | 14 | 0 | 0 | 0 | 520 | 520 | 1680 | 0 | 1680 | 520 | 1680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2022-01-05 17:00:00 | 2021-11-07 07:00:00 | 2022-01-05 17:00:00 | 2021-11-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1680 |  | NotPrmUser |  | NotPrmUser
9356 | 647 | 0 | 0 | 283 | 0 | 0 | 283 | 0 | 0 | 0 | 3100 | 3100 | 85270 | 1600 | 85270 | 3100 | 85270 | 1600 | 20 | 0 | 0 | 0 | 5250032 | 0 | 0 | 0 | 5250032 | 0 | 5250032 | 0 | 0 | 0 | 0 |  |  | 2022-01-03 17:00:00 | 2021-01-07 07:00:00 | 2022-01-03 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85270 |  | NotPrmUser |  | NotPrmUser
9334 | 647 | 0 | 0 | 56 | 0 | 0 | 56 | 0 | 0 | 0 | 1200 | 1200 | 0 | 0 | 0 | 1200 | 0 | 0 | 1620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
9329 | 647 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 820 | 820 | 0 | 0 | 0 | 820 | 0 | 0 | 1430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
9328 | 647 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 3120 | 3120 | 0 | 0 | 0 | 3120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2022-01-05 17:00:00 | 2021-01-07 07:00:00 | 2022-01-05 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
9327 | 647 | 0 | 0 | 363 | 1 | 0 | 362 | 0 | 0 | 0 | 3120 | 3120 | 86950 | 1600 | 86950 | 3120 | 86950 | 1600 | 0 | 0 | 0 | 0 | 5250032 | 0 | 0 | 0 | 5250032 | 0 | 5250032 | 0 | 0 | 0 | 0 |  |  | 2022-01-05 17:00:00 | 2021-01-07 07:00:00 | 2022-01-05 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86950 |  | NotPrmUser |  | NotPrmUser
9558 | 648 | 0 | 0 | 14 | 0 | 0 | 14 | 0 | 0 | 0 | 520 | 520 | 1680 | 0 | 1680 | 520 | 1680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2022-01-05 17:00:00 | 2021-11-07 07:00:00 | 2022-01-05 17:00:00 | 2021-11-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1680 |  | NotPrmUser |  | NotPrmUser
9477 | 648 | 0 | 0 | 283 | 0 | 0 | 283 | 0 | 0 | 0 | 3100 | 3100 | 85270 | 1600 | 85270 | 3100 | 85270 | 1600 | 20 | 0 | 0 | 0 | 5250032 | 0 | 0 | 0 | 5250032 | 0 | 5250032 | 0 | 0 | 0 | 0 |  |  | 2022-01-03 17:00:00 | 2021-01-07 07:00:00 | 2022-01-03 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85270 |  | NotPrmUser |  | NotPrmUser
9455 | 648 | 0 | 0 | 56 | 0 | 0 | 56 | 0 | 0 | 0 | 1200 | 1200 | 0 | 0 | 0 | 1200 | 0 | 0 | 1620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
9450 | 648 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 820 | 820 | 0 | 0 | 0 | 820 | 0 | 0 | 1430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
9449 | 648 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 3120 | 3120 | 0 | 0 | 0 | 3120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2022-01-05 17:00:00 | 2021-01-07 07:00:00 | 2022-01-05 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
9448 | 648 | 0 | 0 | 363 | 1 | 0 | 362 | 0 | 0 | 0 | 3120 | 3120 | 86950 | 1600 | 86950 | 3120 | 86950 | 1600 | 0 | 0 | 0 | 0 | 5250032 | 0 | 0 | 0 | 5250032 | 0 | 5250032 | 0 | 0 | 0 | 0 |  |  | 2022-01-05 17:00:00 | 2021-01-07 07:00:00 | 2022-01-05 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86950 |  | NotPrmUser |  | NotPrmUser
9571 | 649 | 0 | 0 | 5 | 1 | 0 | 4 | 0 | 0 | 0 | 1010 | 1010 | 0 | 0 | 0 | 1010 | 0 | 0 | 1040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-08-30 17:00:00 | 2023-05-01 07:00:00 | 2023-08-30 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
9570 | 649 | 0 | 0 | 12 | 0 | 0 | 12 | 0 | 0 | 0 | 2050 | 2050 | 23870 | 8990 | 23870 | 2050 | 23870 | 8990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-12-31 17:00:00 | 2023-05-01 07:00:00 | 2023-12-31 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23870 |  | NotPrmUser |  | NotPrmUser
9575 | 649 | 0 | 0 | 4 | 2 | 0 | 2 | 0 | 0 | 0 | 2050 | 2050 | 0 | 0 | 0 | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-12-31 17:00:00 | 2023-05-01 07:00:00 | 2023-12-31 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
9569 | 649 | 0 | 0 | 21 | 3 | 0 | 18 | 0 | 0 | 0 | 2050 | 2050 | 23870 | 8990 | 23870 | 2050 | 23870 | 8990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-12-31 17:00:00 | 2023-05-01 07:00:00 | 2023-12-31 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23870 |  | NotPrmUser |  | NotPrmUser
9592 | 651 | 0 | 0 | 2449 | 0 | 0 | 2449 | 0 | 0 | 0 | 5240 | 5240 | 677590 | 15710 | 677590 | 5240 | 677590 | 15710 | 0 | 0 | 0 | 0 | 49859407.9996 | 0 | 0 | 0 | 49859407.9996 | 0 | 49859407.9996 | 0 | 0 | 0 | 0 |  |  | 2024-12-08 17:00:00 | 2023-03-16 07:00:00 | 2024-12-08 17:00:00 | 2023-03-16 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 677590 |  | NotPrmUser |  | NotPrmUser
9593 | 651 | 0 | 0 | 4389 | 2 | 0 | 4387 | 0 | 0 | 0 | 10990 | 10990 | 1178350 | 22270 | 1178350 | 10990 | 1178350 | 22270 | 1080 | 0 | 0 | 0 | 72131024.3966 | 0 | 0 | 0 | 72131024.3966 | 0 | 72131024.3966 | 0 | 0 | 0 | 0 |  |  | 2024-08-03 17:00:00 | 2021-01-07 07:00:00 | 2024-08-03 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1178350 |  | NotPrmUser |  | NotPrmUser
9577 | 651 | 0 | 0 | 6838 | 2 | 0 | 6836 | 0 | 0 | 0 | 12070 | 12070 | 1855940 | 37980 | 1855940 | 12070 | 1855940 | 37980 | 0 | 0 | 0 | 0 | 121990432.3962 | 0 | 0 | 0 | 121990432.3962 | 0 | 121990432.3962 | 0 | 0 | 0 | 0 |  |  | 2024-12-08 17:00:00 | 2021-01-07 07:00:00 | 2024-12-08 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1855940 |  | NotPrmUser |  | NotPrmUser
9584 | 652 | 0 | 0 | 5 | 1 | 0 | 4 | 0 | 0 | 0 | 1010 | 1010 | 0 | 0 | 0 | 1010 | 0 | 0 | 1040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-08-30 17:00:00 | 2023-05-01 07:00:00 | 2023-08-30 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
9580 | 652 | 0 | 0 | 12 | 0 | 0 | 12 | 0 | 0 | 0 | 2050 | 2050 | 23870 | 8990 | 23870 | 2050 | 23870 | 8990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-12-31 17:00:00 | 2023-05-01 07:00:00 | 2023-12-31 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23870 |  | NotPrmUser |  | NotPrmUser
9579 | 652 | 0 | 0 | 4 | 2 | 0 | 2 | 0 | 0 | 0 | 2050 | 2050 | 0 | 0 | 0 | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-12-31 17:00:00 | 2023-05-01 07:00:00 | 2023-12-31 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
9578 | 652 | 0 | 0 | 21 | 3 | 0 | 18 | 0 | 0 | 0 | 2050 | 2050 | 23870 | 8990 | 23870 | 2050 | 23870 | 8990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-12-31 17:00:00 | 2023-05-01 07:00:00 | 2023-12-31 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23870 |  | NotPrmUser |  | NotPrmUser
9591 | 653 | 0 | 0 | 5 | 1 | 0 | 4 | 0 | 0 | 0 | 1010 | 1010 | 0 | 0 | 0 | 1010 | 0 | 0 | 1040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-08-30 17:00:00 | 2023-05-01 07:00:00 | 2023-08-30 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
9587 | 653 | 0 | 0 | 12 | 0 | 0 | 12 | 0 | 0 | 0 | 2050 | 2050 | 23870 | 8990 | 23870 | 2050 | 23870 | 8990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-12-31 17:00:00 | 2023-05-01 07:00:00 | 2023-12-31 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23870 |  | NotPrmUser |  | NotPrmUser
9586 | 653 | 0 | 0 | 4 | 2 | 0 | 2 | 0 | 0 | 0 | 2050 | 2050 | 0 | 0 | 0 | 2050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-12-31 17:00:00 | 2023-05-01 07:00:00 | 2023-12-31 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
9585 | 653 | 0 | 0 | 21 | 3 | 0 | 18 | 0 | 0 | 0 | 2050 | 2050 | 23870 | 8990 | 23870 | 2050 | 23870 | 8990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-12-31 17:00:00 | 2023-05-01 07:00:00 | 2023-12-31 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23870 |  | NotPrmUser |  | NotPrmUser
17377 | 1356 | 0 | 0 | 2449 | 0 | 0 | 2449 | 0 | 0 | 0 | 5240 | 5240 | 677590 | 15710 | 677590 | 5240 | 677590 | 15710 | 0 | 0 | 0 | 0 | 49859407.9996 | 0 | 0 | 0 | 49859407.9996 | 0 | 49859407.9996 | 0 | 0 | 0 | 0 |  |  | 2024-12-08 17:00:00 | 2023-03-16 07:00:00 | 2024-12-08 17:00:00 | 2023-03-16 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 677590 |  | NotPrmUser |  | NotPrmUser
16062 | 1356 | 724 | 0 | 3665 | 2 | 0 | 4387 | 3120 | 0 | 0 | 10990 | 10990 | 1178350 | 22270 | 1012050 | 8310 | 1012050 | 19070 | 1080 | 0 | 0 | 0 | 72131024.3966 | 0 | 0 | 9500063.9974 | 72131024.3966 | 0 | 72131024.3966 | 0 | 0 | 166300 | 0 |  | 2021-01-07 07:00:00 | 2024-08-03 17:00:00 | 2021-01-07 07:00:00 | 2024-08-03 17:00:00 | 2021-11-16 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1012050 |  | NotPrmUser |  | NotPrmUser
16061 | 1356 | 724 | 0 | 6114 | 2 | 0 | 6836 | 3120 | 0 | 0 | 12070 | 12070 | 1855940 | 37980 | 1689640 | 9390 | 1689640 | 34780 | 0 | 0 | 0 | 0 | 121990432.3962 | 0 | 0 | 9500063.9974 | 121990432.3962 | 0 | 121990432.3962 | 0 | 0 | 166300 | 0 |  | 2021-01-07 07:00:00 | 2024-12-08 17:00:00 | 2021-01-07 07:00:00 | 2024-12-08 17:00:00 | 2021-11-16 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1689640 |  | NotPrmUser |  | NotPrmUser
19409 | 1357 | 0 | 0 | 2449 | 0 | 0 | 2449 | 0 | 0 | 0 | 5240 | 5240 | 677590 | 15710 | 677590 | 5240 | 677590 | 15710 | 0 | 0 | 0 | 0 | 49859407.9996 | 0 | 0 | 0 | 49859407.9996 | 0 | 49859407.9996 | 0 | 0 | 0 | 0 |  |  | 2024-12-08 17:00:00 | 2023-03-16 07:00:00 | 2024-12-08 17:00:00 | 2023-03-16 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 677590 |  | NotPrmUser |  | NotPrmUser
18094 | 1357 | 1291 | 0 | 3098 | 2 | 0 | 4387 | 7670 | 0 | 0 | 10990 | 10990 | 1178350 | 22270 | 809970 | 8310 | 809970 | 12350 | 1080 | 0 | 0 | 0 | 72131024.3966 | 0 | 0 | 23588863.9978 | 72131024.3966 | 0 | 72131024.3966 | 0 | 0 | 368380 | 0 |  | 2021-01-07 07:00:00 | 2024-08-03 17:00:00 | 2021-01-07 07:00:00 | 2024-08-03 17:00:00 | 2021-11-16 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 809970 |  | NotPrmUser |  | NotPrmUser
18093 | 1357 | 1291 | 0 | 5547 | 2 | 0 | 6836 | 7670 | 0 | 0 | 12070 | 12070 | 1855940 | 37980 | 1487560 | 9390 | 1487560 | 28060 | 0 | 0 | 0 | 0 | 121990432.3962 | 0 | 0 | 23588863.9978 | 121990432.3962 | 0 | 121990432.3962 | 0 | 0 | 368380 | 0 |  | 2021-01-07 07:00:00 | 2024-12-08 17:00:00 | 2021-01-07 07:00:00 | 2024-12-08 17:00:00 | 2021-11-16 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1487560 |  | NotPrmUser |  | NotPrmUser
21441 | 1358 | 0 | 0 | 2449 | 0 | 0 | 2449 | 0 | 0 | 0 | 5240 | 5240 | 677590 | 15710 | 677590 | 5240 | 677590 | 15710 | 0 | 0 | 0 | 0 | 49859407.9996 | 0 | 0 | 0 | 49859407.9996 | 0 | 49859407.9996 | 0 | 0 | 0 | 0 |  |  | 2024-12-08 17:00:00 | 2023-03-16 07:00:00 | 2024-12-08 17:00:00 | 2023-03-16 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 677590 |  | NotPrmUser |  | NotPrmUser
20126 | 1358 | 1343 | 0 | 3046 | 2 | 0 | 4387 | 10320 | 0 | 0 | 10990 | 10990 | 1178350 | 22270 | 792930 | 8310 | 792930 | 9310 | 1080 | 0 | 0 | 0 | 72131024.3966 | 0 | 0 | 25845663.9978 | 72131024.3966 | 0 | 72131024.3966 | 0 | 0 | 385420 | 0 |  | 2021-01-07 07:00:00 | 2024-08-03 17:00:00 | 2021-01-07 07:00:00 | 2024-08-03 17:00:00 | 2021-11-16 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 792930 |  | NotPrmUser |  | NotPrmUser
20125 | 1358 | 1343 | 0 | 5495 | 2 | 0 | 6836 | 10320 | 0 | 0 | 12070 | 12070 | 1855940 | 37980 | 1470520 | 9390 | 1470520 | 25020 | 0 | 0 | 0 | 0 | 121990432.3962 | 0 | 0 | 25845663.9978 | 121990432.3962 | 0 | 121990432.3962 | 0 | 0 | 385420 | 0 |  | 2021-01-07 07:00:00 | 2024-12-08 17:00:00 | 2021-01-07 07:00:00 | 2024-12-08 17:00:00 | 2021-11-16 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1470520 |  | NotPrmUser |  | NotPrmUser
23473 | 1359 | 24 | 0 | 2425 | 0 | 0 | 2449 | 420 | 0 | 0 | 5240 | 5240 | 677590 | 15710 | 666870 | 5240 | 666870 | 11670 | 0 | 0 | 0 | 0 | 49859407.9996 | 0 | 0 | 1270000 | 49859407.9996 | 0 | 49859407.9996 | 0 | 0 | 10720 | 0 |  | 2023-03-16 07:00:00 | 2024-12-08 17:00:00 | 2023-03-16 07:00:00 | 2024-12-08 17:00:00 | 2023-03-16 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 666870 |  | NotPrmUser |  | NotPrmUser
22158 | 1359 | 1343 | 0 | 3046 | 2 | 0 | 4387 | 10320 | 0 | 0 | 10990 | 10990 | 1178350 | 22270 | 792930 | 8310 | 792930 | 9310 | 1080 | 0 | 0 | 0 | 72131024.3966 | 0 | 0 | 25845663.9978 | 72131024.3966 | 0 | 72131024.3966 | 0 | 0 | 385420 | 0 |  | 2021-01-07 07:00:00 | 2024-08-03 17:00:00 | 2021-01-07 07:00:00 | 2024-08-03 17:00:00 | 2021-11-16 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 792930 |  | NotPrmUser |  | NotPrmUser
22157 | 1359 | 1367 | 0 | 5471 | 2 | 0 | 6836 | 10320 | 0 | 0 | 12070 | 12070 | 1855940 | 37980 | 1459800 | 9390 | 1459800 | 20980 | 0 | 0 | 0 | 0 | 121990432.3962 | 0 | 0 | 27115663.9978 | 121990432.3962 | 0 | 121990432.3962 | 0 | 0 | 396140 | 0 |  | 2021-01-07 07:00:00 | 2024-12-08 17:00:00 | 2021-01-07 07:00:00 | 2024-12-08 17:00:00 | 2021-11-16 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1459800 |  | NotPrmUser |  | NotPrmUser
25505 | 1360 | 24 | 0 | 2425 | 0 | 0 | 2449 | 420 | 0 | 0 | 5240 | 5240 | 677590 | 15710 | 666870 | 5240 | 666870 | 11670 | 0 | 0 | 0 | 0 | 49859407.9996 | 0 | 0 | 1270000 | 49859407.9996 | 0 | 49859407.9996 | 0 | 0 | 10720 | 0 |  | 2023-03-16 07:00:00 | 2024-12-08 17:00:00 | 2023-03-16 07:00:00 | 2024-12-08 17:00:00 | 2023-03-16 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 666870 |  | NotPrmUser |  | NotPrmUser
24190 | 1360 | 1311 | 1 | 3077 | 2 | 0 | 4387 | 10320 | 0 | 0 | 10990 | 10990 | 1178350 | 22270 | 808850 | 8310 | 808850 | 9310 | 1080 | 0 | 0 | 0 | 72131024.3966 | 0 | 0 | 25296668.9976 | 72131024.3966 | 0 | 72131024.3966 | 0 | 0 | 371580 | 0 |  | 2021-01-07 07:00:00 | 2024-08-03 17:00:00 | 2021-01-07 07:00:00 | 2024-08-03 17:00:00 | 2021-11-16 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 808850 |  | NotPrmUser |  | NotPrmUser
24189 | 1360 | 1335 | 1 | 5502 | 2 | 0 | 6836 | 10320 | 0 | 0 | 12070 | 12070 | 1855940 | 37980 | 1475720 | 9390 | 1475720 | 20980 | 0 | 0 | 0 | 0 | 121990432.3962 | 0 | 0 | 26566668.9976 | 121990432.3962 | 0 | 121990432.3962 | 0 | 0 | 382300 | 0 |  | 2021-01-07 07:00:00 | 2024-12-08 17:00:00 | 2021-01-07 07:00:00 | 2024-12-08 17:00:00 | 2021-11-16 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1475720 |  | NotPrmUser |  | NotPrmUser
27537 | 1361 | 0 | 0 | 2449 | 0 | 0 | 2449 | 0 | 0 | 0 | 5240 | 5240 | 677590 | 15710 | 677590 | 5240 | 677590 | 15710 | 0 | 0 | 0 | 0 | 49859407.9996 | 0 | 0 | 0 | 49859407.9996 | 0 | 49859407.9996 | 0 | 0 | 0 | 0 |  |  | 2024-11-25 17:00:00 | 2023-03-04 07:00:00 | 2024-11-25 17:00:00 | 2023-03-04 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 677590 |  | NotPrmUser |  | NotPrmUser
26222 | 1361 | 0 | 0 | 4389 | 2 | 0 | 4387 | 0 | 0 | 0 | 10850 | 10850 | 1178350 | 22270 | 1178350 | 10850 | 1178350 | 22270 | 1110 | 0 | 0 | 0 | 72131024.3966 | 0 | 0 | 0 | 72131024.3966 | 0 | 72131024.3966 | 0 | 0 | 0 | 0 |  |  | 2024-07-17 17:00:00 | 2021-01-07 07:00:00 | 2024-07-17 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1178350 |  | NotPrmUser |  | NotPrmUser
26221 | 1361 | 0 | 0 | 6838 | 2 | 0 | 6836 | 0 | 0 | 0 | 11960 | 11960 | 1855940 | 37980 | 1855940 | 11960 | 1855940 | 37980 | 0 | 0 | 0 | 0 | 121990432.3962 | 0 | 0 | 0 | 121990432.3962 | 0 | 121990432.3962 | 0 | 0 | 0 | 0 |  |  | 2024-11-25 17:00:00 | 2021-01-07 07:00:00 | 2024-11-25 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1855940 |  | NotPrmUser |  | NotPrmUser
29569 | 1362 | 0 | 0 | 2447 | 0 | 0 | 2447 | 0 | 0 | 0 | 5240 | 5240 | 662390 | 15710 | 662390 | 5240 | 662390 | 15710 | 0 | 0 | 0 | 0 | 50048597.96 | 0 | 0 | 0 | 50048597.96 | 0 | 50048597.96 | 0 | 0 | 0 | 0 |  |  | 2024-11-25 17:00:00 | 2023-03-04 07:00:00 | 2024-11-25 17:00:00 | 2023-03-04 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 662390 |  | NotPrmUser |  | NotPrmUser
28254 | 1362 | 0 | 0 | 4383 | 2 | 0 | 4381 | 0 | 0 | 0 | 10850 | 10850 | 1147950 | 22270 | 1147950 | 10850 | 1147950 | 22270 | 1110 | 0 | 0 | 0 | 71941834.46 | 0 | 0 | 0 | 71941834.46 | 0 | 71941834.46 | 0 | 0 | 0 | 0 |  |  | 2024-07-17 17:00:00 | 2021-01-07 07:00:00 | 2024-07-17 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1147950 |  | NotPrmUser |  | NotPrmUser
28253 | 1362 | 0 | 0 | 6830 | 2 | 0 | 6828 | 0 | 0 | 0 | 11960 | 11960 | 1810340 | 37980 | 1810340 | 11960 | 1810340 | 37980 | 0 | 0 | 0 | 0 | 121990432.42 | 0 | 0 | 0 | 121990432.42 | 0 | 121990432.42 | 0 | 0 | 0 | 0 |  |  | 2024-11-25 17:00:00 | 2021-01-07 07:00:00 | 2024-11-25 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1810340 |  | NotPrmUser |  | NotPrmUser
31593 | 1363 | 26 | 0 | 2421 | 0 | 0 | 2447 | 540 | 0 | 0 | 5240 | 5240 | 662390 | 15710 | 649910 | 5240 | 649910 | 11670 | 0 | 0 | 0 | 0 | 50048597.96 | 0 | 0 | 1785625 | 50048597.96 | 0 | 50048597.96 | 0 | 0 | 12480 | 0 |  | 2023-03-04 07:00:00 | 2024-11-25 17:00:00 | 2023-03-04 07:00:00 | 2024-11-25 17:00:00 | 2023-03-04 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 649910 |  | NotPrmUser |  | NotPrmUser
30286 | 1363 | 1883 | 318 | 2182 | 2 | 0 | 4381 | 9830 | 0 | 0 | 10850 | 10850 | 1147950 | 22270 | 578590 | 8190 | 578590 | 9100 | 1110 | 0 | 0 | 0 | 71941834.46 | 0 | 0 | 41896665.6665 | 71941834.46 | 0 | 71941834.46 | 0 | 0 | 679967.8586 | 0 |  | 2021-01-07 07:00:00 | 2024-07-17 17:00:00 | 2021-01-07 07:00:00 | 2024-07-17 17:00:00 | 2021-11-14 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 578590 |  | NotPrmUser |  | NotPrmUser
30285 | 1363 | 1909 | 318 | 4603 | 2 | 0 | 6828 | 9830 | 0 | 0 | 11960 | 11960 | 1810340 | 37980 | 1228500 | 9300 | 1228500 | 20770 | 0 | 0 | 0 | 0 | 121990432.42 | 0 | 0 | 43682290.6665 | 121990432.42 | 0 | 121990432.42 | 0 | 0 | 692447.8586 | 0 |  | 2021-01-07 07:00:00 | 2024-11-25 17:00:00 | 2021-01-07 07:00:00 | 2024-11-25 17:00:00 | 2021-11-14 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1228500 |  | NotPrmUser |  | NotPrmUser
33613 | 1364 | 30 | 68 | 2349 | 0 | 0 | 2447 | 660 | 0 | 0 | 5240 | 5240 | 662390 | 15710 | 649910 | 5240 | 649910 | 11670 | 0 | 0 | 0 | 0 | 50048597.96 | 0 | 0 | 1785625 | 50048597.96 | 0 | 50048597.96 | 0 | 0 | 12480 | 0 |  | 2023-03-04 07:00:00 | 2024-11-25 17:00:00 | 2023-03-04 07:00:00 | 2024-11-25 17:00:00 | 2023-03-04 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 649910 |  | NotPrmUser |  | NotPrmUser
32306 | 1364 | 2071 | 400 | 1912 | 2 | 0 | 4381 | 9830 | 0 | 0 | 10850 | 10850 | 1147950 | 22270 | 578590 | 8130 | 578590 | 9100 | 1110 | 0 | 0 | 0 | 71941834.46 | 0 | 0 | 41896666.282 | 71941834.46 | 0 | 71941834.46 | 0 | 0 | 679967.864 | 0 |  | 2021-01-07 07:00:00 | 2024-07-17 17:00:00 | 2021-01-07 07:00:00 | 2024-07-17 17:00:00 | 2021-11-21 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 578590 |  | NotPrmUser |  | NotPrmUser
32305 | 1364 | 2101 | 468 | 4261 | 2 | 0 | 6828 | 9830 | 0 | 0 | 11960 | 11960 | 1810340 | 37980 | 1228500 | 9240 | 1228500 | 20770 | 0 | 0 | 0 | 0 | 121990432.42 | 0 | 0 | 43682291.282 | 121990432.42 | 0 | 121990432.42 | 0 | 0 | 692447.864 | 0 |  | 2021-01-07 07:00:00 | 2024-11-25 17:00:00 | 2021-01-07 07:00:00 | 2024-11-25 17:00:00 | 2021-11-21 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1228500 |  | NotPrmUser |  | NotPrmUser
35633 | 1365 | 0 | 0 | 2447 | 0 | 0 | 2447 | 0 | 0 | 0 | 5240 | 5240 | 662390 | 15710 | 662390 | 5240 | 662390 | 15710 | 0 | 0 | 0 | 0 | 50048597.96 | 0 | 0 | 0 | 50048597.96 | 0 | 50048597.96 | 0 | 0 | 0 | 0 |  |  | 2024-12-08 17:00:00 | 2023-03-16 07:00:00 | 2024-12-08 17:00:00 | 2023-03-16 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 662390 |  | NotPrmUser |  | NotPrmUser
34326 | 1365 | 0 | 0 | 4383 | 2 | 0 | 4381 | 0 | 0 | 0 | 10990 | 10990 | 1147950 | 22270 | 1147950 | 10990 | 1147950 | 22270 | 1080 | 0 | 0 | 0 | 71941834.46 | 0 | 0 | 0 | 71941834.46 | 0 | 71941834.46 | 0 | 0 | 0 | 0 |  |  | 2024-08-03 17:00:00 | 2021-01-07 07:00:00 | 2024-08-03 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1147950 |  | NotPrmUser |  | NotPrmUser
36345 | 1365 | 0 | 0 | 12 | 3 | 0 | 9 | 0 | 0 | 0 | 12070 | 12070 | 0 | 0 | 0 | 12070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2024-12-08 17:00:00 | 2021-01-07 07:00:00 | 2024-12-08 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
34325 | 1365 | 0 | 0 | 6842 | 5 | 0 | 6837 | 0 | 0 | 0 | 12070 | 12070 | 1810340 | 37980 | 1810340 | 12070 | 1810340 | 37980 | 0 | 0 | 0 | 0 | 121990432.42 | 0 | 0 | 0 | 121990432.42 | 0 | 121990432.42 | 0 | 0 | 0 | 0 |  |  | 2024-12-08 17:00:00 | 2021-01-07 07:00:00 | 2024-12-08 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1810340 |  | NotPrmUser |  | NotPrmUser
37655 | 1366 | 30 | 68 | 2349 | 0 | 0 | 2447 | 660 | 0 | 0 | 5240 | 5240 | 662390 | 15710 | 649910 | 5240 | 649910 | 11670 | 0 | 0 | 0 | 0 | 50048597.96 | 0 | 0 | 1785625 | 50048597.96 | 0 | 50048597.96 | 0 | 0 | 12480 | 0 |  | 2023-03-16 07:00:00 | 2024-12-08 17:00:00 | 2023-03-16 07:00:00 | 2024-12-08 17:00:00 | 2023-03-16 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 649910 |  | NotPrmUser |  | NotPrmUser
36348 | 1366 | 2071 | 400 | 1912 | 2 | 0 | 4381 | 9980 | 0 | 0 | 10990 | 10990 | 1147950 | 22270 | 578590 | 8250 | 578590 | 9100 | 1080 | 0 | 0 | 0 | 71941834.46 | 0 | 0 | 41896666.282 | 71941834.46 | 0 | 71941834.46 | 0 | 0 | 679967.864 | 0 |  | 2021-01-07 07:00:00 | 2024-08-03 17:00:00 | 2021-01-07 07:00:00 | 2024-08-03 17:00:00 | 2021-11-23 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 578590 |  | NotPrmUser |  | NotPrmUser
36347 | 1366 | 7 | 0 | 5 | 3 | 0 | 9 | 6830 | 0 | 0 | 12070 | 12070 | 0 | 0 | 0 | 4160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2021-01-07 07:00:00 | 2024-12-08 17:00:00 | 2021-01-07 07:00:00 | 2024-12-08 17:00:00 | 2023-07-29 17:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
36346 | 1366 | 2108 | 468 | 4266 | 5 | 0 | 6837 | 9980 | 0 | 0 | 12070 | 12070 | 1810340 | 37980 | 1228500 | 9330 | 1228500 | 20770 | 0 | 0 | 0 | 0 | 121990432.42 | 0 | 0 | 43682291.282 | 121990432.42 | 0 | 121990432.42 | 0 | 0 | 692447.864 | 0 |  | 2021-01-07 07:00:00 | 2024-12-08 17:00:00 | 2021-01-07 07:00:00 | 2024-12-08 17:00:00 | 2021-11-23 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1228500 |  | NotPrmUser |  | NotPrmUser
39676 | 1367 | 30 | 68 | 2349 | 4 | 20 | 2423 | 1390 | 0 | 0 | 5860 | 5860 | 662390 | 15710 | 649910 | 4980 | 649910 | 11670 | 0 | 0 | 0 | 0 | 50048597.96 | 0 | 0 | 1785625 | 50048597.96 | 200000 | 50048597.96 | 0 | 0 | 12480 | 2080 |  | 2023-03-16 07:00:00 | 2025-02-19 17:00:00 | 2023-03-16 07:00:00 | 2025-02-19 17:00:00 | 2023-07-06 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 649910 |  | NotPrmUser |  | NotPrmUser
38369 | 1367 | 2071 | 400 | 1912 | 2203 | 28 | 2152 | 9220 | 0 | 0 | 9770 | 10240 | 1147950 | 22270 | 578590 | 2810 | 578590 | 9100 | 2920 | 0 | 0 | 0 | 71941834.46 | 0 | 0 | 41896666.282 | 71941834.46 | 35417785.8268 | 71941834.46 | 0 | 0 | 679967.864 | 608180 |  | 2021-01-07 07:00:00 | 2024-05-02 17:00:00 | 2021-01-07 07:00:00 | 2024-03-04 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 578590 |  | NotPrmUser |  | NotPrmUser
38368 | 1367 | 7 | 0 | 5 | 7 | 0 | 5 | 6830 | 0 | 0 | 12690 | 12690 | 0 | 0 | 0 | 4160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2021-01-07 07:00:00 | 2025-02-19 17:00:00 | 2021-01-07 07:00:00 | 2025-02-19 17:00:00 | 2023-10-10 17:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
38367 | 1367 | 2108 | 468 | 4266 | 2214 | 48 | 4580 | 9220 | 0 | 0 | 12690 | 12690 | 1810340 | 37980 | 1228500 | 5730 | 1228500 | 20770 | 0 | 0 | 0 | 0 | 121990432.42 | 0 | 0 | 43682291.282 | 121990432.42 | 35617785.8268 | 121990432.42 | 0 | 0 | 692447.864 | 610260 |  | 2021-01-07 07:00:00 | 2025-02-19 17:00:00 | 2021-01-07 07:00:00 | 2025-02-19 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1228500 |  | NotPrmUser |  | NotPrmUser
41697 | 1368 | 30 | 68 | 2349 | 4 | 20 | 2423 | 260 | 0 | 0 | 5140 | 5010 | 662390 | 15710 | 649910 | 4880 | 649910 | 11670 | 0 | 0 | 0 | 0 | 50048597.96 | 0 | 0 | 1785625 | 50048597.96 | 200000 | 50048597.96 | 0 | 0 | 12480 | 2080 |  | 2023-03-01 07:00:00 | 2024-11-11 17:00:00 | 2023-03-16 07:00:00 | 2024-11-11 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 649910 |  | NotPrmUser |  | NotPrmUser
40390 | 1368 | 2071 | 400 | 1912 | 2203 | 28 | 2152 | 6960 | 0 | 0 | 9290 | 10240 | 1147950 | 22270 | 578590 | 2330 | 578590 | 9100 | 2550 | 0 | 0 | 0 | 71941834.46 | 0 | 0 | 41896666.282 | 71941834.46 | 35417785.8268 | 71941834.46 | 0 | 0 | 679967.864 | 608180 |  | 2021-01-07 07:00:00 | 2024-05-02 17:00:00 | 2021-01-07 07:00:00 | 2024-01-07 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 578590 |  | NotPrmUser |  | NotPrmUser
40389 | 1368 | 7 | 0 | 5 | 7 | 0 | 5 | 6830 | 0 | 0 | 11840 | 11840 | 0 | 0 | 0 | 3370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2021-01-07 07:00:00 | 2024-11-11 17:00:00 | 2021-01-07 07:00:00 | 2024-11-11 17:00:00 | 2023-10-03 17:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
40388 | 1368 | 2108 | 468 | 4266 | 2214 | 48 | 4580 | 6960 | 0 | 0 | 11840 | 11840 | 1810340 | 37980 | 1228500 | 4880 | 1228500 | 20770 | 0 | 0 | 0 | 0 | 121990432.42 | 0 | 0 | 43682291.282 | 121990432.42 | 35617785.8268 | 121990432.42 | 0 | 0 | 692447.864 | 610260 |  | 2021-01-07 07:00:00 | 2024-11-11 17:00:00 | 2021-01-07 07:00:00 | 2024-11-11 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1228500 |  | NotPrmUser |  | NotPrmUser
43718 | 1369 | 30 | 68 | 2349 | 4 | 20 | 2423 | 260 | 0 | 0 | 5120 | 4990 | 662390 | 15710 | 649910 | 4860 | 649910 | 11670 | 0 | 0 | 0 | 0 | 50048597.96 | 0 | 0 | 1785625 | 50048597.96 | 200000 | 50048597.96 | 0 | 0 | 12480 | 2080 |  | 2023-03-01 07:00:00 | 2024-11-09 17:00:00 | 2023-03-16 07:00:00 | 2024-11-09 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 649910 |  | NotPrmUser |  | NotPrmUser
42411 | 1369 | 2071 | 400 | 1912 | 2203 | 28 | 2152 | 6960 | 0 | 0 | 9220 | 10240 | 1147950 | 22270 | 578590 | 2260 | 578590 | 9100 | 2600 | 0 | 0 | 0 | 71941834.46 | 0 | 0 | 41896666.282 | 71941834.46 | 35417785.8268 | 71941834.46 | 0 | 0 | 679967.864 | 608180 |  | 2021-01-07 07:00:00 | 2024-05-02 17:00:00 | 2021-01-07 07:00:00 | 2023-12-30 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 578590 |  | NotPrmUser |  | NotPrmUser
42410 | 1369 | 7 | 0 | 5 | 7 | 0 | 5 | 6830 | 0 | 0 | 11820 | 11820 | 0 | 0 | 0 | 3440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2021-01-07 07:00:00 | 2024-11-09 17:00:00 | 2021-01-07 07:00:00 | 2024-11-09 17:00:00 | 2023-09-21 17:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
42409 | 1369 | 2108 | 468 | 4266 | 2214 | 48 | 4580 | 6960 | 0 | 0 | 11820 | 11820 | 1810340 | 37980 | 1228500 | 4860 | 1228500 | 20770 | 0 | 0 | 0 | 0 | 121990432.42 | 0 | 0 | 43682291.282 | 121990432.42 | 35617785.8268 | 121990432.42 | 0 | 0 | 692447.864 | 610260 |  | 2021-01-07 07:00:00 | 2024-11-09 17:00:00 | 2021-01-07 07:00:00 | 2024-11-09 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1228500 |  | NotPrmUser |  | NotPrmUser
45739 | 1370 | 30 | 68 | 2349 | 4 | 20 | 2423 | 130 | 0 | 0 | 4990 | 4990 | 662390 | 15710 | 649910 | 4860 | 649910 | 11670 | 0 | 0 | 0 | 0 | 50048597.96 | 0 | 0 | 1785625 | 50048597.96 | 200000 | 50048597.96 | 0 | 0 | 12480 | 2080 |  | 2023-03-16 07:00:00 | 2024-11-09 17:00:00 | 2023-03-16 07:00:00 | 2024-11-09 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 649910 |  | NotPrmUser |  | NotPrmUser
44432 | 1370 | 2073 | 398 | 1912 | 2203 | 28 | 2152 | 6960 | 0 | 0 | 9120 | 10240 | 1147950 | 22270 | 578590 | 2160 | 578590 | 9100 | 2700 | 0 | 0 | 0 | 71941834.46 | 0 | 0 | 41896666.282 | 71941834.46 | 35417785.8268 | 71941834.46 | 0 | 0 | 679967.864 | 608180 |  | 2021-01-07 07:00:00 | 2024-05-02 17:00:00 | 2021-01-07 07:00:00 | 2023-12-18 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 578590 |  | NotPrmUser |  | NotPrmUser
44431 | 1370 | 7 | 0 | 5 | 7 | 0 | 5 | 6830 | 0 | 0 | 11820 | 11820 | 0 | 0 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2021-01-07 07:00:00 | 2024-11-09 17:00:00 | 2021-01-07 07:00:00 | 2024-11-09 17:00:00 | 2023-09-14 17:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
44430 | 1370 | 2110 | 466 | 4266 | 2214 | 48 | 4580 | 6960 | 0 | 0 | 11820 | 11820 | 1810340 | 37980 | 1228500 | 4860 | 1228500 | 20770 | 0 | 0 | 0 | 0 | 121990432.42 | 0 | 0 | 43682291.282 | 121990432.42 | 35617785.8268 | 121990432.42 | 0 | 0 | 692447.864 | 610260 |  | 2021-01-07 07:00:00 | 2024-11-09 17:00:00 | 2021-01-07 07:00:00 | 2024-11-09 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1228500 |  | NotPrmUser |  | NotPrmUser
47760 | 1371 | 30 | 68 | 2349 | 30 | 68 | 2349 | 130 | 0 | 0 | 4990 | 4990 | 662390 | 15710 | 649910 | 4860 | 649910 | 11670 | 0 | 1785625 | 0 | 0 | 50048598.32 | 0 | 0 | 1785625 | 48262973.32 | 1785625 | 48262973.32 | 0 | 0 | 12480 | 12480 |  | 2023-03-16 07:00:00 | 2024-11-09 17:00:00 | 2023-03-16 07:00:00 | 2024-11-09 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 649910 |  | NotPrmUser |  | NotPrmUser
46453 | 1371 | 2073 | 398 | 1912 | 2073 | 398 | 1912 | 6960 | 0 | 0 | 9120 | 9120 | 1147950 | 22270 | 578590 | 2160 | 578590 | 9100 | 2700 | 41896666.3044 | 0 | 0 | 71941834.88 | 0 | 0 | 41896666.3044 | 30045168.5756 | 41531241.9788 | 30045168.5756 | 0 | 0 | 679967.864 | 676171.8623 |  | 2021-01-07 07:00:00 | 2023-12-18 17:00:00 | 2021-01-07 07:00:00 | 2023-12-18 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 578590 |  | NotPrmUser |  | NotPrmUser
46452 | 1371 | 7 | 0 | 5 | 7 | 0 | 5 | 6830 | 0 | 0 | 11820 | 11820 | 0 | 0 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2021-01-07 07:00:00 | 2024-11-09 17:00:00 | 2021-01-07 07:00:00 | 2024-11-09 17:00:00 | 2023-09-14 17:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
46451 | 1371 | 2110 | 466 | 4266 | 2110 | 466 | 4266 | 6960 | 0 | 0 | 11820 | 11820 | 1810340 | 37980 | 1228500 | 4860 | 1228500 | 20770 | 0 | 43682291.3044 | 0 | 0 | 121990433.2 | 0 | 0 | 43682291.3044 | 78308141.8956 | 43316866.9788 | 78308141.8956 | 0 | 0 | 692447.864 | 688651.8623 |  | 2021-01-07 07:00:00 | 2024-11-09 17:00:00 | 2021-01-07 07:00:00 | 2024-11-09 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1228500 |  | NotPrmUser |  | NotPrmUser
51802 | 1373 | 30 | 68 | 2349 | 30 | 68 | 2349 | 130 | 0 | 0 | 5430 | 5430 | 662390 | 15710 | 649910 | 5300 | 649910 | 11670 | 0 | 1785625 | 0 | 0 | 50048598.32 | 0 | 0 | 1785625 | 48262973.32 | 1785625 | 48262973.32 | 0 | 0 | 12480 | 12480 |  | 2023-03-16 07:00:00 | 2024-12-30 17:00:00 | 2023-03-16 07:00:00 | 2024-12-30 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 649910 |  | NotPrmUser |  | NotPrmUser
50495 | 1373 | 2073 | 398 | 1912 | 2073 | 398 | 1912 | 6960 | 0 | 0 | 10700 | 10700 | 1147950 | 22270 | 578590 | 3740 | 578590 | 9100 | 1560 | 41896666.3044 | 0 | 0 | 71941834.88 | 0 | 0 | 41896666.3044 | 30045168.5756 | 41531241.9788 | 30045168.5756 | 0 | 0 | 679967.864 | 676171.8623 |  | 2021-01-07 07:00:00 | 2024-06-30 17:00:00 | 2021-01-07 07:00:00 | 2024-06-30 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 578590 |  | NotPrmUser |  | NotPrmUser
50494 | 1373 | 7 | 0 | 5 | 7 | 0 | 5 | 6830 | 0 | 0 | 12260 | 12260 | 0 | 0 | 0 | 3660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2021-01-07 07:00:00 | 2024-12-30 17:00:00 | 2021-01-07 07:00:00 | 2024-12-30 17:00:00 | 2023-10-18 17:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
50493 | 1373 | 2110 | 466 | 4266 | 2110 | 466 | 4266 | 6960 | 0 | 0 | 12260 | 12260 | 1810340 | 37980 | 1228500 | 5300 | 1228500 | 20770 | 0 | 43682291.3044 | 0 | 0 | 121990433.2 | 0 | 0 | 43682291.3044 | 78308141.8956 | 43316866.9788 | 78308141.8956 | 0 | 0 | 692447.864 | 688651.8623 |  | 2021-01-07 07:00:00 | 2024-12-30 17:00:00 | 2021-01-07 07:00:00 | 2024-12-30 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1228500 |  | NotPrmUser |  | NotPrmUser
53823 | 1374 | 30 | 68 | 2349 | 30 | 68 | 2349 | 130 | 0 | 0 | 5430 | 5430 | 662390 | 15710 | 649910 | 5300 | 649910 | 11670 | 0 | 1785625 | 0 | 0 | 50048598.32 | 0 | 0 | 1785625 | 48262973.32 | 1785625 | 48262973.32 | 0 | 0 | 12480 | 12480 |  | 2023-03-16 07:00:00 | 2024-12-30 17:00:00 | 2023-03-16 07:00:00 | 2024-12-30 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 649910 |  | NotPrmUser |  | NotPrmUser
52516 | 1374 | 2073 | 398 | 1912 | 2073 | 398 | 1912 | 6960 | 0 | 0 | 10700 | 10700 | 1147950 | 22270 | 578590 | 3740 | 578590 | 9100 | 1560 | 41896666.3044 | 0 | 0 | 71941834.88 | 0 | 0 | 41896666.3044 | 30045168.5756 | 41882132.5913 | 30045168.5756 | 0 | 0 | 679967.864 | 677694.5225 |  | 2021-01-07 07:00:00 | 2024-06-30 17:00:00 | 2021-01-07 07:00:00 | 2024-06-30 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 578590 |  | NotPrmUser |  | NotPrmUser
52515 | 1374 | 7 | 0 | 5 | 7 | 0 | 5 | 6830 | 0 | 0 | 12260 | 12260 | 0 | 0 | 0 | 3660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2021-01-07 07:00:00 | 2024-12-30 17:00:00 | 2021-01-07 07:00:00 | 2024-12-30 17:00:00 | 2023-10-18 17:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
52514 | 1374 | 2110 | 466 | 4266 | 2110 | 466 | 4266 | 6960 | 0 | 0 | 12260 | 12260 | 1810340 | 37980 | 1228500 | 5300 | 1228500 | 20770 | 0 | 43682291.3044 | 0 | 0 | 121990433.2 | 0 | 0 | 43682291.3044 | 78308141.8956 | 43667757.5913 | 78308141.8956 | 0 | 0 | 692447.864 | 690174.5225 |  | 2021-01-07 07:00:00 | 2024-12-30 17:00:00 | 2021-01-07 07:00:00 | 2024-12-30 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1228500 |  | NotPrmUser |  | NotPrmUser
55844 | 1375 | 30 | 68 | 2349 | 30 | 68 | 2349 | 130 | 0 | 0 | 5430 | 5430 | 662390 | 15710 | 649910 | 5300 | 649910 | 11670 | 0 | 1785625 | 0 | 0 | 50048598.32 | 0 | 0 | 1785625 | 48262973.32 | 1785625 | 48262973.32 | 0 | 0 | 12480 | 12480 |  | 2023-03-16 07:00:00 | 2024-12-30 17:00:00 | 2023-03-16 07:00:00 | 2024-12-30 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 649910 |  | NotPrmUser |  | NotPrmUser
54537 | 1375 | 2073 | 398 | 1912 | 2073 | 398 | 1912 | 6960 | 0 | 0 | 10700 | 10700 | 1147950 | 22270 | 578590 | 3740 | 578590 | 9100 | 1560 | 41896666.3044 | 0 | 0 | 71941834.88 | 0 | 0 | 41896666.3044 | 30045168.5756 | 41882132.5913 | 30045168.5756 | 0 | 0 | 679967.864 | 677694.5225 |  | 2021-01-07 07:00:00 | 2024-06-30 17:00:00 | 2021-01-07 07:00:00 | 2024-06-30 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 578590 |  | NotPrmUser |  | NotPrmUser
54536 | 1375 | 7 | 0 | 5 | 7 | 0 | 5 | 6830 | 0 | 0 | 12260 | 12260 | 0 | 0 | 0 | 3590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2021-01-07 07:00:00 | 2024-12-30 17:00:00 | 2021-01-07 07:00:00 | 2024-12-30 17:00:00 | 2023-10-26 17:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
54535 | 1375 | 2110 | 466 | 4266 | 2110 | 466 | 4266 | 6960 | 0 | 0 | 12260 | 12260 | 1810340 | 37980 | 1228500 | 5300 | 1228500 | 20770 | 0 | 43682291.3044 | 0 | 0 | 121990433.2 | 0 | 0 | 43682291.3044 | 78308141.8956 | 43667757.5913 | 78308141.8956 | 0 | 0 | 692447.864 | 690174.5225 |  | 2021-01-07 07:00:00 | 2024-12-30 17:00:00 | 2021-01-07 07:00:00 | 2024-12-30 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1228500 |  | NotPrmUser |  | NotPrmUser
57865 | 1376 | 30 | 68 | 2349 | 30 | 68 | 2349 | 130 | 0 | 0 | 5430 | 5430 | 662390 | 15710 | 649910 | 5300 | 649910 | 11670 | 0 | 1785625 | 0 | 0 | 50048598.32 | 0 | 0 | 1785625 | 48262973.32 | 1785625 | 48262973.32 | 0 | 0 | 12480 | 12480 |  | 2023-03-16 07:00:00 | 2024-12-30 17:00:00 | 2023-03-16 07:00:00 | 2024-12-30 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 649910 |  | NotPrmUser |  | NotPrmUser
56558 | 1376 | 2073 | 398 | 1912 | 2073 | 398 | 1912 | 6960 | 0 | 0 | 10700 | 10700 | 1147950 | 22270 | 578590 | 3740 | 578590 | 9100 | 1560 | 41896666.3044 | 0 | 0 | 71941834.88 | 0 | 0 | 41896666.3044 | 30045168.5756 | 41882132.5913 | 30045168.5756 | 0 | 0 | 679967.864 | 677694.5225 |  | 2021-01-07 07:00:00 | 2024-06-30 17:00:00 | 2021-01-07 07:00:00 | 2024-06-30 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 578590 |  | NotPrmUser |  | NotPrmUser
56557 | 1376 | 7 | 0 | 5 | 7 | 0 | 5 | 6830 | 0 | 0 | 12260 | 12260 | 0 | 0 | 0 | 3590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2021-01-07 07:00:00 | 2024-12-30 17:00:00 | 2021-01-07 07:00:00 | 2024-12-30 17:00:00 | 2023-10-26 17:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
56556 | 1376 | 2110 | 466 | 4266 | 2110 | 466 | 4266 | 6960 | 0 | 0 | 12260 | 12260 | 1810340 | 37980 | 1228500 | 5300 | 1228500 | 20770 | 0 | 43682291.3044 | 0 | 0 | 121990433.2 | 0 | 0 | 43682291.3044 | 78308141.8956 | 43667757.5913 | 78308141.8956 | 0 | 0 | 692447.864 | 690174.5225 |  | 2021-01-07 07:00:00 | 2024-12-30 17:00:00 | 2021-01-07 07:00:00 | 2024-12-30 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1228500 |  | NotPrmUser |  | NotPrmUser
59885 | 1377 | 0 | 0 | 2447 | 0 | 0 | 2447 | 0 | 0 | 0 | 5160 | 5160 | 662390 | 15710 | 662390 | 5160 | 662390 | 15710 | 0 | 0 | 0 | 0 | 50048597.96 | 0 | 0 | 0 | 50048597.96 | 0 | 50048597.96 | 0 | 0 | 0 | 0 |  |  | 2025-07-03 17:00:00 | 2023-10-19 07:00:00 | 2025-07-03 17:00:00 | 2023-10-19 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 662390 |  | NotPrmUser |  | NotPrmUser
58578 | 1377 | 0 | 0 | 4383 | 2 | 0 | 4381 | 0 | 0 | 0 | 12800 | 12800 | 1147950 | 22270 | 1147950 | 12800 | 1147950 | 22270 | 960 | 0 | 0 | 0 | 71941834.46 | 0 | 0 | 0 | 71941834.46 | 0 | 71941834.46 | 0 | 0 | 0 | 0 |  |  | 2025-03-04 17:00:00 | 2021-01-07 07:00:00 | 2025-03-04 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1147950 |  | NotPrmUser |  | NotPrmUser
58577 | 1377 | 0 | 0 | 6830 | 2 | 0 | 6828 | 0 | 0 | 0 | 13760 | 13760 | 1810340 | 37980 | 1810340 | 13760 | 1810340 | 37980 | 0 | 0 | 0 | 0 | 121990432.42 | 0 | 0 | 0 | 121990432.42 | 0 | 121990432.42 | 0 | 0 | 0 | 0 |  |  | 2025-07-03 17:00:00 | 2021-01-07 07:00:00 | 2025-07-03 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1810340 |  | NotPrmUser |  | NotPrmUser
61906 | 1378 | 30 | 68 | 2349 | 30 | 68 | 2349 | 130 | 4040 | 10520 | 5430 | 5430 | 521950 | 15710 | 511430 | 5300 | 511430 | 11670 | 0 | 1785625 | 0 | 0 | 50048598.32 | 0 | 0 | 1785625 | 48262973.32 | 1785625 | 48262973.32 | 0 | 0 | 10520 | 10520 |  | 2023-03-16 07:00:00 | 2024-12-30 17:00:00 | 2023-03-16 07:00:00 | 2024-12-30 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 521950 |  | NotPrmUser |  | NotPrmUser
60599 | 1378 | 2073 | 398 | 1912 | 2073 | 398 | 1912 | 6960 | 13170 | 522257.017 | 10700 | 10700 | 899390 | 22270 | 377132.983 | 3740 | 377132.983 | 9100 | 1560 | 41896666.3044 | 0 | 0 | 71941834.88 | 0 | 0 | 41896666.3044 | 30045168.5756 | 41882132.5913 | 30045168.5756 | 0 | 0 | 522257.017 | 520930.7934 |  | 2021-01-07 07:00:00 | 2024-06-30 17:00:00 | 2021-01-07 07:00:00 | 2024-06-30 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 899390 |  | NotPrmUser |  | NotPrmUser
60598 | 1378 | 7 | 0 | 5 | 7 | 0 | 5 | 6830 | 0 | 0 | 12260 | 12260 | 0 | 0 | 0 | 3590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2021-01-07 07:00:00 | 2024-12-30 17:00:00 | 2021-01-07 07:00:00 | 2024-12-30 17:00:00 | 2023-10-26 17:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
60597 | 1378 | 2110 | 466 | 4266 | 2110 | 466 | 4266 | 6960 | 17210 | 532777.017 | 12260 | 12260 | 1421340 | 37980 | 888562.983 | 5300 | 888562.983 | 20770 | 0 | 43682291.3044 | 0 | 0 | 121990433.2 | 0 | 0 | 43682291.3044 | 78308141.8956 | 43667757.5913 | 78308141.8956 | 0 | 0 | 532777.017 | 531450.7934 |  | 2021-01-07 07:00:00 | 2024-12-30 17:00:00 | 2021-01-07 07:00:00 | 2024-12-30 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1421340 |  | NotPrmUser |  | NotPrmUser
63934 | 1379 | 0 | 0 | 25 | 0 | 0 | 25 | 0 | 0 | 0 | 2050 | 2050 | 39070 | 8990 | 39070 | 2050 | 39070 | 8990 | 10 | 0 | 0 | 0 | 2000000 | 0 | 0 | 0 | 2000000 | 0 | 2000000 | 0 | 0 | 0 | 0 |  |  | 2024-12-07 17:00:00 | 2024-04-02 07:00:00 | 2024-12-07 17:00:00 | 2024-04-02 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39070 |  | NotPrmUser |  | NotPrmUser
62619 | 1379 | 0 | 0 | 29 | 0 | 0 | 29 | 0 | 0 | 0 | 2050 | 2050 | 54270 | 8990 | 54270 | 2050 | 54270 | 8990 | 1080 | 0 | 0 | 0 | 4000000 | 0 | 0 | 0 | 4000000 | 0 | 4000000 | 0 | 0 | 0 | 0 |  |  | 2024-08-03 17:00:00 | 2023-11-28 07:00:00 | 2024-08-03 17:00:00 | 2023-11-28 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54270 |  | NotPrmUser |  | NotPrmUser
62618 | 1379 | 0 | 0 | 54 | 0 | 0 | 54 | 0 | 0 | 0 | 3120 | 3120 | 93340 | 17980 | 93340 | 3120 | 93340 | 17980 | 10 | 0 | 0 | 0 | 6000000 | 0 | 0 | 0 | 6000000 | 0 | 6000000 | 0 | 0 | 0 | 0 |  |  | 2024-12-07 17:00:00 | 2023-11-28 07:00:00 | 2024-12-07 17:00:00 | 2023-11-28 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93340 |  | NotPrmUser |  | NotPrmUser
64807 | 1380 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 380 | 380 | 3800 | 0 | 3800 | 380 | 3800 | 0 | 4860 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 500000 | 0 | 500000 | 0 | 0 | 0 | 0 |  |  | 2021-02-20 17:00:00 | 2021-01-07 07:00:00 | 2021-02-20 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3800 |  | NotPrmUser |  | NotPrmUser
64806 | 1380 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 260 | 260 | 1040 | 0 | 1040 | 260 | 1040 | 0 | 420 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 500000 | 0 | 500000 | 0 | 0 | 0 | 0 |  |  | 2022-07-16 17:00:00 | 2022-06-16 07:00:00 | 2022-07-16 17:00:00 | 2022-06-16 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1040 |  | NotPrmUser |  | NotPrmUser
64785 | 1380 | 0 | 0 | 80 | 0 | 0 | 80 | 0 | 0 | 0 | 3720 | 3720 | 19570 | 0 | 19570 | 3720 | 19570 | 0 | 410 | 0 | 0 | 0 | 788494 | 0 | 0 | 0 | 788494 | 0 | 788494 | 0 | 0 | 0 | 0 |  |  | 2022-07-20 17:00:00 | 2021-05-13 07:00:00 | 2022-07-20 17:00:00 | 2021-05-13 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19570 |  | NotPrmUser |  | NotPrmUser
64754 | 1380 | 0 | 0 | 85 | 0 | 0 | 85 | 0 | 0 | 0 | 4080 | 4080 | 27580 | 0 | 27580 | 4080 | 27580 | 0 | 430 | 0 | 0 | 0 | 1108593 | 0 | 0 | 0 | 1108593 | 0 | 1108593 | 0 | 0 | 0 | 0 |  |  | 2022-07-20 17:00:00 | 2021-04-01 07:00:00 | 2022-07-20 17:00:00 | 2021-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27580 |  | NotPrmUser |  | NotPrmUser
64712 | 1380 | 0 | 0 | 238 | 0 | 0 | 238 | 0 | 0 | 0 | 3740 | 3740 | 73880 | 0 | 73880 | 3740 | 73880 | 0 | 0 | 0 | 0 | 0 | 5780965 | 0 | 0 | 0 | 5780965 | 0 | 5780965 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2021-07-01 07:00:00 | 2022-09-10 17:00:00 | 2021-07-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73880 |  | NotPrmUser |  | NotPrmUser
64681 | 1380 | 0 | 0 | 105 | 0 | 0 | 105 | 0 | 0 | 0 | 4310 | 4310 | 32920 | 1680 | 32920 | 4310 | 32920 | 1680 | 670 | 0 | 0 | 0 | 3686800 | 0 | 0 | 0 | 3686800 | 0 | 3686800 | 0 | 0 | 0 | 0 |  |  | 2022-06-23 17:00:00 | 2021-02-07 07:00:00 | 2022-06-23 17:00:00 | 2021-02-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32920 |  | NotPrmUser |  | NotPrmUser
64680 | 1380 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 260 | 260 | 1040 | 0 | 1040 | 260 | 1040 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 |  |  | 2021-02-06 17:00:00 | 2021-01-07 07:00:00 | 2021-02-06 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1040 |  | NotPrmUser |  | NotPrmUser
64650 | 1380 | 0 | 0 | 511 | 0 | 0 | 511 | 0 | 0 | 0 | 5240 | 5240 | 159830 | 1680 | 159830 | 5240 | 159830 | 1680 | 0 | 0 | 0 | 0 | 12464852 | 0 | 0 | 0 | 12464852 | 0 | 12464852 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159830 |  | NotPrmUser |  | NotPrmUser
64985 | 1381 | 0 | 0 | 30 | 0 | 0 | 30 | 0 | 0 | 0 | 480 | 480 | 3600 | 0 | 3600 | 480 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 2022-09-10 17:00:00 | 2022-07-17 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 |  | NotPrmUser |  | NotPrmUser
64856 | 1381 | 0 | 0 | 511 | 0 | 0 | 511 | 0 | 0 | 0 | 5240 | 5240 | 159830 | 1680 | 159830 | 5240 | 159830 | 1680 | 0 | 0 | 0 | 0 | 12464852 | 0 | 0 | 0 | 12464852 | 0 | 12464852 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159830 |  | NotPrmUser |  | NotPrmUser
64834 | 1381 | 0 | 0 | 56 | 0 | 0 | 56 | 0 | 0 | 0 | 1200 | 1200 | 0 | 0 | 0 | 1200 | 0 | 0 | 3740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 2021-06-30 17:00:00 | 2021-02-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
64829 | 1381 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 820 | 820 | 0 | 0 | 0 | 820 | 0 | 0 | 3560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 2021-04-12 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
64828 | 1381 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 5240 | 5240 | 0 | 0 | 0 | 5240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
64827 | 1381 | 0 | 0 | 607 | 1 | 0 | 606 | 0 | 0 | 0 | 5240 | 5240 | 163430 | 1680 | 163430 | 5240 | 163430 | 1680 | 0 | 0 | 0 | 0 | 12464852 | 0 | 0 | 0 | 12464852 | 0 | 12464852 | 0 | 0 | 0 | 0 |  |  | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 2022-09-10 17:00:00 | 2021-01-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163430 |  | NotPrmUser |  | NotPrmUser
66434 | 1383 | 12 | 86 | 2349 | 30 | 68 | 2349 | 130 | 4040 | 12480 | 5430 | 5430 | 662390 | 15710 | 649910 | 5300 | 649910 | 11670 | 0 | 1785625 | 0 | 0 | 50048598.32 | 0 | 0 | 1785625 | 48262973.32 | 1785625 | 48262973.32 | 0 | 0 | 12480 | 12480 |  | 2023-03-16 07:00:00 | 2024-12-30 17:00:00 | 2023-03-16 07:00:00 | 2024-12-30 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 662390 |  | NotPrmUser |  | NotPrmUser
65127 | 1383 | 386 | 2055 | 1942 | 2043 | 398 | 1942 | 5720 | 13170 | 676607.864 | 9460 | 9460 | 1147950 | 22270 | 471342.136 | 3740 | 471342.136 | 9100 | 1560 | 41896666.2877 | 0 | 0 | 71941834.7935 | 0 | 0 | 41896666.2179 | 30045168.4923 | 41882132.5048 | 30045168.4923 | 0 | 0 | 676607.864 | 674334.5225 |  | 2021-06-01 07:00:00 | 2024-06-30 17:00:00 | 2021-06-01 07:00:00 | 2024-06-30 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1147950 |  | NotPrmUser |  | NotPrmUser
65126 | 1383 | 6 | 0 | 6 | 6 | 0 | 6 | 5590 | 0 | 0 | 11020 | 12260 | 0 | 0 | 0 | 5050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2021-06-01 07:00:00 | 2024-12-30 17:00:00 | 2021-01-07 07:00:00 | 2024-12-30 17:00:00 | 2023-05-03 17:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
65125 | 1383 | 404 | 2141 | 4297 | 2079 | 466 | 4297 | 5720 | 17210 | 689087.864 | 11020 | 12260 | 1810340 | 37980 | 1121252.136 | 5300 | 1121252.136 | 20770 | 0 | 43682291.2877 | 0 | 0 | 121990433.1135 | 0 | 0 | 43682291.2179 | 78308141.8123 | 43667757.5048 | 78308141.8123 | 0 | 0 | 689087.864 | 686814.5225 |  | 2021-06-01 07:00:00 | 2024-12-30 17:00:00 | 2021-01-07 07:00:00 | 2024-12-30 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1810340 |  | NotPrmUser |  | NotPrmUser
67673 | 1385 | 0 | 0 | 14 | 0 | 0 | 14 | 0 | 0 | 0 | 230 | 230 | 1680 | 0 | 1680 | 230 | 1680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-05-01 17:00:00 | 2023-04-01 07:00:00 | 2023-05-01 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1680 |  | NotPrmUser |  | NotPrmUser
67592 | 1385 | 0 | 0 | 282 | 0 | 0 | 282 | 0 | 0 | 0 | 5720 | 5720 | 81470 | 1600 | 81470 | 5720 | 81470 | 1600 | 230 | 0 | 0 | 0 | 4750032 | 0 | 0 | 0 | 4750032 | 0 | 4750032 | 0 | 0 | 0 | 0 |  |  | 2023-03-30 17:00:00 | 2021-06-01 07:00:00 | 2023-03-30 17:00:00 | 2021-06-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81470 |  | NotPrmUser |  | NotPrmUser
67570 | 1385 | 0 | 0 | 56 | 0 | 0 | 56 | 0 | 0 | 0 | 1200 | 1200 | 0 | 0 | 0 | 1200 | 0 | 0 | 4450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2021-11-22 17:00:00 | 2021-07-06 07:00:00 | 2021-11-22 17:00:00 | 2021-07-06 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
67565 | 1385 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 820 | 820 | 0 | 0 | 0 | 820 | 0 | 0 | 1420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2021-09-04 17:00:00 | 2021-06-01 07:00:00 | 2021-09-04 17:00:00 | 2021-06-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
67564 | 1385 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 5950 | 5950 | 0 | 0 | 0 | 5950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-05-01 17:00:00 | 2021-06-01 07:00:00 | 2023-05-01 17:00:00 | 2021-06-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
67563 | 1385 | 0 | 0 | 362 | 1 | 0 | 361 | 0 | 0 | 0 | 5950 | 5950 | 83150 | 1600 | 83150 | 5950 | 83150 | 1600 | 0 | 0 | 0 | 0 | 4750032 | 0 | 0 | 0 | 4750032 | 0 | 4750032 | 0 | 0 | 0 | 0 |  |  | 2023-05-01 17:00:00 | 2021-06-01 07:00:00 | 2023-05-01 17:00:00 | 2021-06-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83150 |  | NotPrmUser |  | NotPrmUser
67928 | 1386 | 30 | 68 | 2349 | 30 | 68 | 2349 | 130 | 4040 | 12480 | 5430 | 5430 | 662390 | 15710 | 649910 | 5300 | 649910 | 11670 | 0 | 1785625 | 0 | 0 | 50048598.32 | 0 | 0 | 1785625 | 48262973.32 | 1785625 | 48262973.32 | 0 | 0 | 12480 | 12480 |  | 2023-03-16 07:00:00 | 2024-12-30 17:00:00 | 2023-03-16 07:00:00 | 2024-12-30 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 662390 |  | NotPrmUser |  | NotPrmUser
67927 | 1386 | 2043 | 398 | 1942 | 2043 | 398 | 1942 | 5720 | 13170 | 676607.864 | 9460 | 9460 | 1147950 | 22270 | 471342.136 | 3740 | 471342.136 | 9100 | 1560 | 41896666.26 | 0 | 0 | 71941834.78 | 0 | 0 | 41896666.2044 | 30045168.52 | 41882132.4913 | 30045168.52 | 0 | 0 | 676607.864 | 674334.5225 |  | 2021-06-01 07:00:00 | 2024-06-30 17:00:00 | 2021-06-01 07:00:00 | 2024-06-30 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1147950 |  | NotPrmUser |  | NotPrmUser
67926 | 1386 | 6 | 0 | 6 | 6 | 0 | 6 | 5590 | 0 | 0 | 11020 | 12260 | 0 | 0 | 0 | 5070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2021-06-01 07:00:00 | 2024-12-30 17:00:00 | 2021-01-07 07:00:00 | 2024-12-30 17:00:00 | 2023-05-01 17:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
67925 | 1386 | 2079 | 466 | 4297 | 2079 | 466 | 4297 | 5720 | 17210 | 689087.864 | 11020 | 12260 | 1810340 | 37980 | 1121252.136 | 5300 | 1121252.136 | 20770 | 0 | 43682291.26 | 0 | 0 | 121990433.1 | 0 | 0 | 43682291.2044 | 78308141.84 | 43667757.4913 | 78308141.84 | 0 | 0 | 689087.864 | 686814.5225 |  | 2021-06-01 07:00:00 | 2024-12-30 17:00:00 | 2021-01-07 07:00:00 | 2024-12-30 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1810340 |  | NotPrmUser |  | NotPrmUser
73305 | 1437 | 30 | 68 | 2349 | 30 | 68 | 2349 | 130 | 4040 | 12480 | 5430 | 5430 | 662390 | 15710 | 649910 | 5300 | 649910 | 11670 | 0 | 1785625 | 0 | 0 | 50048598.32 | 0 | 0 | 1785625 | 48262973.32 | 1785625 | 48262973.32 | 0 | 0 | 12480 | 12480 |  | 2023-03-16 07:00:00 | 2024-12-30 17:00:00 | 2023-03-16 07:00:00 | 2024-12-30 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 662390 |  | NotPrmUser |  | NotPrmUser
71998 | 1437 | 2043 | 398 | 1942 | 2043 | 398 | 1942 | 5380 | 13170 | 676607.864 | 9120 | 10758 | 1147950 | 22270 | 471342.136 | 3740 | 471342.136 | 9100 | 1560 | 41896666.26 | 0 | 0 | 71941834.78 | 0 | 0 | 41896666.2044 | 30045168.52 | 41882132.4913 | 30045168.52 | 0 | 0 | 676607.864 | 674334.5225 |  | 2021-07-11 00:00:00 | 2024-06-30 17:00:00 | 2021-01-01 08:00:00 | 2024-06-30 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1147950 |  | NotPrmUser |  | NotPrmUser
71997 | 1437 | 6 | 0 | 6 | 6 | 0 | 6 | 5250 | 0 | 0 | 10680 | 12318 | 0 | 0 | 0 | 5070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2021-07-11 00:00:00 | 2024-12-30 17:00:00 | 2021-01-01 08:00:00 | 2024-12-30 17:00:00 | 2023-05-01 17:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
71996 | 1437 | 2079 | 466 | 4297 | 2079 | 466 | 4297 | 5380 | 17210 | 689087.864 | 10680 | 12318 | 1810340 | 37980 | 1121252.136 | 5300 | 1121252.136 | 20770 | 0 | 43682291.26 | 0 | 0 | 121990433.1 | 0 | 0 | 43682291.2044 | 78308141.84 | 43667757.4913 | 78308141.84 | 0 | 0 | 689087.864 | 686814.5225 |  | 2021-07-11 00:00:00 | 2024-12-30 17:00:00 | 2021-01-01 08:00:00 | 2024-12-30 17:00:00 | 2023-04-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1810340 |  | NotPrmUser |  | NotPrmUser
76046 | 1441 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 240 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2024-09-29 17:00:00 | 2024-09-01 07:00:00 | 2024-09-29 17:00:00 | 2024-09-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
76045 | 1441 | 0 | 0 | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 160 | 160 | 0 | 0 | 0 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2024-09-14 17:00:00 | 2024-08-27 07:00:00 | 2024-09-14 17:00:00 | 2024-08-27 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
76044 | 1441 | 0 | 0 | 297 | 1 | 0 | 296 | 0 | 0 | 0 | 3030 | 3030 | 0 | 0 | 0 | 3030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2024-09-29 17:00:00 | 2023-10-01 07:00:00 | 2024-09-29 17:00:00 | 2023-10-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
76043 | 1441 | 0 | 0 | 128 | 0 | 0 | 128 | 0 | 0 | 0 | 1080 | 1080 | 0 | 0 | 0 | 1080 | 0 | 0 | 1690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2024-02-03 17:00:00 | 2023-10-01 07:00:00 | 2024-02-03 17:00:00 | 2023-10-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
76042 | 1441 | 0 | 0 | 68 | 0 | 0 | 68 | 0 | 0 | 0 | 300 | 300 | 0 | 0 | 0 | 300 | 0 | 0 | 2730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-11-04 17:00:00 | 2023-10-01 07:00:00 | 2023-11-04 17:00:00 | 2023-10-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
76041 | 1441 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 3030 | 3030 | 0 | 0 | 0 | 3030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2024-09-29 17:00:00 | 2023-10-01 07:00:00 | 2024-09-29 17:00:00 | 2023-10-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
76040 | 1441 | 0 | 0 | 500 | 2 | 0 | 498 | 0 | 0 | 0 | 3030 | 3030 | 0 | 0 | 0 | 3030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2024-09-29 17:00:00 | 2023-10-01 07:00:00 | 2024-09-29 17:00:00 | 2023-10-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
76345 | 1445 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2024-02-29 17:00:00 | 2024-02-28 07:00:00 | 2024-02-29 17:00:00 | 2024-02-28 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
76343 | 1445 | 0 | 0 | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 60 | 60 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2024-02-28 17:00:00 | 2024-02-21 07:00:00 | 2024-02-28 17:00:00 | 2024-02-21 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
76278 | 1445 | 0 | 0 | 294 | 0 | 0 | 294 | 0 | 0 | 0 | 1010 | 1010 | 0 | 0 | 0 | 1010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2024-02-27 17:00:00 | 2023-11-01 07:00:00 | 2024-02-27 17:00:00 | 2023-11-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
76199 | 1445 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 1030 | 1030 | 0 | 0 | 0 | 1030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2024-02-29 17:00:00 | 2023-11-01 07:00:00 | 2024-02-29 17:00:00 | 2023-11-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
76198 | 1445 | 0 | 0 | 301 | 1 | 0 | 300 | 0 | 0 | 0 | 1030 | 1030 | 0 | 0 | 0 | 1030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2024-02-29 17:00:00 | 2023-11-01 07:00:00 | 2024-02-29 17:00:00 | 2023-11-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
76494 | 1446 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0 | 0 | 240 | 240 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2025-07-16 17:00:00 | 2025-06-19 07:00:00 | 2025-07-16 17:00:00 | 2025-06-19 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
76492 | 1446 | 0 | 0 | 9 | 0 | 0 | 9 | 0 | 0 | 0 | 380 | 380 | 0 | 0 | 0 | 380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2025-07-02 17:00:00 | 2025-05-15 07:00:00 | 2025-07-02 17:00:00 | 2025-05-15 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
76427 | 1446 | 0 | 0 | 891 | 3 | 0 | 888 | 0 | 0 | 0 | 5420 | 5420 | 0 | 0 | 0 | 5420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2025-07-16 17:00:00 | 2023-10-01 07:00:00 | 2025-07-16 17:00:00 | 2023-10-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
76387 | 1446 | 0 | 0 | 128 | 0 | 0 | 128 | 0 | 0 | 0 | 1080 | 1080 | 0 | 0 | 0 | 1080 | 0 | 0 | 3980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2024-02-03 17:00:00 | 2023-10-01 07:00:00 | 2024-02-03 17:00:00 | 2023-10-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
76349 | 1446 | 0 | 0 | 68 | 0 | 0 | 68 | 0 | 0 | 0 | 300 | 300 | 0 | 0 | 0 | 300 | 0 | 0 | 5120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-11-04 17:00:00 | 2023-10-01 07:00:00 | 2023-11-04 17:00:00 | 2023-10-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
76348 | 1446 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 5420 | 5420 | 0 | 0 | 0 | 5420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2025-07-16 17:00:00 | 2023-10-01 07:00:00 | 2025-07-16 17:00:00 | 2023-10-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
76347 | 1446 | 0 | 0 | 1104 | 4 | 0 | 1100 | 0 | 0 | 0 | 5420 | 5420 | 0 | 0 | 0 | 5420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2025-07-16 17:00:00 | 2023-10-01 07:00:00 | 2025-07-16 17:00:00 | 2023-10-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
76905 | 1447 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0 | 0 | 3930 | 3930 | 0 | 0 | 0 | 3930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-30 17:00:00 | 2025-01-09 07:00:00 | 2026-04-30 17:00:00 | 2025-01-09 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
76901 | 1447 | 0 | 0 | 9 | 0 | 0 | 9 | 0 | 0 | 0 | 4150 | 4150 | 0 | 0 | 0 | 4150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-23 17:00:00 | 2024-12-08 07:00:00 | 2026-04-23 17:00:00 | 2024-12-08 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
76708 | 1447 | 0 | 0 | 891 | 1 | 0 | 890 | 0 | 0 | 0 | 7830 | 7830 | 934920 | 21600 | 934920 | 7830 | 934920 | 21600 | 0 | 0 | 0 | 0 | 59790826.4 | 0 | 0 | 0 | 59790826.4 | 0 | 59790826.4 | 0 | 0 | 0 | 0 |  |  | 2026-04-30 17:00:00 | 2023-10-01 07:00:00 | 2026-04-30 17:00:00 | 2023-10-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 934920 |  | NotPrmUser |  | NotPrmUser
76668 | 1447 | 0 | 0 | 128 | 0 | 0 | 128 | 0 | 0 | 0 | 1080 | 1080 | 0 | 0 | 0 | 1080 | 0 | 0 | 6510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2024-02-03 17:00:00 | 2023-10-01 07:00:00 | 2024-02-03 17:00:00 | 2023-10-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
76630 | 1447 | 0 | 0 | 68 | 0 | 0 | 68 | 0 | 0 | 0 | 300 | 300 | 0 | 0 | 0 | 300 | 0 | 0 | 7530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-11-04 17:00:00 | 2023-10-01 07:00:00 | 2023-11-04 17:00:00 | 2023-10-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
76629 | 1447 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 7830 | 7830 | 0 | 0 | 0 | 7830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-30 17:00:00 | 2023-10-01 07:00:00 | 2026-04-30 17:00:00 | 2023-10-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
76628 | 1447 | 0 | 0 | 1104 | 2 | 0 | 1102 | 0 | 0 | 0 | 7830 | 7830 | 934920 | 21600 | 934920 | 7830 | 934920 | 21600 | 0 | 0 | 0 | 0 | 59790826.4 | 0 | 0 | 0 | 59790826.4 | 0 | 59790826.4 | 0 | 0 | 0 | 0 |  |  | 2026-04-30 17:00:00 | 2023-10-01 07:00:00 | 2026-04-30 17:00:00 | 2023-10-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 934920 |  | NotPrmUser |  | NotPrmUser
77186 | 1448 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0 | 0 | 3890 | 3890 | 0 | 0 | 0 | 3890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-30 17:00:00 | 2025-01-14 07:00:00 | 2026-04-30 17:00:00 | 2025-01-14 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
77182 | 1448 | 0 | 0 | 9 | 0 | 0 | 9 | 0 | 0 | 0 | 3990 | 3990 | 0 | 0 | 0 | 3990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-23 17:00:00 | 2024-12-26 07:00:00 | 2026-04-23 17:00:00 | 2024-12-26 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
76989 | 1448 | 0 | 0 | 774 | 1 | 0 | 773 | 0 | 0 | 0 | 7830 | 7830 | 752260 | 20040 | 752260 | 7830 | 752260 | 20040 | 0 | 0 | 0 | 0 | 43460000 | 0 | 0 | 0 | 43460000 | 0 | 43460000 | 0 | 0 | 0 | 0 |  |  | 2026-04-30 17:00:00 | 2023-10-01 07:00:00 | 2026-04-30 17:00:00 | 2023-10-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 752260 |  | NotPrmUser |  | NotPrmUser
76949 | 1448 | 0 | 0 | 124 | 0 | 0 | 124 | 0 | 0 | 0 | 1080 | 1080 | 0 | 0 | 0 | 1080 | 0 | 0 | 6510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2024-02-03 17:00:00 | 2023-10-01 07:00:00 | 2024-02-03 17:00:00 | 2023-10-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
76911 | 1448 | 0 | 0 | 62 | 0 | 0 | 62 | 0 | 0 | 0 | 300 | 300 | 0 | 0 | 0 | 300 | 0 | 0 | 7290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-11-04 17:00:00 | 2023-10-01 07:00:00 | 2023-11-04 17:00:00 | 2023-10-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
76910 | 1448 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 7830 | 7830 | 0 | 0 | 0 | 7830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-30 17:00:00 | 2023-10-01 07:00:00 | 2026-04-30 17:00:00 | 2023-10-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
76909 | 1448 | 0 | 0 | 977 | 2 | 0 | 975 | 0 | 0 | 0 | 7830 | 7830 | 752260 | 20040 | 752260 | 7830 | 752260 | 20040 | 0 | 0 | 0 | 0 | 43460000 | 0 | 0 | 0 | 43460000 | 0 | 43460000 | 0 | 0 | 0 | 0 |  |  | 2026-04-30 17:00:00 | 2023-10-01 07:00:00 | 2026-04-30 17:00:00 | 2023-10-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 752260 |  | NotPrmUser |  | NotPrmUser
77256 | 1449 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 30 | 30 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2024-02-10 17:00:00 | 2024-02-07 07:00:00 | 2024-02-10 17:00:00 | 2024-02-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
77255 | 1449 | 0 | 0 | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 70 | 70 | 0 | 0 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2024-02-08 17:00:00 | 2024-02-01 07:00:00 | 2024-02-08 17:00:00 | 2024-02-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
77192 | 1449 | 0 | 0 | 294 | 0 | 0 | 294 | 0 | 0 | 0 | 1030 | 1030 | 0 | 0 | 0 | 1030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2024-02-06 17:00:00 | 2023-10-10 07:00:00 | 2024-02-06 17:00:00 | 2023-10-10 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
77191 | 1449 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 1060 | 1060 | 0 | 0 | 0 | 1060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2024-02-10 17:00:00 | 2023-10-10 07:00:00 | 2024-02-10 17:00:00 | 2023-10-10 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
77190 | 1449 | 0 | 0 | 301 | 1 | 0 | 300 | 0 | 0 | 0 | 1060 | 1060 | 0 | 0 | 0 | 1060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2024-02-10 17:00:00 | 2023-10-10 07:00:00 | 2024-02-10 17:00:00 | 2023-10-10 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
77518 | 1450 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0 | 0 | 5150 | 5150 | 0 | 0 | 0 | 5150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-30 17:00:00 | 2024-08-19 07:00:00 | 2026-04-30 17:00:00 | 2024-08-19 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
77514 | 1450 | 0 | 0 | 9 | 0 | 0 | 9 | 0 | 0 | 0 | 5250 | 5250 | 0 | 0 | 0 | 5250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-23 17:00:00 | 2024-07-31 07:00:00 | 2026-04-23 17:00:00 | 2024-07-31 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
77333 | 1450 | 0 | 0 | 774 | 1 | 0 | 773 | 0 | 0 | 0 | 9090 | 9090 | 752260 | 20040 | 752260 | 9090 | 752260 | 20040 | 0 | 0 | 0 | 0 | 43460000 | 0 | 0 | 0 | 43460000 | 0 | 43460000 | 0 | 0 | 0 | 0 |  |  | 2026-04-30 17:00:00 | 2023-05-01 07:00:00 | 2026-04-30 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 752260 |  | NotPrmUser |  | NotPrmUser
77294 | 1450 | 0 | 0 | 124 | 0 | 0 | 124 | 0 | 0 | 0 | 1080 | 1080 | 0 | 0 | 0 | 1080 | 0 | 0 | 7770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-09-07 17:00:00 | 2023-05-01 07:00:00 | 2023-09-07 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
77259 | 1450 | 0 | 0 | 62 | 0 | 0 | 62 | 0 | 0 | 0 | 300 | 300 | 0 | 0 | 0 | 300 | 0 | 0 | 8550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-06-04 17:00:00 | 2023-05-01 07:00:00 | 2023-06-04 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
77258 | 1450 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 9090 | 9090 | 0 | 0 | 0 | 9090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-30 17:00:00 | 2023-05-01 07:00:00 | 2026-04-30 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
77257 | 1450 | 0 | 0 | 977 | 2 | 0 | 975 | 0 | 0 | 0 | 9090 | 9090 | 752260 | 20040 | 752260 | 9090 | 752260 | 20040 | 0 | 0 | 0 | 0 | 43460000 | 0 | 0 | 0 | 43460000 | 0 | 43460000 | 0 | 0 | 0 | 0 |  |  | 2026-04-30 17:00:00 | 2023-05-01 07:00:00 | 2026-04-30 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 752260 |  | NotPrmUser |  | NotPrmUser
77783 | 1451 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0 | 0 | 5150 | 5150 | 0 | 0 | 0 | 5150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-30 17:00:00 | 2024-08-19 07:00:00 | 2026-04-30 17:00:00 | 2024-08-19 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
77787 | 1451 | 0 | 0 | 9 | 0 | 0 | 9 | 0 | 0 | 0 | 5140 | 5140 | 1920 | 0 | 1920 | 5140 | 1920 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-22 17:00:00 | 2024-08-12 07:00:00 | 2026-04-22 17:00:00 | 2024-08-12 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1920 |  | NotPrmUser |  | NotPrmUser
77779 | 1451 | 0 | 0 | 9 | 0 | 0 | 9 | 0 | 0 | 0 | 5250 | 5250 | 0 | 0 | 0 | 5250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-23 17:00:00 | 2024-07-31 07:00:00 | 2026-04-23 17:00:00 | 2024-07-31 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
77598 | 1451 | 0 | 0 | 774 | 1 | 0 | 773 | 0 | 0 | 0 | 9090 | 9090 | 752260 | 20040 | 752260 | 9090 | 752260 | 20040 | 0 | 0 | 0 | 0 | 43460000 | 0 | 0 | 0 | 43460000 | 0 | 43460000 | 0 | 0 | 0 | 0 |  |  | 2026-04-30 17:00:00 | 2023-05-01 07:00:00 | 2026-04-30 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 752260 |  | NotPrmUser |  | NotPrmUser
77559 | 1451 | 0 | 0 | 124 | 0 | 0 | 124 | 0 | 0 | 0 | 1080 | 1080 | 0 | 0 | 0 | 1080 | 0 | 0 | 7770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-09-07 17:00:00 | 2023-05-01 07:00:00 | 2023-09-07 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
77524 | 1451 | 0 | 0 | 62 | 0 | 0 | 62 | 0 | 0 | 0 | 300 | 300 | 0 | 0 | 0 | 300 | 0 | 0 | 8550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-06-04 17:00:00 | 2023-05-01 07:00:00 | 2023-06-04 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
77523 | 1451 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 9090 | 9090 | 0 | 0 | 0 | 9090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-30 17:00:00 | 2023-05-01 07:00:00 | 2026-04-30 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
77522 | 1451 | 0 | 0 | 986 | 2 | 0 | 984 | 0 | 0 | 0 | 9090 | 9090 | 754180 | 20040 | 754180 | 9090 | 754180 | 20040 | 0 | 0 | 0 | 0 | 43460000 | 0 | 0 | 0 | 43460000 | 0 | 43460000 | 0 | 0 | 0 | 0 |  |  | 2026-04-30 17:00:00 | 2023-05-01 07:00:00 | 2026-04-30 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 754180 |  | NotPrmUser |  | NotPrmUser
78325 | 1453 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0 | 0 | 120 | 120 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-30 17:00:00 | 2026-04-18 07:00:00 | 2026-04-30 17:00:00 | 2026-04-18 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
78317 | 1453 | 0 | 0 | 9 | 0 | 0 | 9 | 0 | 0 | 0 | 60 | 60 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-23 17:00:00 | 2026-04-18 07:00:00 | 2026-04-23 17:00:00 | 2026-04-18 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
78321 | 1453 | 0 | 0 | 9 | 0 | 0 | 9 | 0 | 0 | 0 | 110 | 110 | 1920 | 0 | 1920 | 110 | 1920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-16 17:00:00 | 2026-04-05 07:00:00 | 2026-04-16 17:00:00 | 2026-04-05 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1920 |  | NotPrmUser |  | NotPrmUser
78136 | 1453 | 0 | 0 | 774 | 1 | 0 | 773 | 0 | 0 | 0 | 8970 | 8970 | 752260 | 20040 | 752260 | 8970 | 752260 | 20040 | 120 | 0 | 0 | 0 | 43460000 | 0 | 0 | 0 | 43460000 | 0 | 43460000 | 0 | 0 | 0 | 0 |  |  | 2026-04-16 17:00:00 | 2023-05-01 07:00:00 | 2026-04-16 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 752260 |  | NotPrmUser |  | NotPrmUser
78097 | 1453 | 0 | 0 | 124 | 0 | 0 | 124 | 0 | 0 | 0 | 1080 | 1080 | 0 | 0 | 0 | 1080 | 0 | 0 | 7890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-09-07 17:00:00 | 2023-05-01 07:00:00 | 2023-09-07 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
78062 | 1453 | 0 | 0 | 62 | 0 | 0 | 62 | 0 | 0 | 0 | 300 | 300 | 0 | 0 | 0 | 300 | 0 | 0 | 8670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-06-04 17:00:00 | 2023-05-01 07:00:00 | 2023-06-04 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
78061 | 1453 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 9090 | 9090 | 0 | 0 | 0 | 9090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-30 17:00:00 | 2023-05-01 07:00:00 | 2026-04-30 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
78060 | 1453 | 0 | 0 | 986 | 2 | 0 | 984 | 0 | 0 | 0 | 9090 | 9090 | 754180 | 20040 | 754180 | 9090 | 754180 | 20040 | 0 | 0 | 0 | 0 | 43460000 | 0 | 0 | 0 | 43460000 | 0 | 43460000 | 0 | 0 | 0 | 0 |  |  | 2026-04-30 17:00:00 | 2023-05-01 07:00:00 | 2026-04-30 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 754180 |  | NotPrmUser |  | NotPrmUser
78332 | 1455 | 0 | 0 | 839 | 1 | 0 | 838 | 0 | 0 | 0 | 3860 | 3860 | 163200 | 2340 | 163200 | 3860 | 163200 | 2340 | 0 | 0 | 0 | 0 | 14303603.61 | 0 | 0 | 0 | 14303603.61 | 0 | 14303603.61 | 0 | 0 | 0 | 0 |  |  | 2024-10-15 17:00:00 | 2023-07-11 07:00:00 | 2024-10-15 17:00:00 | 2023-07-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163200 |  | NotPrmUser |  | NotPrmUser
78331 | 1455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
78330 | 1455 | 0 | 0 | 839 | 1 | 0 | 838 | 0 | 0 | 0 | 3860 | 3860 | 163200 | 2340 | 163200 | 3860 | 163200 | 2340 | 0 | 0 | 0 | 0 | 14303603.61 | 0 | 0 | 0 | 14303603.61 | 0 | 14303603.61 | 0 | 0 | 0 | 0 |  |  | 2024-10-15 17:00:00 | 2023-07-11 07:00:00 | 2024-10-15 17:00:00 | 2023-07-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163200 |  | NotPrmUser |  | NotPrmUser
79074 | 1457 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0 | 0 | 120 | 120 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-30 17:00:00 | 2026-04-18 07:00:00 | 2026-04-30 17:00:00 | 2026-04-18 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
79070 | 1457 | 0 | 0 | 9 | 0 | 0 | 9 | 0 | 0 | 0 | 60 | 60 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-23 17:00:00 | 2026-04-18 07:00:00 | 2026-04-23 17:00:00 | 2026-04-18 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
79066 | 1457 | 0 | 0 | 9 | 0 | 0 | 9 | 0 | 0 | 0 | 110 | 110 | 1920 | 0 | 1920 | 110 | 1920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-16 17:00:00 | 2026-04-05 07:00:00 | 2026-04-16 17:00:00 | 2026-04-05 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1920 |  | NotPrmUser |  | NotPrmUser
78885 | 1457 | 0 | 0 | 774 | 1 | 0 | 773 | 0 | 0 | 0 | 8970 | 8970 | 752260 | 20040 | 752260 | 8970 | 752260 | 20040 | 120 | 0 | 0 | 0 | 56498000.24 | 0 | 0 | 0 | 56498000.24 | 0 | 56498000.24 | 0 | 0 | 0 | 0 |  |  | 2026-04-16 17:00:00 | 2023-05-01 07:00:00 | 2026-04-16 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 752260 |  | NotPrmUser |  | NotPrmUser
78846 | 1457 | 0 | 0 | 124 | 0 | 0 | 124 | 0 | 0 | 0 | 1080 | 1080 | 0 | 0 | 0 | 1080 | 0 | 0 | 7890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-09-07 17:00:00 | 2023-05-01 07:00:00 | 2023-09-07 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
78811 | 1457 | 0 | 0 | 62 | 0 | 0 | 62 | 0 | 0 | 0 | 300 | 300 | 0 | 0 | 0 | 300 | 0 | 0 | 8670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-06-04 17:00:00 | 2023-05-01 07:00:00 | 2023-06-04 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
78810 | 1457 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 9090 | 9090 | 0 | 0 | 0 | 9090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-04-30 17:00:00 | 2023-05-01 07:00:00 | 2026-04-30 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
78809 | 1457 | 0 | 0 | 986 | 2 | 0 | 984 | 0 | 0 | 0 | 9090 | 9090 | 754180 | 20040 | 754180 | 9090 | 754180 | 20040 | 0 | 0 | 0 | 0 | 56498000.24 | 0 | 0 | 0 | 56498000.24 | 0 | 56498000.24 | 0 | 0 | 0 | 0 |  |  | 2026-04-30 17:00:00 | 2023-05-01 07:00:00 | 2026-04-30 17:00:00 | 2023-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 754180 |  | NotPrmUser |  | NotPrmUser
79080 | 1458 | 0 | 0 | 839 | 1 | 0 | 838 | 0 | 0 | 0 | 3860 | 3860 | 225610 | 4250 | 225610 | 3860 | 225610 | 4250 | 0 | 0 | 0 | 0 | 14303603.61 | 0 | 0 | 0 | 14303603.61 | 0 | 14303603.61 | 0 | 0 | 0 | 0 |  |  | 2024-10-15 17:00:00 | 2023-07-11 07:00:00 | 2024-10-15 17:00:00 | 2023-07-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225610 |  | NotPrmUser |  | NotPrmUser
79079 | 1458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
79078 | 1458 | 0 | 0 | 839 | 1 | 0 | 838 | 0 | 0 | 0 | 3860 | 3860 | 225610 | 4250 | 225610 | 3860 | 225610 | 4250 | 0 | 0 | 0 | 0 | 14303603.61 | 0 | 0 | 0 | 14303603.61 | 0 | 14303603.61 | 0 | 0 | 0 | 0 |  |  | 2024-10-15 17:00:00 | 2023-07-11 07:00:00 | 2024-10-15 17:00:00 | 2023-07-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225610 |  | NotPrmUser |  | NotPrmUser
79287 | 1460 | 0 | 0 | 296 | 0 | 0 | 296 | 0 | 0 | 0 | 3114 | 3114 | 1110 | 1480 | 1110 | 3114 | 1110 | 1480 | -2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2024-08-29 14:00:00 | 2023-05-11 10:00:00 | 2024-08-29 14:00:00 | 2023-05-11 10:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1110 |  | NotPrmUser |  | NotPrmUser
79286 | 1460 | 169 | 175 | 701 | 337 | 7 | 701 | 2936 | 0 | 1484931.9586 | 6714 | 6714 | 3136330.4549 | 8 | 1651398.4963 | 3778 | 1651398.4963 | 8 | -2 | 0 | 0 | 0 | 0 | 0 | 0 | 167835206.0756 | 251600627.9244 | 179988861.5538 | 0 | 0 | 0 | 1484931.9586 | 1651674.7165 |  | 2021-10-10 08:00:00 | 2024-08-05 14:00:00 | 2021-10-10 08:00:00 | 2024-08-05 14:00:00 | 2022-12-31 08:00:00 | 0 | 1484931.9586 | 0 | 0 | 419435834 | 251600627.9244 | 167835206.0756 | 167835206.0756 | 3136330.4549 |  | NotPrmUser |  | NotPrmUser
79285 | 1460 | 6 | 75 | 0 | 78 | 3 | 0 | 2688 | 0 | 0 | 2706 | 2720 | 0 | 0 | 0 | 18 | 0 | 0 | 3368 | 0 | 0 | 0 | 0 | 0 | 0 | 90508890.2 | 4763625.8 | 94932785.1556 | 0 | 0 | 0 | 0 | 0 |  | 2021-11-15 08:00:00 | 2023-01-03 16:00:00 | 2021-11-15 08:00:00 | 2023-01-02 10:00:00 | 2022-12-31 08:00:00 | 0 | 0 | 0 | 0 | 95272516 | 4763625.8 | 90508890.2 | 90508890.2 | 0 |  | NotPrmUser |  | NotPrmUser
79284 | 1460 | 750 | 0 | 0 | 750 | 0 | 0 | 480 | 0 | 0 | 480 | 480 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-10-10 16:00:00 | 2021-08-01 08:00:00 | 2021-10-10 16:00:00 | 2021-08-01 08:00:00 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
79283 | 1460 | 6 | 0 | 0 | 6 | 0 | 0 | 720 | 0 | 0 | 720 | 720 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-11-14 16:00:00 | 2021-08-01 08:00:00 | 2021-11-14 16:00:00 | 2021-08-01 08:00:00 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
79282 | 1460 | 38 | 0 | 38 | 38 | 0 | 38 | 2224 | 0 | 0 | 7354 | 7354 | 0 | 0 | 0 | 416 | 0 | 0 | -2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2021-08-01 08:00:00 | 2024-08-29 14:00:00 | 2021-08-01 08:00:00 | 2024-08-29 14:00:00 | 2024-06-30 14:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
79281 | 1460 | 969 | 250 | 1035 | 1209 | 10 | 1035 | 3408 | 0 | 1484931.9586 | 7354 | 7354 | 3137440.4549 | 1488 | 1652508.4963 | 3946 | 1652508.4963 | 1488 | -2 | 0 | 0 | 0 | 0 | 0 | 0 | 258344096.2756 | 256364253.7244 | 274921646.7094 | 0 | 0 | 0 | 1484931.9586 | 1651674.7165 |  | 2021-08-01 08:00:00 | 2024-08-29 14:00:00 | 2021-08-01 08:00:00 | 2024-08-29 14:00:00 | 2022-12-31 08:00:00 | 0 | 1484931.9586 | 0 | 0 | 514708350 | 256364253.7244 | 258344096.2756 | 258344096.2756 | 3137440.4549 |  | NotPrmUser |  | NotPrmUser
80837 | 1461 | 0 | 0 | 262 | 0 | 0 | 262 | 0 | 0 | 0 | 1079 | 1079 | 0 | 0 | 0 | 1079 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2021-12-16 17:00:00 | 2021-08-14 08:00:00 | 2021-12-16 17:00:00 | 2021-08-14 08:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
80836 | 1461 | 0 | 0 | 7 | 1 | 0 | 6 | 0 | 0 | 0 | 1079 | 1079 | 0 | 0 | 0 | 1079 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2021-12-16 17:00:00 | 2021-08-14 08:00:00 | 2021-12-16 17:00:00 | 2021-08-14 08:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
80835 | 1461 | 0 | 0 | 269 | 1 | 0 | 268 | 0 | 0 | 0 | 1079 | 1079 | 0 | 0 | 0 | 1079 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2021-12-16 17:00:00 | 2021-08-14 08:00:00 | 2021-12-16 17:00:00 | 2021-08-14 08:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
80987 | 1462 | 0 | 0 | 839 | 1 | 0 | 838 | 0 | 0 | 0 | 3860 | 3860 | 225610 | 4250 | 225610 | 3860 | 225610 | 4250 | 0 | 0 | 0 | 0 | 14303603.61 | 0 | 0 | 0 | 14303603.61 | 0 | 14303603.61 | 0 | 0 | 0 | 0 |  |  | 2024-10-15 17:00:00 | 2023-07-11 07:00:00 | 2024-10-15 17:00:00 | 2023-07-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225610 |  | NotPrmUser |  | NotPrmUser
80986 | 1462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
80985 | 1462 | 0 | 0 | 839 | 1 | 0 | 838 | 0 | 0 | 0 | 3860 | 3860 | 225610 | 4250 | 225610 | 3860 | 225610 | 4250 | 0 | 0 | 0 | 0 | 14303603.61 | 0 | 0 | 0 | 14303603.61 | 0 | 14303603.61 | 0 | 0 | 0 | 0 |  |  | 2024-10-15 17:00:00 | 2023-07-11 07:00:00 | 2024-10-15 17:00:00 | 2023-07-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225610 |  | NotPrmUser |  | NotPrmUser
82593 | 1463 | 0 | 0 | 839 | 0 | 0 | 839 | 0 | 0 | 0 | 5190 | 5190 | 1250940 | 4920 | 1250940 | 5190 | 1250940 | 4920 | 0 | 0 | 0 | 0 | 129353453.42 | 0 | 0 | 0 | 129353453.42 | 0 | 129353453.42 | 0 | 0 | 0 | 0 |  |  | 2026-05-25 17:00:00 | 2024-09-08 07:00:00 | 2026-05-25 17:00:00 | 2024-09-08 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250940 |  | NotPrmUser |  | NotPrmUser
82592 | 1463 | 0 | 0 | 839 | 0 | 0 | 839 | 0 | 0 | 0 | 4550 | 4550 | 911710 | 4920 | 911710 | 4550 | 911710 | 4920 | 1680 | 0 | 0 | 0 | 91910143.1 | 0 | 0 | 0 | 91910143.1 | 0 | 91910143.1 | 0 | 0 | 0 | 0 |  |  | 2025-11-04 17:00:00 | 2024-05-05 07:00:00 | 2025-11-04 17:00:00 | 2024-05-05 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 911710 |  | NotPrmUser |  | NotPrmUser
82591 | 1463 | 0 | 0 | 1678 | 0 | 0 | 1678 | 0 | 0 | 0 | 5200 | 5200 | 820940 | 9840 | 820940 | 5200 | 820940 | 9840 | 1730 | 0 | 0 | 0 | 79409029.3203 | 0 | 0 | 0 | 79409029.3203 | 0 | 79409029.3203 | 0 | 0 | 0 | 0 |  |  | 2025-10-29 17:00:00 | 2024-02-07 07:00:00 | 2025-10-29 17:00:00 | 2024-02-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 820940 |  | NotPrmUser |  | NotPrmUser
82590 | 1463 | 0 | 0 | 839 | 0 | 0 | 839 | 0 | 0 | 0 | 4440 | 4440 | 760120 | 4920 | 760120 | 4440 | 760120 | 4920 | 2490 | 0 | 0 | 0 | 76876265.32 | 0 | 0 | 0 | 76876265.32 | 0 | 76876265.32 | 0 | 0 | 0 | 0 |  |  | 2025-07-31 17:00:00 | 2024-02-07 07:00:00 | 2025-07-31 17:00:00 | 2024-02-07 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 760120 |  | NotPrmUser |  | NotPrmUser
82589 | 1463 | 0 | 0 | 1678 | 1 | 0 | 1677 | 0 | 0 | 0 | 5730 | 5730 | 555000 | 10170 | 555000 | 5730 | 555000 | 10170 | 3000 | 0 | 0 | 0 | 77850670.5804 | 0 | 0 | 0 | 77850670.5804 | 0 | 77850670.5804 | 0 | 0 | 0 | 0 |  |  | 2025-05-28 17:00:00 | 2023-07-11 07:00:00 | 2025-05-28 17:00:00 | 2023-07-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 555000 |  | NotPrmUser |  | NotPrmUser
81188 | 1463 | 0 | 0 | 12 | 2 | 0 | 10 | 0 | 0 | 0 | 8730 | 8730 | 0 | 0 | 0 | 8730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-05-25 17:00:00 | 2023-07-11 07:00:00 | 2026-05-25 17:00:00 | 2023-07-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
81187 | 1463 | 0 | 0 | 5885 | 3 | 0 | 5882 | 0 | 0 | 0 | 8730 | 8730 | 4298710 | 34770 | 4298710 | 8730 | 4298710 | 34770 | 0 | 0 | 0 | 0 | 455399561.7407 | 0 | 0 | 0 | 455399561.7407 | 0 | 455399561.7407 | 0 | 0 | 0 | 0 |  |  | 2026-05-25 17:00:00 | 2023-07-11 07:00:00 | 2026-05-25 17:00:00 | 2023-07-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4298710 |  | NotPrmUser |  | NotPrmUser
83800 | 1464 | 0 | 0 | 839 | 0 | 0 | 839 | 0 | 0 | 0 | 7200 | 7200 | 1250940 | 4920 | 1250940 | 7200 | 1250940 | 4920 | 0 | 0 | 0 | 0 | 129353453.42 | 0 | 0 | 0 | 129353453.42 | 0 | 129353453.42 | 0 | 0 | 0 | 0 |  |  | 2026-07-10 17:00:00 | 2024-02-17 07:00:00 | 2026-07-10 17:00:00 | 2024-02-17 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250940 |  | NotPrmUser |  | NotPrmUser
83599 | 1464 | 0 | 0 | 839 | 0 | 0 | 839 | 0 | 0 | 0 | 6380 | 6380 | 911710 | 4920 | 911710 | 6380 | 911710 | 4920 | 230 | 0 | 0 | 0 | 91910143.1 | 0 | 0 | 0 | 91910143.1 | 0 | 91910143.1 | 0 | 0 | 0 | 0 |  |  | 2026-06-14 17:00:00 | 2024-05-01 07:00:00 | 2026-06-14 17:00:00 | 2024-05-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 911710 |  | NotPrmUser |  | NotPrmUser
83198 | 1464 | 0 | 0 | 1678 | 0 | 0 | 1678 | 0 | 0 | 0 | 6610 | 6610 | 820940 | 9840 | 820940 | 6610 | 820940 | 9840 | 720 | 0 | 0 | 0 | 79409029.3203 | 0 | 0 | 0 | 79409029.3203 | 0 | 79409029.3203 | 0 | 0 | 0 | 0 |  |  | 2026-04-12 17:00:00 | 2024-02-01 07:00:00 | 2026-04-12 17:00:00 | 2024-02-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 820940 |  | NotPrmUser |  | NotPrmUser
82997 | 1464 | 0 | 0 | 839 | 0 | 0 | 839 | 0 | 0 | 0 | 6070 | 6070 | 760120 | 4920 | 760120 | 6070 | 760120 | 4920 | 1260 | 0 | 0 | 0 | 76876265.32 | 0 | 0 | 0 | 76876265.32 | 0 | 76876265.32 | 0 | 0 | 0 | 0 |  |  | 2026-02-02 17:00:00 | 2024-02-01 07:00:00 | 2026-02-02 17:00:00 | 2024-02-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 760120 |  | NotPrmUser |  | NotPrmUser
82596 | 1464 | 0 | 0 | 1678 | 1 | 0 | 1677 | 0 | 0 | 0 | 6410 | 6410 | 871300 | 9600 | 871300 | 6410 | 871300 | 9600 | 2670 | 0 | 0 | 0 | 77850670.5804 | 0 | 0 | 0 | 77850670.5804 | 0 | 77850670.5804 | 0 | 0 | 0 | 0 |  |  | 2025-08-20 17:00:00 | 2023-07-11 07:00:00 | 2025-08-20 17:00:00 | 2023-07-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 871300 |  | NotPrmUser |  | NotPrmUser
82595 | 1464 | 0 | 0 | 12 | 2 | 0 | 10 | 0 | 0 | 0 | 9080 | 9080 | 0 | 0 | 0 | 9080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2026-07-10 17:00:00 | 2023-07-11 07:00:00 | 2026-07-10 17:00:00 | 2023-07-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
82594 | 1464 | 0 | 0 | 5885 | 3 | 0 | 5882 | 0 | 0 | 0 | 9080 | 9080 | 4615010 | 34200 | 4615010 | 9080 | 4615010 | 34200 | 0 | 0 | 0 | 0 | 455399561.7407 | 0 | 0 | 0 | 455399561.7407 | 0 | 455399561.7407 | 0 | 0 | 0 | 0 |  |  | 2026-07-10 17:00:00 | 2023-07-11 07:00:00 | 2026-07-10 17:00:00 | 2023-07-11 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4615010 |  | NotPrmUser |  | NotPrmUser
84005 | 1466 | 0 | 0 | 51 | 0 | 0 | 51 | 0 | 0 | 0 | 2300 | 2300 | 0 | 0 | 0 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2024-11-17 17:00:00 | 2024-04-02 07:00:00 | 2024-11-17 17:00:00 | 2024-04-02 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
84004 | 1466 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 196 | 196 | 0 | 0 | 0 | 196 | 0 | 0 | 284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2024-04-21 13:00:00 | 2024-04-02 07:00:00 | 2024-04-21 13:00:00 | 2024-04-02 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
84003 | 1466 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0 | 0 | 300 | 300 | 0 | 0 | 0 | 300 | 0 | 0 | 284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2024-04-02 07:00:00 | 2024-03-03 07:00:00 | 2024-04-02 07:00:00 | 2024-03-03 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
84002 | 1466 | 0 | 0 | 59 | 0 | 0 | 59 | 0 | 0 | 0 | 2600 | 2600 | 0 | 0 | 0 | 2600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2024-11-17 17:00:00 | 2024-03-03 07:00:00 | 2024-11-17 17:00:00 | 2024-03-03 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
84056 | 1468 | 0 | 0 | 55 | 0 | 0 | 55 | 0 | 0 | 0 | 2300 | 2300 | 0 | 0 | 0 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2024-10-18 17:00:00 | 2024-03-03 07:00:00 | 2024-10-18 17:00:00 | 2024-03-03 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
84055 | 1468 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 2300 | 2300 | 0 | 0 | 0 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2024-10-18 17:00:00 | 2024-03-03 07:00:00 | 2024-10-18 17:00:00 | 2024-03-03 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
84054 | 1468 | 0 | 0 | 57 | 0 | 0 | 57 | 0 | 0 | 0 | 2300 | 2300 | 0 | 0 | 0 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2024-10-18 17:00:00 | 2024-03-03 07:00:00 | 2024-10-18 17:00:00 | 2024-03-03 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
84080 | 1469 | 0 | 1 | 0 | 0 | 1 | 0 | 30 | 0 | 0 | 110 | 100 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 200 | 1000 | 300 | 1000 | 0 | 0 | 0 | 0 |  | 2024-06-01 07:00:00 | 2024-06-11 17:00:00 | 2024-06-01 07:00:00 | 2024-06-12 17:00:00 | 2024-06-04 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser
84082 | 1471 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 100 | 100 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 |  |  | 2024-06-11 17:00:00 | 2024-06-01 07:00:00 | 2024-06-11 17:00:00 | 2024-06-01 07:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | NotPrmUser |  | NotPrmUser

## Query
SELECT t.*, ROWID FROM SUMTASK t