## Task_Calculation
task_id | proj_id | wbs_id | Activity_%_Complete | Performance_%_Complete | Budgeted_Labor_Cost | Budgeted_Nonlabor_Cost | Budgeted_Material_Cost | Budgeted_Expenses_Cost | Budget_Total_Cost | Remaining_Labor_Cost | Remaining_Nonlabor_Cost | Remaining_Material_Cost | Remaining_Expenses_Cost | Remaining_Total_Cost | Actual_Labor_Cost | Actual_Nonlabor_Cost | Actual_Material_Cost | Actual_Expenses_Cost | Actual_Total_Cost | At_Completion_Labor_Cost | At_Completion_Nonlabor_Cost | At_Completion_Material_Cost | At_Completion_Expenses_Cost | At_Completion_Total_Cost | Earned_Value_Cost | Actual_Cost | Estimate_To_Complete | Budget_At_Completion | Estimate_At_Completion_Cost
313464 | 1474 | 84085 | 27 | 27 | 0 | 0 | 0 | 1000 | 1000 | 0 | 0 | 0 | 800 | 800 | 0 | 0 | 0 | 200 | 200 | 0 | 0 | 0 | 1000 | 1000 | 270 | 200 | 800 | 1000 | 1000
313465 | 1474 | 84085 | 23 | 23 | 0 | 0 | 0 | 1000 | 1000 | 0 | 0 | 0 | 780 | 780 | 0 | 0 | 0 | 520 | 520 | 0 | 0 | 0 | 1300 | 1300 | 230 | 520 | 780 | 1000 | 1300
313466 | 1474 | 84085 | 25 | 25 | 250 | 250 | 250 | 250 | 1000 | 150 | 175 | 250 | 175 | 750 | 150 | 75 | 200 | 75 | 500 | 300 | 250 | 450 | 250 | 1250 | 250 | 500 | 750 | 1000 | 1250